## Notes
MOEN-IMS bulk upload — extraction notes (source reports: latest per region, July 2026)
FILES PRODUCED
community_progress_bulk.csv | Kobo/seed format. 536 communities: Greater Accra 90, Eastern 146, Upper West 106, Volta 95, North East 99. Load with: python manage.py seed_sites_from_kobo (point DATA_FILE at this csv) or adapt.
boq_upload.xlsx | BoQ Template sheet matches the system upload template. Material Mapping sheet lists every distinct material name: exact/fuzzy = safe to upload; unmatched = add to inventory first or correct the name.
upload_review_notes.xlsx | This file. Statuses, completion %, and data that could not be mapped to counts.
SOURCES USED (cumulative snapshots)
Greater Accra + Eastern | Summary Progress report April 2026 GAR-ER.xlsx + Material Reconcillation List April 2026.xlsx (consultant: Jondee Limited)
Upper West | NOVEMBER 2025 REPORT.docx per-contractor works tables
Volta / Oti | DONAB ENG April 2026 narrative — counts derived from prose statements; ambiguous sentences in Volta_Unparsed sheet were NOT counted
North East | Sbinc end-of-year Dec 2025 PDF works matrix + material reconciliation (consultant: SBINC Consult)
Upper East | MARCH 2026 report: community register with package numbers & status (UE_Register sheet) — no per-community works counts reported
Bono East / Ashanti | Q4 2025 reports: quarterly pole/transformer installs + community status (no cumulative counts)
Upper East (2025 fill) | JULY 2025 PDF: per-community completion % and METERS CONNECTED (mapped to cs_1ph). Package numbers joined from the March 2026 register.
Bono East / Ashanti (2025 fill) | DECEMBER 2025 registers: community + package + contractor (+% where stated). No physical counts — count columns blank.
Savannah / Northern (2025 fill) | NOV 2025 per-community % table + completed list. Region assigned by district lookup — verify Savannah vs Northern.
Bono / Ahafo (2025 fill) | Q3 2025 commissioned-transformer lists → tx_commissioned counts for those communities.
Central (2025 fill) | DEC 2025 per-community % — community/contractor rows only, counts blank.
Western / Western North | Only contractor-level % reported all year — no per-community data exists (Percent_Complete sheet).
MAPPING ASSUMPTIONS
ht_strung / lv_strung | Reports record SPANS strung; MOEN-IMS reads poles strung. Values carried over as reported.
tx_dressed | Mapped from "Transformer dressed/installed/delivered-to-site c/w" (feeds transformers_installed).
cs_1ph | Upper West reports one combined "customers connected" figure — recorded as 1-phase.
Volta counts | Sum of quantified prose statements 2016–2026; treat as minimums. 114 ambiguous sentences excluded (see Volta_Unparsed).
North East works | Some rows report supplied==planted==dressed; figures as printed in the consultant matrix.
BOQ contract quantities | From material reconciliation "contract" column; quantity_received = "supplied". GA-E is per community; North East is per package (community blank).
Route-length lines | "HT/LV Distance (km)" and "Voltage Level" lines skipped — attributes, not materials.
STANDARD-KIT BOQ ROWS (Option B)
What | 15 REAL inventory items per community for the 9 regions with no material reconciliation — 23,025 rows for 1,535 communities. Kit = 5 target-drivers (11 Meter Concrete Pole [HT], 9M Wooden Pole [LV], 33/0.433 100KVA 3-ph transformer, 1-ph + 3-ph meters) + the 10 support materials present in >=85% of GA-E communities with actuals.
Quantities | contract_quantity = 0 except Upper West, where known contract figures were placed on the representative pole/transformer/meter lines. quantity_received = 0 everywhere. Bulk-edit real quantities (and swap pole/transformer types per community if different) when reconciliations arrive.
Pole types | HT=11m Concrete, LV=9m Wooden, TX=33/0.433 100KVA are REPRESENTATIVE choices — actual types per community are unknown from the reports. Swapping the item later keeps targets correct as long as the name stays a pole/transformer/meter.
Upload parts | boq_upload.xlsx is the master. Upload the 4 part files instead (part1 actuals, parts 2-4 kit regions) — one 30k-row upload risks a gateway timeout.
Consultants | Volta=Donab, Bono East/Ashanti=Powerdok, Central=ARQ; others marked TBD — correct before or after upload.
BEFORE UPLOADING
1. | Fix unmatched materials (Material Mapping sheet, red rows) — add to inventory or rename. Kit lines need NO new inventory items (all real).
2. | Communities must exist (07_Communities template) with consistent spelling before progress upload.
3. | Upper East register (UE_Register) has package numbers usable to backfill package_number for UE communities.
4. | quantity_received in BoQ counts as delivered-to-contractor per reports, not site receipts.
5. | Duplicate material lines within a community were SUMMED (the system upserts on item+package+community); zero upsert-key collisions remain.

## UE_Register
contractor | package_number | district | community | project | status
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Anafobiisi Zuin | SHEP-4 | completed
Albak Legacy Enterprise | SHEP-4-UER-BWD-ALE-10-2020 | Bawku West | Alarigo | SHEP-4 | Works in progress
Albak Legacy Enterprise | SHEP-4-UER-BWD-ALE-10-2021 | Bawku West | Azuwera | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Terkura -Pungu | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Wuru | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Kolna/Biu Ext | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Kolna Biu | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Tampol A Ext | SHEP-4 | Works in progress
3 Coolman Company Limited | SHEP-4-UER-KNED-3CCL-10-19 | Kasena Nankana East | Kologo Natire | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Akuka | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Azaazi (Atosala | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Mayoro - Wanchoko (Ext | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Gumango Basic Sch | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Lower Gumango | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Mayoro Wanjagina | SHEP-4 | Works in progress
A.A. Warncharn Company Limited | SHEP-4-UER-KNED-AAWCL-10-19 | Kasena Nankana East | Bania | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Kazensa | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Zuasa | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Yadem | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Guluk | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Abaayeri | SHEP-4 | Works in progress
Abeo Electrical Eng. Wks Ltd. | SHEP-4-BSD-UER-AEEWL-09-16 | Builsa South | Tuadem | SHEP-4 | Works in progress
Adda Elect. Services Ltd. | SHEP-4-UER-BSL-ADDA-16 | Builsa South | Fumbisi-Naadema | SHEP-4 | Works in progress
Adda Elect. Services Ltd. | SHEP-4-UER-BSL-ADDA-16 | Builsa South | Baasa-Puing | SHEP-4 | Works in progress
Adda Elect. Services Ltd. | SHEP-4-UER-BSL-ADDA-16 | Builsa South | Wupiasa | SHEP-4 | Works in progress
Adda Elect. Services Ltd. | SHEP-4-UER-BSL-ADDA-16 | Builsa South | Bachongsa-Nyanbisa | SHEP-4 | Works in progress
Adda Elect. Services Ltd. | SHEP-4-UER-BSL-ADDA-16 | Builsa South | Gbedemazeng | SHEP-4 | Works in progress
Alback legacy Enterprise | SHEP-4-UER-BTD-ALE-08-2020 | Bolga/Talensi | Kumbiligo | SHEP-4 | Works in progress
Alback legacy Enterprise | SHEP-4-UER-BTD-ALE-08-2020 | Bolga/Talensi | Dorong/Kembiisi/Daboting | SHEP-4 | Works in progress
Alback legacy Enterprise | SHEP-4-UER-BTD-ALE-08-2020 | Bolga/Talensi | Pusu Namongo | SHEP-4 | Works in progress
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Tirago | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Iddi | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Agon-Nara | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Tinogo | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Nin-Sarko | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Nara Sung | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Sakperi-Natinga | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Sarabogo | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Avondango Chief's Palace | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Zuulugo | SHEP-4 | Works are nearing completion
Ampohblay Will Ltd | SHEP-UER-B/KNWDs-AWL-10-14 | Binduri | Avondango Market | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Ayone | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Ayone Basic School | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Konkua Doone | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Avire Doone | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Azenko Doone Ayakarike | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Azeka Doone | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Tanpeliga | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Adingo Doone | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UR-BUDIC-14-1 | Bongo | Ayansum Doone | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-16 | Talensi | Namoranteng | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Talensi | Santeng | SHEP-4 | Works Completed
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Talensi | Tenzuk | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Talensi | Duusi-Tindongo | SHEP-4 | Works are nearing completion
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Talensi | Yaale | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Talensi | Tampoog | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-TAD-BUDIC-17 | Kasena Nankana West. | Azinzoka | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-BUDIC-16 | Kasena Nankana West. | Gonnum Daboo | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-BUDIC-16 | Kasena Nankana West. | Gonnum Aku-A | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-BUDIC-16 | Kasena Nankana West. | Zampeego/Apibisi | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-UE-BUDIC-16 | Kasena Nankana West. | Tintuumbisi | SHEP-4 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Lower Nangalikinnia No. 1 | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Lower Nangalikinnia No. 2 | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Janania-Gaani | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Kasinia-Korania | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Kworise-Korania | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Avbisi/Dozongo | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Geribisi | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Akumbisi | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Kundalsa-Biu | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Jaagu-Biu | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Gunsa | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Upper Gaani | SHEP-5 | Works in progress
Budic Engineering Ltd. | SHEP-5-KNE-KWA-16 | Kasena Nankana East | Lower Gaani | SHEP-5 | Works in progress
Buhas Enterprise Limited | SHEP-4-KNW-BEL-16 | Kasena Nankana West | Gumongo | SHEP-4 | Works in progress
Buhas Enterprise Limited | SHEP-4-KNW-BEL-16 | Kasena Nankana West | Alimbila | SHEP-4 | Works in progress
Buhas Enterprise Limited | SHEP-4-KNW-BEL-16 | Kasena Nankana West | Nabango Nyongo | SHEP-4 | Works in progress
Buhas Enterprise Limited | SHEP-4-KNW-BEL-16 | Kasena Nankana West | Dazongo | SHEP-4 | Works in progress
Daniel Abatara Elect. | SHEP-4-UER-BD-DAEW-05-20 | Bongo | Asabire | SHEP-4 | Works in progress
Daniel Abatara Elect. | SHEP-4-UER-BD-DAEW-05-20 | Bongo | Asabire Doone | SHEP-4 | Works in progress
Daniel Abatara Elect. | SHEP-4-UER-BD-DAEW-05-20 | Bongo | Bungu | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Kasiesa-Yemona | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Kasiesa-chief’s Palace | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Kasiesa-Yipaala | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Kasiesa-Sinsangsa | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Kanjarga-Logvogsa | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Doninga | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Zamsa | SHEP-4 | Works in progress
Daniel Abatara Elect. Wks | SHEP-4-UER-BSD-DAEL-16 | Builsa South | Uwasa-Zuasa | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Zopeli | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Alotam/Wiriguud | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Teshie Natinga (Extension) | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Kpalsako | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Tang Dabote | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Ayad/Kinab-Dabote | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Toende | SHEP-4 | Works in progress
Dokmel Elect. Eng. Works | SHEP-4-UER-BWD-DEEWD-16 | Bawku West | Wiiga/Gunga | SHEP-4 | Works in progress
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Palgaa | SHEP-5 | Works in progress
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Tongo-Zubeogo | SHEP-5 | Works in progress
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Tongo-Yaapas | SHEP-5 | Works in progress
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Tongo-Zoo | SHEP-5 | Works in progress
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Shia | SHEP-5 | Works Completed
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Nungu | SHEP-5 | Community relocated as a of result mining project
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Nungu-Biengo | SHEP-5 | Community relocated as a of result mining project
E. K. Asare Enterprise Ltd. | SHEP-5-TD-ASARE-16 | Talensi | Duusi-Natinga | SHEP-5 | Works in progress
E. K. Enterprise | SHEP-4-UER-BD-EKAEL-05-20 | Talensi/Bolga | Zaare | SHEP-4 | Works in progress
E. K. Enterprise | SHEP-4-UER-BD-EKAEL-05-20 | Talensi/Bolga | Aware Doone Ext | SHEP-4 | Works are nearing completion
E.K. Asare Enterprise | SHEP-4-UER-BD-E.K-17 | Bongo | Apuwongo-Tingre | SHEP-4 | Works in progress
E.K. Asare Enterprise | SHEP-4-UER-BD-E.K-17 | Bongo | Yekine Tingre | SHEP-4 | Works in progress
E.K. Asare Enterprise | SHEP-4-UER-BD-E.K-17 | Bongo | Boko Azumbuo | SHEP-4 | Works in progress
E.K. Asare Enterprise | SHEP-4-UER-BD-E.K-17 | Bongo | Boko Asackow | SHEP-4 | Works in progress
E.K. Asare Enterprise | SHEP-4-UER-BD-E.K-17 | Bongo | Apuwongo Zui | SHEP-4 | Works in progress
E.K. Asare Enterprise | SHEP-4-UER-BD-E. K-17 | Bongo | Boko Kumabilgo | SHEP-4 | Works in progress
Elios Company Ltd. | SHEP-4-UER-BD-ECL-17 | Binduri | Dabuugu/Kukparigu | SHEP-4 | Works in progress
Elios Company Ltd. | SHEP-4-UER-BD-ECL-17 | Binduri | Dulnatinga/Agbelgimvoos | SHEP-4 | Works in progress
Elios Company Ltd. | SHEP-4-UER-BD-ECL-17 | Binduri | Boko #2 | SHEP-4 | Works Completed
Elios Company Ltd. | SHEP-4-UER-BD-ECL-17 | Binduri | Bazua Newtown (ext)/Biaka | SHEP-4 | Works in progress
Elios Company Ltd. | SHEP-4-UER-BD-ECL-17 | Binduri | Sakparna Tinga | SHEP-4 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Kpukparibuliga | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Atamidabog | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Mengnatim | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Yousbara | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Yousbara #1 | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Tendana | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Tendana-Yabrago #2 | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Tendana-Yabrago #1 | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Karateshie-Nanteng | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Karateshie-Basic School | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Karateshie-Kparasako | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Karateshie-Natinga Old | SHEP-5 | Works in progress
EX-TEE Electricals Ltd. | SHEP-5-UER-GTD-EX-TEE-16 | Garu Tempane | Bugri Abarsandabogun/Ku | SHEP-5 | Works in progress
Farprise Limited | SHEP-4-UER-GD-FL-05-2019 | Garu | Samaduri | SHEP-4 | Works in progress
Farprise Limited | SHEP-4-UER-GD-FL-05-2019 | Garu | Farfar Sabkuan | SHEP-4 | Works in progress
Farprise Limited | SHEP-4-UER-GD-FL-05-2019 | Garu | Vambra | SHEP-4 | Works in progress
Farprise Limited | SHEP-4-UER-GD-FL-05-2019 | Garu | Georin Aloko | SHEP-4 | Works in progress
Farprise Limited | SHEP-4-UER-GD-FL-05-2019 | Garu | Songuuri | SHEP-4 | Works in progress
Guuru Link Limited | SHEP-4-UE-BD-GLL-03-2020 | Binduri | Bansi Central | SHEP-4 | Works are nearing completion
Guuru Link Limited | SHEP-4-UE-BD-GLL-03-2020 | Binduri | Natinga/Bansisakpa Natinga | SHEP-4 | Works are nearing completion
Happy World of Techn. Ltd. | SHEP-4-BD-HWOTL | Binduri | Yarigungu-Natinga | SHEP-4 | Works completed
Happy World of Techn. Ltd. | SHEP-4-BD-HWOTL | Binduri | Yarigungu-Asikonde | SHEP-4 | Works completed
Happy World of Techn. Ltd. | SHEP-4-BD-HWOTL | Binduri | Bakanga | SHEP-4 | Works completed
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Teshnatinga/Terago | SHEP-4 | Works in progress
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Saratinga-Teshnatinga | SHEP-4 | Works in progress
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Gareke #1 - Teshnatinga | SHEP-4 | works are nearing complete
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Gareke #2 - Teshnatinga | SHEP-4 | works are nearing complete
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Silteega | SHEP-4 | Works in progress
Happy World of Techn. Ltd. | SHEP-4-UER-PD-HWTL-09-16 | Pusiga | Poanaba | SHEP-4 | Works in progress
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 | Talensi/Pusiga | GAARE BONG | SHEP-4 | Works in progress
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 | Talensi/Pusiga | GAARE LOOTE/ZOORE | SHEP-4 | Works in progress
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 | Talensi/Pusiga | GAARE MARKET | SHEP-4 | Work are nearing complete
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 | Talensi/Pusiga | GBANI DATOK/TASOYERI | SHEP-4 | Works in progress
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 | Talensi/Pusiga | GBANI DANYIRE | SHEP-4 | Works in progress
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 |  | GBEWAA NO.2/SIGNOGO | SHEP | works are nearing complete
Happy World of Technology Ltd. | SHEP-4/THENGASHEP-UER-TD&HWTL-08-19 |  | GBEWAA NO.1 | SHEP | works are nearing complete
Hassanash Nash Ventures | SHEP-4-UER-TD-HNVL-06-20 | Garu | Zansibuliga 2 | SHEP-4 | Works in progress
Hassanash Nash Ventures | SHEP-4-UER-TD-HNVL-06-20 | Garu | Zansibuliga 3 | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa South | Vandema | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa South | Nandem/Damburinsa | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa South | Kalaasa | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa South | Fumbisi Extension | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa North | Kandem | SHEP-4 | Works in progress
Hassanash Ventures | SHEP-4-BS&ND-UER-HV-11-16 | Builsa North | Nyansa | SHEP-4 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Kpaliga | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Sugure | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Yampan-Lalsaa Basic Sch. | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Yampan-Lalsaa | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Yampan-Lalsaa Tingre | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Kukrabod | SHEP-5 | Works in progress
Ibbecow Company Limited | SHEP-5-BM-ICL-16 | Bawku | Yakin | SHEP-5 | Works in progress
Ibbecow Company Ltd. | SHEP-UER-PD-14 | Pusiga | Kulungugu Chamata | SHEP-4 | Works are nearing completion
Ibbecow Company Ltd. | SHEP-UER-PD-14 | Pusiga | Kulungugu Natinga | SHEP-4 | Works are nearing completion
Ibbecow Company Ltd. | SHEP-UER-PD-14 | Pusiga | Kulungugu Cinkon | SHEP-4 | Works are nearing completion
Ibbecow Company Ltd. | SHEP-UER-PD-14 | Pusiga | Kulungugu CEPS | SHEP-4 | Works are nearing completion
Ibbecow Company Ltd. | SHEP-UER-PD-14 | Pusiga | Kulungugu Main Town | SHEP-4 | Works are nearing completion
Ike Electrical Co. Ltd | SHEP-4-UER-BD-REL-09-19 | Binduri | Sakpari Central | SHEP-4 | Works in progress
Ike Electrical Co. Ltd | SHEP-4-UER-BD-REL-09-19 | Binduri | Sakpari-Kumpalgoga | SHEP-4 | Works in progress
Ike Electrical Co. Ltd | SHEP-4-UER-BD-REL-09-19 | Binduri | Sakpari-Bakango | SHEP-4 | Works in progress
Ike Electrical Co. Ltd | SHEP-4-UER-BD-REL-09-19 | Binduri | Sakpari-Poayamire | SHEP-4 | Works in progress
ILA Eng. Ltd | SHEP-4-UER-BSD-DAEL-16 | Bongo | Akamo | SHEP-4 | Works in progress
ILA Eng. Ltd | SHEP-4-UER-BSD-DAEL-16 | Bongo | Yaka | SHEP-4 | Works in progress
ILA Eng. Ltd | SHEP-4-UER-BSD-DAEL-16 | Bongo | Akundoo chief's Palace | SHEP-4 | Works in progress
ILA Eng. Ltd | SHEP-4-UER-BSD-DAEL-16 | Bongo | Akundoo-kiibo/Apeliga | SHEP-4 | Works in progress
ILA Eng. Ltd | SHEP-4-UER-BSD-DAEL-16 | Bongo | Asakule | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Tendaatengen | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Bansi-Barigu | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Gotesaliga | SHEP-4 | Works are nearing completion
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Tinogo | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Asintapelug | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Aniisi (Ext) | SHEP-4 | Works in progress
J - Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Binduri | Bawk-Sapeliga | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Punelingo | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Gunwoko/Basengo-More | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Tundoogo/Tingino | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Gunwoko No. 2/Bigkum | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Pogitam (Ext) | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Tangasia | SHEP-4 | Works in progress
Jetumah Electrical Works Ltd. | SHEP-4-NR-KNVD-JEWL-10-16 | Kasena Nankana | Wugingo/Basengo | SHEP-4 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Ziki Asobilla | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Dangunga Ziboko | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Dangunga Basic School | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Dangunga Makpale | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Dangunga Gbango | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Dangunga Gundango | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Kansongo | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Sakpare | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Timpeligo Yipala | SHEP-5 | Works in progress
Jews Electricals Limited | SHEP-5-BWD-JEL-16 | Bawku West | Timpeligo Cental/Googo | SHEP-5 | Works in progress
J-Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Pusiga | Belimtanga | SHEP-4 | Works are nearing completion
J-Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Pusiga | Salwabin | SHEP-4 | Works are nearing completion
J-Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Pusiga | Tesgbego | SHEP-4 | Works are nearing completion
J-Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Pusiga | Sarabogo | SHEP-4 | Works are nearing completion
J-Karimus Company Ltd. | SHEP-4-UER-BD-JKCL-17 | Pusiga | Palnnaba | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Koose Sanga | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Koose Chief's Palace | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Bimpiela #1 | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Bimpiela #2 | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Bimpiela Extension | SHEP-4 | Works in progress
Joditec Electrical Ltd | SHEP-4-UER-BWM-16 | Pusiga | Kogadem | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASN-05-2020 | Bongo | Bongo Herbal Centre | SHEP-4 | Works are nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASN-05-2020 | Bongo | CHIPS Compound /Akire Kunkua | SHEP-4 | Works Completed
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASN-05-2020 | Bongo | Boko Market | SHEP-4 | Works Completed
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Kadali | SHEP-4 | Works are nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Tindongo | SHEP-4 | Works are nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Goo/Widongo | SHEP-4 | Works are nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Awaa Atiabiisi | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Awaa Tarongo Ext | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Abelumzanga Ext | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Awale Namoo | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Sikabiisi Nayari | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Sikabiisi Akondone | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Sikabiisi Abokobisi | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Lungu Dangoogo | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Lungu Ext | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Ayourpia | SHEP-4 | Works are nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Beo Lembisi | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KASNECL-07-19 | Bongo | Beo Mooshidaboro | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-BD-KECL-03-2020 | Binduri | Soogtinga/Buarin | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UE-BD-KECL-03-2020 | Binduri | Bazua NewTown/Biaka | SHEP-4 | Works in progress
KASN Engineering and Consult Ltd | SHEP-4-UER-TD-KECL-03-2020 | Talensi | Zanwore | SHEP-4 | Nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-TD-KECL-03-2020 | Talensi | Degaare | SHEP-4 | Nearing completion
KASN Engineering and Consult Ltd | SHEP-4-UER-TD-KECL-03-2020 | Talensi | Kuzoo/Sapakyare | SHEP-4 | Nearing completion
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Kembisi | SHEP-4 | Works are nearing completion
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Zurebisi | SHEP-4 | Works are nearing completion
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Kumberigo | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Nyonkoko | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Sirigu (Nayire) / Tangabiisi | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Sapio | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Tinganibiisi | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Bugelego | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Mossi | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Mossi (Ext) | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Ayesikabiisi | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-4-UER-BM-KEL-16 | Bolgatanga Municipality | Dubila | SHEP-4 | Works in progress
Khesby Engineering Ltd. | SHEP-5-BD-KEL-16 | Bongo | Kangkoo | SHEP-5 | Works in progress
Khesby Engineering Ltd. | SHEP-5-BD-KEL-16 | Bongo | Vea-Zangongo | SHEP-5 | Works in progress
Khesby Engineering Ltd. | SHEP-5-BD-KEL-16 | Bongo | Kulipeeliga | SHEP-5 | Works in progress
Khesby Engineering Ltd. | SHEP-5-BD-KEL-16 | Bongo | Tarongo Awaah | SHEP-5 | Works in progress
Khesby Engineering Ltd. | SHEP-5-BD-KEL-16 | Bongo | Sapeeba/Ayelbia | SHEP-5 | Works in progress
King Nimod Electrical | SHEP-4UE-KNWD-KEW-16 | Kasena Nankana West | Kansan | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4UE-KNWD-KEW-16 | Kasena Nankana West | Pungbisi/Kulnyurisum | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4UE-KNWD-KEW-16 | Kasena Nankana West | Kasalingo/Chengo | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4UE-KNWD-KEW-16 | Kasena Nankana West | Kumbusigo | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4-UER-KEWL-16 | Binduri | Azum-Sapeliga | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4-UER-KEWL-16 | Binduri | Kpagogo #1 | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4-UER-KEWL-16 | Binduri | Kpagogo #2 | SHEP-4 | Works in progress
King Nimod Electrical | SHEP-4-UER-KEWL-16 | Binduri | Kpagogo North | SHEP-4 | Works in progress
Kwodam Elect. Eng. Ltd. | SHEP-5-BS-KWODAM-16 | Builsa South | Fumbisi-Bachiesa | SHEP-5 | Works in progress
Kwodam Elect. Eng. Ltd. | SHEP-5-BS-KWODAM-16 | Builsa South | Bachiesa-Sainyanyeri | SHEP-5 | Works in progress
Kwodam Elect. Eng. Ltd. | SHEP-5-BS-KWODAM-16 | Builsa South | Fumbisi-Batuisa | SHEP-5 | Works in progress
Kwodam Elect. Eng. Ltd. | SHEP-5-BS-KWODAM-16 | Builsa South | Fumbisi-Sinsangsa | SHEP-5 | Works in progress
Kwodam Elect. Eng. Ltd. | SHEP-5-BS-KWODAM-16 | Builsa South | Bachonsa | SHEP-5 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Jiningsa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Nyakasa/Piisa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Samsa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Sikabsa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Zogsa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Luisa | SHEP-4 | Works are nearing completion
Kwodam Electrical Ent. | SHEP-UE-KWODAM-15 | Builsa South | Kunyinsa | SHEP-4 | Works are nearing completion
Kwofos Engineering Limited | SHEP-4-UER-KNWD-KEL-8-2020 | Kasena Nankana West | Kaliveo Awenia | SHEP-4 | Works in progress
Kwofos Engineering Limited | SHEP-4-UER-KNWD-KEL-8-2020 | Kasena Nankana West | Kaliveo Ext | SHEP-4 | Works in progress
Kwofos Engineering Ltd | SHEP-4-UER-BSD-KEL-09-2020 | Builsa South | Gbedemblisi | SHEP-4 | No materials released
Kwofos Engineering Ltd. | SHEP-4-UE-KNWD-KEL-16 | Kasena Nankana West. | Ayingayire/Akaoore | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UE-KNWD-KEL-16 | Kasena Nankana West. | Gayingo/Bolinga (Nayeri) | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UE-KNWD-KEL-16 | Kasena Nankana West. | Aburiwasa/Leengo | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UE-KNWD-KEL-16 | Kasena Nankana West. | Achuligoyire | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-KND-KEL-10-16 | Kasena Nankana East. | Sonnu-Kura Nayagenia | SHEP-4 | Works are nearing completion
Kwofos Engineering Ltd. | SHEP-4-UER-KND-KEL-10-16 | Kasena Nankana East. | Nayegenia Ext. | SHEP-4 | Works are nearing completion
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Magnori Central | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Bador(Ext)/Kiwurugu/ Hebuku Saataya | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Gumakutari Ext(1&2) | SHEP-4 | Works remaining only HT
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Gumakutari Chief's palace | SHEP-4 | Works remaining only HT
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Galaka-Mognori | SHEP-4 | Works remaining only HT
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Galaka-Magnori(Ext) | SHEP-4 | Works remaining only HT
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Baribari-Parabnating | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16 P2 | Bawku Muncipality | Mognori Baribari/Abisigin/ Awigbeeg/Zeidbin(Ext) | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Nyorugu(Ext.) | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Missiga Bubula(Ext.) | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Missiga-Yas Natinga # 1 | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Missiga-Yas Natinga # 2 | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Missiga Bubula Zawse # 1 | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Missiga Bubula Zawse # 2 | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Pars Natinga/Azara-Saa | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Tisungu (Ext) | SHEP-4 | Works completed
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Zuuku Kutanga/Sampiasae # 1&2 | SHEP-4 | Works in progress
Kwofos Engineering Ltd. | SHEP-4-UER-BM-KEL-16P1 | Bawku Muncipality | Kpalwega(Ext)/Kwaliga | SHEP-4 | Works completed
mahamadu Asaki Company Limited | SHEP-4-UER-GD-MACL-10-2020 | Garu | Kolmasig 1 & 2 | SHEP-4 | Works in progress
Malka - Mulq Limited | SHEP-4-UER-BD-MML-05-20 | Bongo | Kansoo | SHEP-4 | Works in progress
Malka - Mulq Limited | SHEP-4-UER-BD-MML-05-20 | Bongo | Azoosid Aana/Akonka | SHEP-4 | Works in progress
Metro Energy & Training Wks. | SHEP-4-UER-KNWD-MEAT-16 | Kasena Nankana West | Wolingum | SHEP-4 | Works in progress
Metro Energy & Training Wks. | SHEP-4-UER-KNWD-MEAT-16 | Kasena Nankana West | Akadaka | SHEP-4 | Works in progress
Metro Energy & Training Wks. | SHEP-4-UER-KNWD-MEAT-16 | Kasena Nankana West | Pingo/Tikongo | SHEP-4 | Works in progress
Metro Energy & Training Wks. | SHEP-4-UER-KNWD-MEAT-16 | Kasena Nankana West | Abuguziondone | SHEP-4 | Works in progress
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Sugudi Chief's Palace | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Sugudi Duakom | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Tambiugu | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Pulmakuom Koose-Jingle | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Pulmakuom Koose | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Pilmakuom Central | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Sanga # 3 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Sanga Chief's Palace | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Dabia # 1 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Dabia # 2 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Bulungu- Koltisi # 1 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Bulungu- Koltisi # 2 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Bulungu-Zopeliga | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Kampodi-Tambnogin | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Kampodi-# 1&2 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Zuabulga # 1 | SHEP-5 | Works are nearing completion
Mohatu Electrical Limited | SHEP-5-PD-MEL-16 | Pusiga | Zuabulga # 2 | SHEP-5 | Works are nearing completion
Mohatu Electrical Ltd | SHEP-4-UER-BM-MEL-16 | Bawku Muncipality | Gentiga #1 | SHEP-4 | Works are nearing completion
Mohatu Electrical Ltd | SHEP-4-UER-BM-MEL-16 | Bawku Muncipality | Gentiga #2 | SHEP-4 | Works are nearing completion
Mohatu Electrical Ltd | SHEP-4-UER-BM-MEL-16 | Bawku Muncipality | Tampezue #1 | SHEP-4 | Works are nearing completion
Mohatu Electrical Ltd | SHEP-4-UER-BM-MEL-16 | Bawku Muncipality | Tampezue #2 | SHEP-4 | Works are nearing completion
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Morgo | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Kultamise | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Kulanaba Kultamise/Tempani | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Nware | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Kamadugu/Sunkelma | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-PD-MEL-16 | Pusiga | Koose Basic School | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-UER-BD-REL-09-29 | Kasena Nankana East | Saboro | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-UER-KNW-MEEL-04-19 | Kasena Nankana West | Benbisi | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-UER-KNW-MEEL-04-19 | Kasena Nankana West | Kayelo | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4-UER-KNW-MEEL-04-19 | Kasena Nankana West | Adungu | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4/THENGASHEP-UER-GT&PD-MEEL-09-18 | Tampane | Zangsirboliga | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4/THENGASHEP-UER-GT&PD-MEEL-09-18 | Pusiga | Terage | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4/THENGASHEP-UER-GT&PD-MEEL-09-18 | Garu | Nkinikogo | SHEP-4 | Works in progress
Mohatu Electrical Ltd. | SHEP-4/THENGASHEP-UER-GT&PD-MEEL-09-18 | pusiga | Banterfargo | SHEP-4 | Works in progress
Multi Amb Limited | SHEP-4-UER-BD-MAMBL-05-20 | Bongo | Akendoo/Mission | SHEP-4 | Works in progress
Multi Amb Limited | SHEP-4-UER-BD-MAMBL-05-20 | Bongo | Konkuaa | SHEP-4 | Works in progress
Multi Amb Limited | SHEP-4-UER-BD-MAMBL-05-20 | Bongo | Akanseringo Ext | SHEP-4 | Works in progress
My Turn Standard Co. Limited | SHEP-4-UER-BD-HNVL-05-20 | Bongo | Ganlagrum | SHEP-4 | Works in progress
My Turn Standard Co. Limited | SHEP-4-UER-BD-HNVL-05-20 | Bongo | Akebga Ext | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-BWD-NEW-10-2020 | Bawku West | Guzongo Salipiiga | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-BWD-NEW-10-2020 | Bawku West | Kukurizua Ext. | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-BWD-NEW-10-2020 | Bawku West | Sheiga | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-GD-MACL-10-2020 | Garu | Kuparbuliga | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-GD-NWE-10-2020 | Garu | Kukparbuliga | SHEP-4 | Works in progress
Nantah-Waz Enterprise | SHEP-4-UER-GD-NWE-10-2020 | Garu | Ampunateng Ext. | SHEP-4 | Works in progress
Payaba Enterprise | SHEP-4-UER-BD-PE-03-2020 | Binduri | Bansi Winaba | SHEP-4 | Works in progress
Payaba Enterprise | SHEP-4-UER-BD-PE-03-2020 | Binduri | Ziako Tesnatinga / Buarin | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Benwoko | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Adugbal | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Bulpiese Nabuya | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Duayediga 2 | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Duayediga 3 | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Duayediga 1 | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Zotrikoum | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Tambalagu | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Trudiga | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Gabri Bolgatanga | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Zomandiga | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Kanbogun Zambala | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Timlgbog | SHEP-4 | Works in progress
Powerboard Company limited | SHEP-4-UER-TD-PCL-09-19 | Tampane | Mamamburi | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Kori-Alabyire | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Kori-Kanansa Kauesa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Kori-Kanansa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Yipaala # 1 | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Yipaala # 2 | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Awichaanayire | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Chanyire Nanjana-Yea | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Chanyire-Guuta | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-05-16 | Builsa North | Chanyire-Yipaala | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Kaljisa #1 | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Kaljisa #2 | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Longsa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Kobedam | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Nawasa #1 | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Suwaransa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Faransa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Yimonsa | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Chiok (Atidiok) | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-4-BND-PESL--16 | Builsa North | Nanjuaping | SHEP-4 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Kologo-Natinga | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Kologo-Tingre | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Kuloko Yoldeing | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Kolok Gumyako | SHEP-5 | Works are nearing completion
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Kuloko Aporozua | SHEP-5 | Works are nearing completion
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Yalugu Natinga/ | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Barigun/Magnori | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Yalugu Ganaga | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Yalugu Kpanating | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Barabogo Tengbeong | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Barabogo Natinga | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Agumsi Bulzua | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Agumsi Natinga | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Agumsi Tambig Natinga | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Nafkoliga Tambizeeg | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Nafkoliga Agumsi | SHEP-5 | Works in progress
Powertech Eng. Serv. Ltd. | SHEP-5-BD-PESL-16 | Binduri | Nafkoliga Natinga | SHEP-5 | Works in progress
Powertech Engineering Ltd | SHEP-4-UER-GD-PEL-05-19 | Garu | Zare-Zua | SHEP-4 | Works in progress
Powertech Engineering Ltd | SHEP-4-UER-GD-PEL-05-19 | Garu | Duubulugu | SHEP-4 | Works in progress
Powertech Engineering Ltd | SHEP-4-UER-GD-PEL-05-19 | Garu | Kpatia Poraguur | SHEP-4 | Works in progress
Powertech Engineering Ltd | SHEP-4-UER-GD-PEL-05-19 | Garu | Poraguur | SHEP-4 | Works in progress
Powertech Engineering Ltd | SHEP-4-UER-GD-PEL-05-19 | Garu | Kugri Kpalsiako | SHEP-4 | Works in progress
Psam 91 | SHEP-4-UER-BWD-PE-10-2020 | Bawku West | Zeogo | SHEP-4 | Works in progress
Psam 91 | SHEP-4-UER-BWD-PE-10-2020 | Bawku West | Widnaba | SHEP-4 | Works in progress
Psam 91 | SHEP-4-UER-BWD-PE-10-2020 | Bawku West | Biaknawezer | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Bugore | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Gozesi | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Sitande | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Kopella | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Agaogo | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Zeego | SHEP-4 | Works in progress
Quanta Elect. Co. Ltd. | SHEP-4-UER-QECL-16 | Bawku West | Gabuliga | SHEP-4 | Works in progress
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Polugu | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Kumbosco | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Kumbosco Clinic | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Yarigabisi - Asogrebisi | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Yarigabisi - Agungabisi | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Yarigabisi - Awanabisi | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Yarigabisi - Ricemill | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Tongo Beo Primary | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bolgatanga Mun. | Tongo Beo Chief's Palace | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bongo | Tankuo (Tankoo) | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UE-BM/BD-REL-16 | Bongo | Tankuo Nayiri | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Konkua (Ext) | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Nyonkoko/Asonge | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Benkote (Ext) | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Zoore | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Genebiisi/Banenbiisi | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Pogwongbiisi/Kokan | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Akenga (Ext) | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Boosiya (ext) | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Boosiya Gambigo Tingre | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Soorebiisi | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Tansobkor | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16-P1 | Bolgatanga Municipality | Nyangu Yorogo Asogrebiisi | SHEP-4 | Works in progress
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Zenga | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Tokobiisi | SHEP | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Dorongo New | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Akegma/tampo | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Katanga Boko | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Anaba-Doone | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Nyaariga Doone | SHEP-4 | Works completed
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Nungo/Nayire | SHEP-4 | Works in progress
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Tingchioaneuure/Dachio | SHEP-4 | Works in progress
Richmanda Eng. Ltd. | SHEP-UER-REL-16P2 | Bolgatanga Municipality | Torsin | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-4-UER-BD-REL-09-16 | Bongo | Yekine-Dabuure | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-4-UER-BD-REL-09-16 | Bongo | Dua Ext | SHEP-4 | Works are nearing completion
Richmanda Eng. Ltd. | SHEP-4-UER-BD-REL-09-16 | Bongo | Yekine Ext | SHEP-4 | Works are nearing completion
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Saaka | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Tazika | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Kazugu | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Kazugu Navio JSS | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Kuliya #1 | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Kuliya #2 | SHEP-5 | Works in progress
Richmanda Enterprise Ltd. | SHEP-5-KNWD-IBCL-16 | Kasena Nankana West | Bagtua | SHEP-5 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Siirigu | SHEP-4 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Menkaesir | SHEP-4 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Namore | SHEP-4 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Tambaalugu | SHEP-4 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Bugwia Seltego | SHEP-4 | Works in progress
Sounsong Company Ltd | SHEP-4-UER-GD-SCL-05-19 | Garu | Waadugu | SHEP-4 | Works in progress
Standard Techs Engineering Service | SHEP-4-UER-TD-STES-06-20 | Tampane | Zansibuliga # 1 | SHEP-4 | Works in progress
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Zeego (Zaago)/Bankago Ext | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Atoba-Mognori | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Atoba-Avoase | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Tansia-Bugrin/Zeego/ Kolnatinga | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Atoba Main Town | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Kaadi-Kudugu | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Agomisin | SHEP-4 | No materials released
Tirago Enterprise Ltd. | SHEP-4-UER-BD-TEL-17 | Binduri | Wabzug | SHEP-4 | No materials released
Tuima Electricals Works | SHEP-4-UER-BWD-TEW-08-2020 | Bawku West | Tarikom Gbere | SHEP-4 | Works in progress
Tuima Electricals Works | SHEP-4-UER-BWD-TEW-08-2020 | Bawku West | Tarikom | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Kalosoko | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Zuo Timpelugu | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Mainzuo Ext | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Naaga No.1 | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Naaga No.2 | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Kungogo | SHEP-4 | Works in progress
Twins Touch Electricals Limited | SHEP-4-UER-KNED-TTEL-10-19 | Kasena Nankana East | Punyoro Kababia | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Googo | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Weeri/Natinga (EXT.) | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Kpalsako | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Bugare Kpalsako | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Apoddabogo | SHEP-4 | Works in progress
Vims Electrical & Electronics Ltd. | SHEP-4-UER-BWM-16 | Bawku West | Zobako | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Kugasego Bugri | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Jelakologo | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Kolebore | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Nyosbara | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Terudig | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Tubong | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Zotrikkuom | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Nadigiri | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Subzude | SHEP-4 | Works in progress
Washdan Company Limited | SHEP-4-UER-TD-WDCL-09-19 | Tampane | Nambina-Sigure | SHEP-4 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Chuchuliga-Awuchinayeri | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Chuchuliga-Yiepala | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Jaata | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Molinsa | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Tajirinsa | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Tampela | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Kaasa | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Yiekpen No. 1 | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Yiekpen No. 2 | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Jangsa | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Kalijisa | SHEP-5 | Works in progress
Wilwak Enterprise Limited | SHEP-5-BN-WEL-16 | Builsa North | Fiisa | SHEP-5 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Zuuli Basic School | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Kuka-Nabug | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Kaabing/Zuli #2 | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Gaag-Kuka | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Bukgri Corner/Ariziem/ | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Kuka-Natinga (EXT.) | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Megog(Ext) | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Winating | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Lamb/Lambkong/Tempelug | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Narun/Winadateng | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Zom | SHEP-4 | Works in progress
Y.B. General Electricals Ltd. | SHEP-4-UER-BM-YGBEL-16 | Bawku Municipality | Zaasi/Kpalug/Terug | SHEP-4 | Works in progress
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Abitateega | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Kolsuga | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Jankpasi | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Nate | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Wakuan #1 | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Wakuan #2 | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Kpalisako | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Kpatua 1&2 | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Gozesi | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Kugre Natenga | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Siisi | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Avuusum | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Farfar Ext | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Yizidug #1 | costsharing | Ongoing
Garu Assambly | COST SHARING-UER-GD-07-2024 | Garu | Yizidug #2 | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Aunkongo-Abempingo 1&2 | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Gia Nangua | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Gia Bagania | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Doba Akon Doone | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Gongnia-Bundunia | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Namolo East | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | Namolo West | costsharing | Ongoing
Kasena Nankana East Assembly |  | Kasena Nankana East | BAWIU | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | NINKOGA # 1&2 | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | Pusiga Ext | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | Kulungugu Ext | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | ZUABULIGA #3 | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | DAWARE | costsharing | Ongoing
Pusiga District Assembly |  | Pusiga | GARAKE NO. 1&2 | costsharing | Ongoing

## Community_Status
region | district | community | contractor | status | remarks
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Adoe | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Boana | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Bomua | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Tom | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Busunya West | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Busunya East | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Dromankese | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Dromankese No.2 | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | WENCHI MUNICIPAL/ NKORANZA NORTH WENCHI MUNICIPAL/ NKORANZA NORTH | Dromankoma | PABSEIMAH PABSEIMAH | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | PRU | Ajaraja Beposo | KINGSCO ELECT. LTD. | Intensification works | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH | Mamprisi Line Ext. | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Belompe Ext. | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Kadelso Ext. | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Bemkrom Ext. | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Timber Market | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Just Love area | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Substation and Magazine | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Kwajove No.2 | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Kobeda | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Jidi Town | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Central College | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Gruma Down | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Assemblies of God (Nwoase) | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH | Targona | KORIGU | Intensification works | FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Attakrom Asugya | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Adekese | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Azuma Akura | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | atakrom | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Kaaka | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Abena Anum | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Dagomba alhassan | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Kpukpabine | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Bunkwata | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Berecha Krom | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Naaba | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Yerepemso | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Bukariakura | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Dakori | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Adage | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Alampram | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Drepo | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Fosu Akura | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Domeabra | KORIGU KORIGU | Virgin community | FIRST QUARTER FIRST QUARTER
Bono East | ATEBUBU AMANTIN | Islamic | UNIQUE TITAN COMPANY LTD. | Intensification works | FIRST QUARTER
Bono East | ATEBUBU AMANTIN | New Duabone | UNIQUE TITAN COMPANY LTD. | Intensification works | FIRST QUARTER
Bono East | ATEBUBU AMANTIN | Agric Station | UNIQUE TITAN COMPANY LTD. | Intensification works | FIRST QUARTER
Bono East | ATEBUBU AMANTIN | Sabon Zongo | UNIQUE TITAN COMPANY LTD. | Intensification works | FIRST QUARTER
Bono East | SENE WEST | Amangoase | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE WEST | Konkose | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE WEST | Chokose | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE WEST | Ningo | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE WEST | Todaykope | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE WEST | Asempaneye | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | KINTAMPO NORTH | Nyamebekyere | KORIGU | Virgin community | SECOND QUARTER
Bono East | KINTAMPO NORTH | Sarachigona | KORIGU | Virgin community | SECOND QUARTER
Bono East | KINTAMPO NORTH | Tanokrom | KORIGU | Virgin community | SECOND QUARTER
Bono East | KINTAMPO NORTH | Baabu Akura | KORIGU | Virgin community | SECOND QUARTER
Bono East | KINTAMPO NORTH | Tamno Akura | KORIGU | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Gbili | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Bilaba/Gbeti | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Abuoso/Chafi | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Issifu-Yaw Mensah | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Wajul | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Asuoso Mud | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Sumsunpe/Aliwoe | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Ningo Akpalu | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Oldman | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Beposo | FRANVES | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Tabus | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Gakope | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Ohiasomawo | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE EAST | CFAO Quarters | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Nyakonakope | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | SENE EAST | Agyata | STEVGARBS | Virgin community | SECOND QUARTER
Bono East | ATEBUBU AMANTIN | Mem | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Watro | KAMNAA | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Old Kronkron | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Kitikrom | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Seneso | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Kokofu | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Garadima | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Duabone | KAMNAA | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Yaw Tuffour | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Bresuano | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Asempaneye | KAMNAA | Virgin community | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Agric Station | KAMNAA | Intensification works | THIRD QUARTER
Bono East | PRU | Budan | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Congo | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Brahabebome | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Bomboben | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Wobrase | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Wodomeabra | MY REDEEMER | Virgin community | THIRD QUARTER
Bono East | PRU | Zamara North | KINGSCO ELECTRICALS &CIVIL ENG. LTD. | Intensification works | THIRD QUARTER
Bono East | PRU | Zamara South | KINGSCO ELECTRICALS &CIVIL ENG. LTD. | Intensification works | THIRD QUARTER
Bono East | PRU | Zamara East | KINGSCO ELECTRICALS &CIVIL ENG. LTD. | Intensification works | THIRD QUARTER
Bono East | PRU | Zamara West | KINGSCO ELECTRICALS &CIVIL ENG. LTD. | Intensification works | THIRD QUARTER
Bono East | PRU | Yawpare | KINGSCO ELECTRICALS &CIVIL ENG. LTD. | Virgin community | THIRD QUARTER
Bono East | NKORANZA NORTH | Odumase | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Fiema | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Akonkonti | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Bonte | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Yefri | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Asekye | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Senya | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Bomini | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Domeabra | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Akrudwa | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Bodom | FRANVES | Intensification works
Bono East | NKORANZA NORTH | Pienyina | FRANVES | Virgin community
Bono East | NKORANZA NORTH | Mangoase Junction | FRANVES | Virgin community
Bono East | ATEBUBU AMANTIN | Nyomase | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Beposo | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Jumpa | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Kumfia | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Fakwasi | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Dobidi | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | ATEBUBU AMANTIN | Amantin Dogu | UNIQUE TITAN COMPANY LTD. | Intensification works | THIRD QUARTER
Bono East | SENE WEST | Africa/Zabrama | UNIQUE COSBY | Virgin community | FOURTH QUARTER
Bono East | SENE WEST | Davakope | UNIQUE COSBY | Virgin community | FOURTH QUARTER
Bono East | SENE WEST | Dunkwape | UNIQUE COSBY | Virgin community | FOURTH QUARTER
Bono East | SENE WEST | Burkina | UNIQUE COSBY | Virgin community | FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Asukoko | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Awurata | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Kongo | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Larempe | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Nkeyinedea | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Yabraso | KORIGU KORIGU | Intensification works | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Telefufuo | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Wala Akura | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Sempoa Akura | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Awaa Akura | KORIGU KORIGU | Virgin community | FOURTH QUARTER FOURTH QUARTER
Bono East | KINTAMPO NORTH KINTAMPO NORTH | Sissala Line Ext. | KORIGU KORIGU | Intensification works | FOURTH QUARTER FOURTH QUARTER
Bono East | PRU | Zongo | KINGSCO ELECTRICALS & CIVIL ENG. LTD. | Intensification works | FOURTH QUARTER
Bono East | PRU | Lowcost Area | KINGSCO ELECTRICALS & CIVIL ENG. LTD. | Intensification works | FOURTH QUARTER
Bono East | PRU | Amanfrom | KINGSCO ELECTRICALS & CIVIL ENG. LTD. | Intensification works | FOURTH QUARTER
Bono East | PRU | Adom Fiano Road | KINGSCO ELECTRICALS & CIVIL ENG. LTD. | Intensification works | FOURTH QUARTER
Bono East | PRU | New Ajona | MY REDEEMER | Intensification works | FOURTH QUARTER
Bono East | PRU | Jato Zongo Jumpa Akura | MY REDEEMER | Intensification works | FOURTH QUARTER
Bono East | PRU | Jato Zongo Area | MY REDEEMER | Intensification works | FOURTH QUARTER
Bono East | PRU | Zongo No.3 Mangoase | MY REDEEMER | Intensification works | FOURTH QUARTER
Bono East | PRU | Kachawura Newsite | MY REDEEMER | Intensification works | FOURTH QUARTER
Bono East | PRU | Jumpe | MY REDEEMER | Virgin community | FOURTH QUARTER
Bono East | PRU | New Patuda | MY REDEEMER | Virgin community | FOURTH QUARTER
Ashanti | ADANSI FOMENA | Anyinabrem | ISAAC FORDJOUR LIMITED | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Bura | ISAAC FORDJOUR LIMITED | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Bena | ISAAC FORDJOUR LIMITED | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Kwakukrom | ISAAC FORDJOUR LIMITED | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Denkyie | ISAAC FORDJOUR LIMITED | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Nintini | BUKJEE | Virgin community | FIRST QUARTER
Ashanti | ADANSI FOMENA | Apunpunso | BUKJEE | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Mosikrom | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Santaso | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Asubuoso | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Barlana | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Domeabra | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | SEKEYRE CENTRAL | Tailor Nkwanta | SAINI MORRISON ENG. LTD | Virgin community | FIRST QUARTER
Ashanti | NEW EDUBIASE | Amudurase | GLOBAL NEW BEGINNING | Intensification works | FIRST QUARTER FIRST QUARTER
Ashanti | NEW EDUBIASE | Adansi Paaso | GLOBAL NEW BEGINNING | Intensification works | FIRST QUARTER FIRST QUARTER
Ashanti | NEW EDUBIASE | Ataasi-Nkwanta | GLOBAL NEW BEGINNING | Intensification works | FIRST QUARTER FIRST QUARTER
Ashanti | KWABRE EAST | Akotosu | OSMED PLUS COMPANY LTD. | Intensification works | FIRST QUARTER FIRST QUARTER
Ashanti | KWABRE EAST | Adjei Mpra | OSMED PLUS COMPANY LTD. | Intensification works | FIRST QUARTER FIRST QUARTER
Ashanti | OFFINSO SOUTH | Apotosu Town | PATCO | Virgin community | FIRST QUARTER FIRST QUARTER
Ashanti | OFFINSO SOUTH | Ayaasu Town | PATCO | Virgin community | FIRST QUARTER FIRST QUARTER
Ashanti | OFFINSO SOUTH | Namong Wenchi | PATCO | Virgin community | FIRST QUARTER FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Asuokor 1&2 | POSSIBLE POWER LIMITED | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Adiembra | POSSIBLE POWER LIMITED | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Dotiem | POSSIBLE POWER LIMITED | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Ango | POSSIBLE POWER LIMITED | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Ofirikrom | POSSIBLE POWER LIMITED | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Nyameadom | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Dotiem | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Dunyan-Nkwanta | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Asibey-Nkwanta | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Bonsukrom | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AHAFO ANO SOUTH | Awaduwa Nkwanta | PRESTIGE ELECT. LTD | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Abubuasini | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Wromanso | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Subima | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Gyaaman | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Skuumu | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Bepotenten | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Penipa | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Aboagyekrom | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Mmodobamu | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Esaase | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | AMANSIE CENTRAL | Homabene | NEW LIFE | Virgin community | FIRST QUARTER
Ashanti | ATWIMA MPONUA | Wansamire | EAGLE POWER | Virgin community | FIRST QUARTER
Ashanti | ATWIMA MPONUA | Awesesu | EAGLE POWER | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Kwakye Krom | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Nyamebekyere | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Adukroba | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Bethlehem | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Adomanyame | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Beseasi | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Boakyekrom | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | ADANSI SOUTH | Nnyameso | ANS ELECTRIC | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Bosomposo | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Mpapaamu | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | New Atwene | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Kwaem | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Sraneso No.1 | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Sraneso Zongo | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | OFFINSO NORTH OFFINSO NORTH | Sraneso No.2 | AUGYEB AUGYEB CONTRACT LIMITED | Virgin community | FIRST QUARTER
Ashanti | ASANTE AKIM | Anawuokrom | MATWEN AWURADE | Virgin community | FIRST QUARTER
Ashanti | ASANTE AKIM | Nsiakrom | MATWEN AWURADE | Virgin community | FIRST QUARTER
Ashanti | ASANTE AKIM | Nyamebekyekrom | MATWEN AWURADE | Virgin community | FIRST QUARTER
Ashanti | ASANTE AKIM | Beposo | MATWEN AWURADE | Virgin community | FIRST QUARTER
Ashanti | ASANTE AKIM | Bomfa Newsite | MATWEN AWURADE | Intensification works | FIRST QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Yadome | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Bertenase | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Adubanaso | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Mensahkrom | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Asaasebomebosia | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Akaasu No.1 | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Akaasu No.2 | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Dampayam | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Comfortable Nkwanta | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Ofrikrom | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Agengensu | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Bredi | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | ADANSI SOUTH/ SEKYERE CENTRAL | Fawoman | AGENBEC | Virgin community | SECOND QUARTER
Ashanti | SEKYERE CENTRAL | Okun Nkwanta | SAINI MORRISON | Virgin community | SECOND QUARTER
Ashanti | SEKYERE CENTRAL | Okufea | SAINI MORRISON | Virgin community | SECOND QUARTER
Ashanti | SEKYERE CENTRAL | Congo Nkwanta | SAINI MORRISON | Virgin community | SECOND QUARTER
Ashanti | KWABRE EAST | Adantem Manchia Newsite | ANTOA-B | Intensification works | SECOND QUARTER
Ashanti | KWABRE EAST | Adiembra New Site | POMARK | Intensification works | SECOND QUARTER
Ashanti | KWABRE EAST | Djako | POMARK | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Nkwabeng | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Pepease Ankaase | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Dadieso Mexico | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Dadieso Agric | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Adanso Agya Zone | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | EFFIDUASE & ATWIMA KWAHOMA | Adanso Agya Hwe | OSMED PLUS | Intensification works | SECOND QUARTER
Ashanti | KWABRE EAST | Ntrodanim | TWINS TOUCH | Intensification works | SECOND QUARTER
Ashanti | OFFINSO SOUTH | Amankwatia Town | PATCO | Virgin community | SECOND QUARTER
Ashanti | OFFINSO SOUTH | Amaning Town | PATCO | Virgin community | SECOND QUARTER
Ashanti | OFFINSO SOUTH | Boahenkwaa Town | PATCO | Virgin community | SECOND QUARTER
Ashanti | OFFINSO SOUTH | Baaniekrom | PATCO | Virgin community | SECOND QUARTER
Ashanti | OFFINSO SOUTH | Wawase Town | PATCO | Virgin community | SECOND QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Ntwaso & Aduntia | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Mile 18 | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Adwease No. 1&2 | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Sudantoa | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Odumto | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Manfo | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Sabe 1 | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Sabe 2 | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Apeboso | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Nwease | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Akwankwaso | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Asuadae | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Mpenkyireni | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | AMANSIE CENTRAL AMANSIE CENTRAL | Bentenseni | PURETEC PURETEC | Virgin community | THIRD QUARTER THIRD QUARTER
Ashanti | ASANTE AKIM | Wioso | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Akutuase | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Amantena | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Pekyebrekye | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Behwe | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Nyinamponase | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Praaso | PURETEC | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Agogo | NEW LIFE | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Juaso | NEW LIFE | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Domeabra | NEW LIFE | Intensification works | THIRD QUARTER
Ashanti | ASANTE AKIM | Hwediem | NEW LIFE | Intensification works | THIRD QUARTER
Ashanti | ATWIMA KWAHOMA | Ampabame No. 2 | DADIE KWADWO | Intensification works | THIRD QUARTER
Ashanti | ATWIMA KWAHOMA | Asaman Township | DADIE KWADWO | Intensification works | THIRD QUARTER
Ashanti | ATWIMA KWAHOMA | Nketia Township | DADIE KWADWO | Intensification works | THIRD QUARTER
Ashanti | BOSOMTWI | Jachie Newsite | MATWEN AWURADE | Intensification works | FOURTH QUARTER
Ashanti | BOSOMTWI | Akwaduom | MATWEN AWURADE | Intensification works | FOURTH QUARTER
Ashanti | BOSOMTWI | Aboaso Newsite | MATWEN AWURADE | Intensification works | FOURTH QUARTER
Ashanti | BOSOMTWI | Sewia Newsite | MATWEN AWURADE | Intensification works | FOURTH QUARTER
Ashanti | BOSOMTWI | Atobiase Newsite | MATWEN AWURADE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Fomena Ahmadiya SHS | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Nursing & Midwifery | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Dompoase SHS | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | New Amensia | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Kusa Newsite | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Kyekyewere Newsite | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Hemang Poultry Newsite | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Dadwen Newsite | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Akrokeri Training College | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Asare Bediako SHS | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Broni Kurom Senit | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Sampakrom | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Abadwam | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Aktakyieso Community Mining | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Sodua | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Akrofuom | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | New Nyamebekyere | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Wiawso Community Mining | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Adumenu Community Mining Site | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Kusa Scrap | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ADANSI NORTH | Bonriase 1D1F | BUKJEE | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Sene | GLOBAL NEW BEGINNING | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Saase | GLOBAL NEW BEGINNING | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | DKC | GLOBAL NEW BEGINNING | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Bkankyi | GLOBAL NEW BEGINNING | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Agyeikrom | GLOBAL NEW BEGINNING | Virgin community | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Nkrang | NEWLIFE LTD. | Virgin community | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Atwima Mim | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Nkawie Panin | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Adankwame | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Newtown | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | ATWIMA NWABIAGYA NORTH | Amadum | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | AFIGYA KWABRE NORTH & SOUTH | Adam & Hawa | NEWLIFE LTD. | Virgin community | FOURTH QUARTER
Ashanti | AFIGYA KWABRE NORTH & SOUTH | Alhidaya | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | AFIGYA KWABRE NORTH & SOUTH | Wonoagya | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | AFIGYA KWABRE NORTH & SOUTH | Ajaiku | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | AFIGYA KWABRE NORTH & SOUTH | Ahenfo | NEWLIFE LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Adersena | KAMNAA COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Otentic | KAMNAA COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Donase | KAMNAA COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Penchreni | KAMNAA COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Abenase | KAMNAA COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Dwenease | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Hwereso | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Atiakrom | PABSEIMAH COMPANY LTD. | Virgin community | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Adersena Islam | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EJISU MUNICIPALITY | Donase Krakrom | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EFFIDUASE | Nsutam dandwa | PABSEIMAH COMPANY LTD. | Virgin community | FOURTH QUARTER
Ashanti | EFFIDUASE | Nsutam Kofikrom | PABSEIMAH COMPANY LTD. | Virgin community | FOURTH QUARTER
Ashanti | EFFIDUASE | Akwam | PABSEIMAH COMPANY LTD. | Virgin community | FOURTH QUARTER
Ashanti | EFFIDUASE | Oyoko Akotosu | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EFFIDUASE | Oyoko SDA | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | EFFIDUASE | Pepease Domeabra | PABSEIMAH COMPANY LTD. | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | Atwedie | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | Kwawkrom | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | Yawkwei No.2 | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | OdumaseMrOdoom Ar | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | Praaso Old Town | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM NORTH | Konongo Lady Diana | APAM A.E. COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Akrofuom Extension | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Sikaman | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Brofoyedu | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Amponyase | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Amponyase Junction | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Wawase | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Fenaso Nkwanta | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | AKROFUOM | Kokotenten | ANS ELECTRICALS LTD. | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM SOUTH | Wenchi | BADJER ENGINEERING SERVICES COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM SOUTH | Bompata | BADJER ENGINEERING SERVICES COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM SOUTH | Kropa | BADJER ENGINEERING SERVICES COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM SOUTH | Bogu No.2 | BADJER ENGINEERING SERVICES COMPANY LIMITED | Intensification works | FOURTH QUARTER
Ashanti | ASANTE AKIM SOUTH | Jubi | BADJER ENGINEERING SERVICES COMPANY LIMITED | Intensification works | FOURTH QUARTER
North East | East Mamprusi | Messiah Clinic 1 | Khesby Engineering Ltd | all works completed | 35mm cable needed for earth improvement
North East | East Mamprusi | Lansec | Khesby Engineering Ltd
North East | Bunkpurugu- Yunyoo | Mantana | Adda Electrical Service | LV poles planted and strung HT planted | transformers needed
North East | East Mamprusi | C Section | Gatkom Company Ltd | HT done LV poles planted | LV concrete poles accessories needed
North East | East Mamprusi | Tuni Newtown | Al-Sofwan Company Ltd | LV poles planted and strung | 120mm conductors needed
North East | East Mamprusi | Chesterfield | A,Awucheib Electricals | Both LV HT works completed | transformer needed
North East | East Mamprusi | Gbalafong | A,Awucheib Electricals
North East | East Mamprusi | Yamusah | Kwofos Engineering Ltd | HT/LV poles planted | conductors and accessories needed
North East | East Mamprusi | Atabia(India) | Kwofos Engineering Ltd
North East | East Mamprusi | Bimobafong | Faprise Limited | HT/LV poles planted and strung
North East | East Mamprusi | Chief Kosalana | Faprise Limited
North East | East Mamprusi | Hats 1 | Adda Electrical Service | HT/LV poles planted and strung | transformers needed
North East | East Mamprusi | Hats 2 | Adda Electrical Service
North East | East Mamprusi | Yamusah | Jomers Electrical Works | LV poles planted and strung | transformers needed
North East | East Mamprusi | Chief Kosalana | Jomers Electrical Works
North East | East Mamprusi | Namienboku | Gatkom Company Limited | HT LV poles planted | HT&LV conductors and accessories needed
North East | East Mamprusi | Kurukuduri1 | Medi-Saha Enterprise | HT ana some of the Lv poles planted | LV poles and conductors
North East | East Mamprusi | Kurukuduri2 | Medi-Saha Enterprise

## Percent_Complete
region | level | district | community | contractor | pct_previous | pct_current | note
Western | contractor |  |  | KWABLISHA SERVICES LTd | 0 | 13 | 6 communities
Western | contractor |  |  | PAKASSEN Ltd | 0 | 16 | 8 communities
Western | contractor |  |  | SAINI MORRISON | 39 | 25 | 5 communities
Western | contractor |  |  | SDIL LIMITED | 85 | 76 | 1 communities
Western | contractor |  |  | CO-SAAH LIMITED | 0 | 0 | 5 communities
Western | contractor |  |  | DAILY ELECTRICALS Ltd | 5 | 5 | 10 communities
Western | contractor |  |  | TRANSACTORS LIMITED | 17 | 30 | 12 communities
Western | contractor |  |  | NZEMANLE COMPANY Ltd | 0 | 0 | 9 communities
Western | contractor |  |  | CONTRACTOR | OVERALL COMPLETION STATUS - % (PREVIOUS MONTH) | OVERALL COMPLETION STATUS - % (CURRENT) | TOTAL NUMBER OF COMMUNITIES communities
Western | contractor |  |  | VOLTAGE ELECTRICALS Ltd | 0 | 0 | 4 communities
Western | contractor |  |  | EUROFLEX 1 | 0 | 0 | 20 communities
Western | contractor |  |  | AYEKOO GHANA Ltd | 0 | 0 | 5 communities
Western | contractor |  |  | TOTAL |  |  | 85 communities
Western North | contractor |  |  | S K DUKU ENTERPRISE | 75 | 75 | 1 communities
Western North | contractor |  |  | ALPHA Ltd | 0 | 0 | 8 communities
Western North | contractor |  |  | ZENECCA Co Ltd | 0 | 0 | 14 communities
Western North | contractor |  |  | TOTAL |  |  | 23 communities
Bono & Ahafo | contractor |  |  | WashDan | 36.60 | 34.54 | 11 communities (Q3)
Bono & Ahafo | contractor |  |  | Fidelity | 67.00 | 68.00 | 48 communities (Q3)
Bono & Ahafo | contractor |  |  | Pabseimah | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | A.A Warncharn | 16.31 | 16.31 | 49 communities (Q3)
Bono & Ahafo | contractor |  |  | Power Board | 70.89 | 70.89 | 19 communities (Q3)
Bono & Ahafo | contractor |  |  | E.K. Senkyere Company Limited | 70.55 | 86.50 | 25 communities (Q3)
Bono & Ahafo | contractor |  |  | Ahmson | 14.83 | 14.83 | 6 communities (Q3)
Bono & Ahafo | contractor |  |  | Kwamens Eng. Company Ltd | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | Gyabsharah | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | Ans Electricals | 33.00 | 33.12 | 3 communities (Q3)
Bono & Ahafo | contractor |  |  | Ibbecow | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | Bedfi | 34.45 | 34.45 | 29 communities (Q3)
Bono & Ahafo | contractor |  |  | Manpower | 34.64 | 34.64 | 10 communities (Q3)
Bono & Ahafo | contractor |  |  | Kwanash | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | Prestige | 9.00 | 9.02 | 1 communities (Q3)
Bono & Ahafo | contractor |  |  | Kyeduma | 67.00 | 34.22 | 7 communities (Q3)
Bono & Ahafo | contractor |  |  | Pat Hayford Company Ltd | - | - | - communities (Q3)
Bono & Ahafo | contractor |  |  | Tanja Engineering Works | 35.03 | 35.03 | 15 communities (Q3)
Bono & Ahafo | contractor |  |  | Osmed Plus Company Limited | 28.0 | 31.84 | 10 communities (Q3)
Bono & Ahafo | contractor |  |  | Pure Tech Electricals Limited | 5.66 | 5.66 | 9 communities (Q3)
Bono & Ahafo | contractor |  |  | New Life Electrical $ Construction Limited | 28.66 | 28.66 | 9 communities (Q3)
Bono & Ahafo | contractor |  |  | Global New Beginning Electricals & Cont. Limited | 1.0 | 12.27 | 4 communities (Q3)
Bono & Ahafo | contractor |  |  | Apam A.E Company Limited | 76.18 | 87.87 | 28 communities (Q3)
Bono & Ahafo | contractor |  |  | Badjer Engineering Company Limited | 20.26 | 38.21 | 12 communities (Q3)
Bono & Ahafo | contractor |  |  | Faah Tech Engineering Company Limited | 19.10 | 19.10 | 6 communities (Q3)
Bono & Ahafo | contractor |  |  | Jasco Electrical Works Limited | 22.29 | 22.29 | 7 communities (Q3)
Bono & Ahafo | contractor |  |  | Upper View company Limited | 15.92 | 15.92 | 5 communities (Q3)
Bono & Ahafo | contractor |  |  | Amakye Global Links Enterprise | 25.47 | 25.47 | 8 communities (Q3)
Bono & Ahafo | contractor |  |  | TOTAL |  |  | 314 communities (Q3)
Central | community | ALL | 17th December, 2025 | Supply of some materials still outstanding | CONSULTANT and Contractors | MoEn
Central | community | UPPER DENKYIRA EAST | First reported – 8th June, 2023 | Replacement of defective poles still outstanding | CONSULTANT and Contractors
Central | community | UPPER/LOWER DENKYIRA | OPPONSO | NABIKO CONSTRUCTION CO. LTD. | 80 | 80 | 0
Central | community | UPPER/LOWER DENKYIRA | FAWOMAYE | NABIKO CONSTRUCTION CO. LTD. | 80 | 80 | 0
Central | community | UPPER/LOWER DENKYIRA | TEKYEMOSO | NABIKO CONSTRUCTION CO. LTD. | 80 | 80 | 0
Central | community | UPPER/LOWER DENKYIRA | KYEBI | NABIKO CONSTRUCTION CO. LTD. | 80 | 80 | 0
Central | community | UPPER/LOWER DENKYIRA | ATOBIASE | NABIKO CONSTRUCTION CO. LTD. | 80 | 80 | 0
Central | community | TWIFO ATTI MORKWA | BIMPONG AGYA NO. 2 | ELECTROTOPZ ENGINEERING WORKS | 90 | 90 | 0
Central | community | TWIFO ATTI MORKWA | BIMPONSO | ELECTROTOPZ ENGINEERING WORKS | 90 | 90 | 0
Central | community | TWIFO ATTI MORKWA | MANTEKROM | ELECTROTOPZ ENGINEERING WORKS | 85 | 85 | 0
Central | community | TWIFO ATTI MORKWA | CANNAN | ELECTROTOPZ ENGINEERING WORKS | 90 | 90 | 0
Central | community | TWIFO ATTI MORKWA | ASAMOAKROM | ELECTROTOPZ ENGINEERING WORKS | 90 | 90 | 0
Central | community | UPPER DENKYIRA WEST | ABOABOSO | WILLIDON | 55 | 55 | 0
Central | community | UPPER DENKYIRA WEST | ADWENPAYE | WILLIDON | 80 | 80 | 0
Central | community | UPPER DENKYIRA WEST | AKROFUOM | WILLIDON | 55 | 55 | 0
Central | community | UPPER DENKYIRA WEST | NIPANKROM | WILLIDON | 75 | 75 | 0
Central | community | UPPER DENKYIRA WEST | ANIANTENMAN | WILLIDON | 85 | 85 | 0
Central | community | AGONA EAST | FAAWHIA | WILLIDON | 80 | 80 | 0
Central | community | AGONA EAST | OSUANKWAA | WILLIDON | 85 | 85 | 0
Central | community | AGONA EAST | KOFI ABBAM | PAKASSEN LIMITED | 90 | 90 | 0
Central | community | AGONA EAST | OKOTOKWA | PAKASSEN LIMITED | 85 | 85 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AKUPAN | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | ANOMABOKUMA | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | KOBINA AGYIR | INFRASTUCTURE | 65 | 65 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | EHAWOHO | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | MAMA NYAMEBEKYERE | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | ESIKADO NO. 1 | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | ESIKADO NO. 2 | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | MOROKROM | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | MBOFRAFADWEN | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | ADZEYEPENA | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AJUMAKO OBRAYEKO | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | EYAN ATTAKWA | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | BISEASE NURSING | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AJUMAKO NEW SITE | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AJUMAKO EBENEZER | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | DWENEWOHO KOSOSEN | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AJUMAKO KROMIANFO | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | AKRA AWONA | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | IMMUNA AWONA | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | EKUMFI ABOR | INFRASTUCTURE | 0 | 0 | 0
Central | community | AJUMAKO- EYAN-ESSIAM | TWA | INFRASTUCTURE | 0 | 0 | 0
Central | community | UPPER DENKYIRA EAST | ABUAKWA AKRABONG | IKE ELECT. & CIVIL ENG. | 75 | 75 | 0
Central | community | UPPER DENKYIRA EAST | ADDO | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | UPPER DENKYIRA EAST | AKROMA | IKE ELECT. & CIVIL ENG. | 80 | 80 | 0
Central | community | UPPER DENKYIRA EAST | ALESEKWAA | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | UPPER DENKYIRA EAST | KOFI ENU KWA | IKE ELECT. & CIVIL ENG. | 75 | 75 | 0
Central | community | UPPER DENKYIRA EAST | KOKRABO | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | UPPER DENKYIRA EAST | KOKWADO | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | UPPER DENKYIRA EAST | KORTSIA | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | UPPER DENKYIRA EAST | KWAME NTSIFUL | IKE ELECT. & CIVIL ENG. | 70 | 70 | 0
Central | community | AGONA EAST | FAWHIA NO. 2 | LUKE AND SONS ENGINEERING CO. LTD. | 100 | 100 | 0
Central | community | AGONA EAST | KWESIKROM | LUKE AND SONS ENGINEERING CO. LTD. | 100 | 100 | 0
Central | community | AGONA EAST | DUABONE | LUKE AND SONS ENGINEERING CO. LTD. | 50 | 50 | 0
Central | community | AGONA EAST | AGONA NKRAN | LUKE AND SONS ENGINEERING CO. LTD. | 65 | 65 | 0
Central | community | AGONA EAST | MANSIFO | LUKE AND SONS ENGINEERING CO. LTD. | 100 | 100 | 0
Central | community | AGONA EAST | DAUDA/ACHAMFO | LUKE AND SONS ENGINEERING CO. LTD. | 65 | 65 | 0
Central | community | AGONA EAST | DOMOKYI | LUKE AND SONS ENGINEERING CO. LTD. | 80 | 80 | 0
Central | community | AGONA EAST | TAWORA | LUKE AND SONS ENGINEERING CO. LTD. | 50 | 50 | 0
Central | community | AGONA EAST | KWAME SAM | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | KWASI PAINTSIL | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | NAMPONG | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | OBREPO | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | OBUODURO | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | ODUGUAN | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | OKYENEKWA | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | PETERKWA | POWERTEC VENTURES | 90 | 90 | 0
Central | community | AGONA EAST | SANEKWA | POWERTEC VENTURES | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | ATEKYEM METAL | VOLTAGE ELECTRICALS | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | BOSENGA LINE | VOLTAGE ELECTRICALS | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | MBRADEN | VOLTAGE ELECTRICALS | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | KYEKYEREWERE | VOLTAGE ELECTRICALS | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | ASIKUMA | VOLTAGE ELECTRICALS | 90 | 90 | 0
Central | community | UPPER DENKYIRA EAST | AJIMPOMA | VOLTAGE ELECTRICALS | 60 | 60 | 0
Upper East | community | Binduri | Bansi Central | Guuru Link LTD | 92 | 92 | meters connected: 204
Upper East | community | Binduri | Natinga/Bansisakpa Natinga | Guuru Link LTD | 92 | 92 | meters connected: 124
Upper East | community | Binduri | Bansi Winaba | Payaba Enterprise | 90 | 90 | meters connected: 20
Upper East | community | Binduri | Ziako Tesnatinga / Buarin | Payaba Enterprise | 70 | 70 | meters connected: 80
Upper East | community | Binduri | Soogtinga/Buarin | KASN Engineering and Consult Ltd | 80 | 80 | meters connected: 55
Upper East | community | Binduri | Bazua NewTown/Biaka | KASN Engineering and Consult Ltd | 70 | 70 | meters connected: 35
Upper East | community | Garu | Samaduri | Farprise LTD | 42 | 42 | meters connected: 0
Upper East | community | Garu | Farfar Sabkuan | Farprise LTD | 30 | 30 | meters connected: 0
Upper East | community | Garu | Vambra | Farprise LTD | 35 | 35 | meters connected: 0
Upper East | community | Garu | Georin Aloko | Farprise LTD | 37 | 37 | meters connected: 0
Upper East | community | Garu | Songuuri | Farprise LTD | 45 | 45 | meters connected: 0
Upper East | community | Tampane | Benwoko | Powerboard Company LTD | 80 | 85 | meters connected: 65
Upper East | community | Tampane | Adugbal | Powerboard Company LTD | 45 | 45 | meters connected: 0
Upper East | community | Tampane | Bulpiese Nabuya | Powerboard Company LTD | 62 | 62 | meters connected: 0
Upper East | community | Tampane | Duayediga 2 | Powerboard Company LTD | 55 | 55 | meters connected: 0
Upper East | community | Tampane | Duayediga 3 | Powerboard Company LTD | 76 | 76 | meters connected: 0
Upper East | community | Tampane | Duayediga 1 | Powerboard Company LTD | 47 | 47 | meters connected: 0
Upper East | community | Tampane | Zotrikoum | Powerboard Company LTD | 50 | 80 | meters connected: 45
Upper East | community | Tampane | Tambalagu | Powerboard Company LTD | 46 | 46 | meters connected: 0
Upper East | community | Tampane | Trudiga | Powerboard Company LTD | 41 | 41 | meters connected: 0
Upper East | community | Tampane | Gabri Bolgatanga | Powerboard Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Zomandiga | Powerboard Company LTD | 53 | 75 | meters connected: 55
Upper East | community | Tampane | Kanbogun Zambala | Powerboard Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Timlgbog | Powerboard Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Mamamburi | Powerboard Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Kugasego Bugri | Washdan Company LTD | 61 | 61 | meters connected: 0
Upper East | community | Tampane | Jelakologo | Washdan Company LTD | 60 | 60 | meters connected: 0
Upper East | community | Tampane | Kolebore | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Nyosbara | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Terudig | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Tubong | Washdan Company LTD | 85 | 85 | meters connected: 60
Upper East | community | Tampane | Zotrikkuom | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Nadigiri | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Subzude | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Tampane | Nambina-Sigure | Washdan Company LTD | 67 | 67 | meters connected: 0
Upper East | community | Builsa South | Gbedemblisi | Kwofos Engineering Ltd | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana West | Kaliveo Awenia | Kwofos Engineering Ltd | 80 | 80 | meters connected: 158
Upper East | community | Bongo | Akendoo/Mission | Multi Amb LTD | 29 | 29 | meters connected: 0
Upper East | community | Bongo | Konkuaa | Multi Amb LTD | 29 | 29 | meters connected: 207
Upper East | community | Bongo | Ganlagrum | My Turn Standard Co. LTD | 99 | 99 | meters connected: 204
Upper East | community | Tampane | Zansibuliga # 1 | Standard Techs Engineering Service | 56 | 56 | meters connected: 0
Upper East | community | Bawku West | Alarigo | Albak Legacy Enterprise | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Azuwera | Albak Legacy Enterprise | 33 | 33 | meters connected: 0
Upper East | community | Garu | Takore | Jack Jeff Company Limited | 13 | 13 | meters connected: 0
Upper East | community | Bolgatanga | Atansobligu | Albak Legacy Enterprise | 44 | 44 | meters connected: 0
Upper East | community | Bawku West | Tarikom Gbere | Tuima Electricals Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Tarikom | Tuima Electricals Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Guzongo Salipiiga | Nantah-Waz Enterprise | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Sheiga | Nantah-Waz Enterprise | 0 | 0 | meters connected: 0
Upper East | community | Garu | Kolmasig 1 & 2 | mahamadu Asaki Company Limited | 0 | 0 | meters connected: 150
Upper East | community | Garu | Kuparbuliga | Nantah-Waz Enterprise | 0 | 0 | meters connected: 170
Upper East | community | Talensi | Zanwore | KASN Engineering and Consult Ltd | 100 | 100 | meters connected: 130
Upper East | community | Talensi | Degaare | KASN Engineering and Consult Ltd | 100 | 100 | meters connected: 100
Upper East | community | Talensi | Kuzoo/Sapakyare | KASN Engineering and Consult Ltd | 100 | 100 | meters connected: 210
Upper East | community | Garu | Kukparbuliga | Nantah-Waz Enterprise | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Asabire | Daniel Abatara Elect. | 30 | 30 | meters connected: 0
Upper East | community | Bongo | Asabire Doone | Daniel Abatara Elect. | 63 | 63 | meters connected: 0
Upper East | community | Bongo | Bungu | Daniel Abatara Elect. | 63 | 63 | meters connected: 0
Upper East | community | Garu | Zansibuliga 2 | Hassanash Nash Ventures | 33 | 33 | meters connected: 0
Upper East | community | Garu | Zansibuliga 3 | Hassanash Nash Ventures | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Saka | Jack Jeff Company Limited | 23 | 23 | meters connected: 0
Upper East | community | Bawku West | Zeogo | Psam 91 Electricals | 23 | 23 | meters connected: 0
Upper East | community | Bawku West | Widnaba | Psam 91 Electricals | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Biaknawezer | Psam 91 Electricals | 23 | 23 | meters connected: 0
Upper East | community | Bolga/Talensi | Kumbiligo | Alback legacy Company Limited | 58 | 58 | meters connected: 0
Upper East | community | Binduri | Kologo-Natinga | Powertech Engineering Ltd | 85 | 85 | meters connected: 50
Upper East | community | Binduri | Kologo-Tingre | Powertech Engineering Ltd | 56 | 90 | meters connected: 60
Upper East | community | Binduri | Kuloko Yoldeing | Powertech Engineering Ltd | 91 | 91 | meters connected: 0
Upper East | community | Binduri | Kolok Gumyako | Powertech Engineering Ltd | 58 | 58 | meters connected: 0
Upper East | community | Binduri | Kuloko Aporozua | Powertech Engineering Ltd | 56 | 56 | meters connected: 0
Upper East | community | Binduri | Yalugu Natinga/ | Powertech Engineering Ltd | 65 | 65 | meters connected: 0
Upper East | community | Binduri | Barigun/Magnori | Powertech Engineering Ltd | 54 | 54 | meters connected: 0
Upper East | community | Binduri | Yalugu Ganaga | Powertech Engineering Ltd | 68 | 68 | meters connected: 0
Upper East | community | Binduri | Yalugu Kpanating | Powertech Engineering Ltd | 55 | 55 | meters connected: 0
Upper East | community | Binduri | Barabogo Tengbeong | Powertech Engineering Ltd | 49 | 49 | meters connected: 0
Upper East | community | Binduri | Barabogo Natinga | Powertech Engineering Ltd | 68 | 68 | meters connected: 0
Upper East | community | Binduri | Agumsi Bulzua | Powertech Engineering Ltd | 56 | 56 | meters connected: 0
Upper East | community | Binduri | Agumsi Natinga | Powertech Engineering Ltd | 56 | 56 | meters connected: 0
Upper East | community | Binduri | Agumsi Tambig Natinga | Powertech Engineering Ltd | 56 | 56 | meters connected: 0
Upper East | community | Binduri | Nafkoliga Tambizeeg | Powertech Engineering Ltd | 56 | 56 | meters connected: 0
Upper East | community | Binduri | Nafkoliga Agumsi | Powertech Engineering Ltd | 44 | 44 | meters connected: 0
Upper East | community | Binduri | Nafkoliga Natinga | Powertech Engineering Ltd | 51 | 51 | meters connected: 0
Upper East | community | Builsa North | Chuchuliga-Awuchinayeri | Wilwak Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Builsa North | Chuchuliga-Yiepala | Wilwak Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Builsa North | Jaata | Wilwak Enterprise Limited | 28 | 28 | meters connected: 0
Upper East | community | Builsa North | Molinsa | Wilwak Enterprise Limited | 30 | 30 | meters connected: 0
Upper East | community | Builsa North | Tajirinsa | Wilwak Enterprise Limited | 33 | 33 | meters connected: 0
Upper East | community | Builsa North | Tampela | Wilwak Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Builsa North | Kaasa | Wilwak Enterprise Limited | 25 | 25 | meters connected: 0
Upper East | community | Builsa North | Yiekpen No. 1 | Wilwak Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Builsa North | Yiekpen No. 2 | Wilwak Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Builsa North | Jangsa | Wilwak Enterprise Limited | 22 | 22 | meters connected: 37
Upper East | community | Builsa North | Kalijisa | Wilwak Enterprise Limited | 90 | 90 | meters connected: 100
Upper East | community | Builsa North | Fiisa | Wilwak Enterprise Limited | 96 | 96 | meters connected: 50
Upper East | community | Garu Tempane | Kpukparibuliga | EX-TEE Electricals Ltd. | 0 | 0 | meters connected: 0
Upper East | community | Garu Tempane | Atamidabog | EX-TEE Electricals Ltd. | 0 | 0 | meters connected: 0
Upper East | community | Garu Tempane | Mengnatim | EX-TEE Electricals Ltd. | 0 | 0 | meters connected: 0
Upper East | community | Garu Tempane | Yousbara | EX-TEE Electricals Ltd. | 80 | 80 | meters connected: 185
Upper East | community | Garu Tempane | Yousbara #1 | EX-TEE Electricals Ltd. | 85 | 85 | meters connected: 195
Upper East | community | Garu Tempane | Tendana | EX-TEE Electricals Ltd. | 88 | 88 | meters connected: 150
Upper East | community | Garu Tempane | Tendana-Yabrago #2 | EX-TEE Electricals Ltd. | 35 | 35 | meters connected: 103
Upper East | community | Garu Tempane | Tendana-Yabrago #1 | EX-TEE Electricals Ltd. | 41 | 41 | meters connected: 120
Upper East | community | Garu Tempane | Karateshie-Nanteng | EX-TEE Electricals Ltd. | 7 | 7 | meters connected: 70
Upper East | community | Garu Tempane | Karateshie-Basic School | EX-TEE Electricals Ltd. | 9 | 9 | meters connected: 0
Upper East | community | Garu Tempane | Karateshie-Kparasako | EX-TEE Electricals Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Garu Tempane | Karateshie-Natinga Old | EX-TEE Electricals Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Garu Tempane | Bugri Abarsandabogun/Ku | EX-TEE Electricals Ltd. | 16 | 16 | meters connected: 0
Upper East | community | Kasena Nankana East | Lower Nangalikinnia No. 1 | Budic Electrical & Engineering Works | 31 | 31 | meters connected: 63
Upper East | community | Kasena Nankana East | Lower Nangalikinnia No. 2 | Budic Electrical & Engineering Works | 29 | 29 | meters connected: 66
Upper East | community | Kasena Nankana East | Janania-Gaani | Budic Electrical & Engineering Works | 81 | 81 | meters connected: 183
Upper East | community | Kasena Nankana East | Kasinia-Korania | Budic Electrical & Engineering Works | 49 | 49 | meters connected: 0
Upper East | community | Kasena Nankana East | Kworise-Korania | Budic Electrical & Engineering Works | 55 | 55 | meters connected: 102
Upper East | community | Kasena Nankana East | Avbisi/Dozongo | Budic Electrical & Engineering Works | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana East | Geribisi | Budic Electrical & Engineering Works | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Akumbisi | Budic Electrical & Engineering Works | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana East | Kundalsa-Biu | Budic Electrical & Engineering Works | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana East | Jaagu-Biu | Budic Electrical & Engineering Works | 11 | 11 | meters connected: 0
Upper East | community | Kasena Nankana East | Gunsa | Budic Electrical & Engineering Works | 19 | 19 | meters connected: 0
Upper East | community | Kasena Nankana East | Upper Gaani | Budic Electrical & Engineering Works | 13 | 13 | meters connected: 0
Upper East | community | Kasena Nankana East | Lower Gaani | Budic Electrical & Engineering Works | 9 | 9 | meters connected: 0
Upper East | community | Kasena Nankana West | Saaka | Richmanda Enterprise Ltd. | 75 | 75 | meters connected: 127
Upper East | community | Kasena Nankana West | Tazika | Richmanda Enterprise Ltd. | 80 | 80 | meters connected: 210
Upper East | community | Kasena Nankana West | Kazugu | Richmanda Enterprise Ltd. | 70 | 70 | meters connected: 229
Upper East | community | Kasena Nankana West | Kazugu Navio JSS | Richmanda Enterprise Ltd. | 79 | 79 | meters connected: 178
Upper East | community | Kasena Nankana West | Kuliya #1 | Richmanda Enterprise Ltd. | 67 | 67 | meters connected: 220
Upper East | community | Kasena Nankana West | Kuliya #2 | Richmanda Enterprise Ltd. | 82 | 82 | meters connected: 187
Upper East | community | Kasena Nankana West | Bagtua | Richmanda Enterprise Ltd. | 80 | 80 | meters connected: 117
Upper East | community | Bawku | Kpaliga | Ibbecow Company Limited | 85 | 85 | meters connected: 220
Upper East | community | Bawku | Sugure | Ibbecow Company Limited | 69 | 69 | meters connected: 169
Upper East | community | Bawku | Yampan-Lalsaa Basic Sch. | Ibbecow Company Limited | 87 | 87 | meters connected: 116
Upper East | community | Bawku | Yampan-Lalsaa | Ibbecow Company Limited | 81 | 81 | meters connected: 58
Upper East | community | Bawku | Yampan-Lalsaa Tingre | Ibbecow Company Limited | 83 | 83 | meters connected: 105
Upper East | community | Bawku | Kukrabod | Ibbecow Company Limited | 78 | 78 | meters connected: 63
Upper East | community | Bawku | Yakin | Ibbecow Company Limited | 80 | 80 | meters connected: 102
Upper East | community | Bongo | Kangkoo | Khesby Engineering Ltd. | 88 | 90 | meters connected: 70
Upper East | community | Bongo | Vea-Zangongo | Khesby Engineering Ltd. | 120 | 120 | meters connected: 103
Upper East | community | Bongo | Kulipeeliga | Khesby Engineering Ltd. | 92 | 92 | meters connected: 83
Upper East | community | Bongo | Tarongo Awaah | Khesby Engineering Ltd. | 88 | 88 | meters connected: 91
Upper East | community | Bongo | Sapeeba/Ayelbia | Khesby Engineering Ltd. | 92 | 92 | meters connected: 100
Upper East | community | Bawku West | Ziki Asobilla | Jews Electricals Limited | 53 | 53 | meters connected: 0
Upper East | community | Bawku West | Dangunga Ziboko | Jews Electricals Limited | 13 | 70 | meters connected: 0
Upper East | community | Bawku West | Dangunga Basic School | Jews Electricals Limited | 39 | 63 | meters connected: 0
Upper East | community | Bawku West | Dangunga Makpale | Jews Electricals Limited | 22 | 75 | meters connected: 0
Upper East | community | Bawku West | Dangunga Gbango | Jews Electricals Limited | 67 | 67 | meters connected: 0
Upper East | community | Bawku West | Dangunga Gundango | Jews Electricals Limited | 33 | 55 | meters connected: 0
Upper East | community | Bawku West | Kansongo | Jews Electricals Limited | 33 | 63 | meters connected: 0
Upper East | community | Bawku West | Sakpare | Jews Electricals Limited | 50 | 50 | meters connected: 0
Upper East | community | Bawku West | Timpeligo Yipala | Jews Electricals Limited | 48 | 48 | meters connected: 0
Upper East | community | Bawku West | Timpeligo Cental/Googo | Jews Electricals Limited | 29 | 29 | meters connected: 0
Upper East | community | Builsa South | Fumbisi-Bachiesa | Kwodam Elect. Eng. Ltd. | 44 | 44 | meters connected: 0
Upper East | community | Builsa South | Bachiesa-Sainyanyeri | Kwodam Elect. Eng. Ltd. | 46 | 46 | meters connected: 0
Upper East | community | Builsa South | Fumbisi-Batuisa | Kwodam Elect. Eng. Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Fumbisi-Sinsangsa | Kwodam Elect. Eng. Ltd. | 66 | 66 | meters connected: 0
Upper East | community | Builsa South | Bachonsa | Kwodam Elect. Eng. Ltd. | 46 | 46 | meters connected: 0
Upper East | community | Pusiga | Sugudi Duakom | Mohatu Electrical Limited | 78 | 78 | meters connected: 0
Upper East | community | Pusiga | Tambiugu | Mohatu Electrical Limited | 85 | 85 | meters connected: 0
Upper East | community | Pusiga | Pulmakuom Koose-Jingle | Mohatu Electrical Limited | 71 | 71 | meters connected: 0
Upper East | community | Pusiga | Pulmakuom Koose | Mohatu Electrical Limited | 72 | 72 | meters connected: 60
Upper East | community | Pusiga | Pilmakuom Central | Mohatu Electrical Limited | 68 | 68 | meters connected: 70
Upper East | community | Pusiga | Sanga # 3 | Mohatu Electrical Limited | 69 | 69 | meters connected: 50
Upper East | community | Pusiga | Sanga Chief's Palace | Mohatu Electrical Limited | 70 | 70 | meters connected: 70
Upper East | community | Pusiga | Dabia # 1 | Mohatu Electrical Limited | 94 | 94 | meters connected: 30
Upper East | community | Pusiga | Dabia # 2 | Mohatu Electrical Limited | 80 | 80 | meters connected: 80
Upper East | community | Pusiga | Bulungu- Koltisi # 1 | Mohatu Electrical Limited | 79 | 79 | meters connected: 0
Upper East | community | Pusiga | Bulungu- Koltisi # 2 | Mohatu Electrical Limited | 100 | 100 | meters connected: 120
Upper East | community | Pusiga | Bulungu-Zopeliga | Mohatu Electrical Limited | 58 | 58 | meters connected: 0
Upper East | community | Pusiga | Kampodi-Tambnogin | Mohatu Electrical Limited | 65 | 65 | meters connected: 55
Upper East | community | Pusiga | Kampodi-# 1&2 | Mohatu Electrical Limited | 69 | 69 | meters connected: 45
Upper East | community | Pusiga | Zuabulga # 1 | Mohatu Electrical Limited | 67 | 67 | meters connected: 0
Upper East | community | Pusiga | Zuabulga # 2 | Mohatu Electrical Limited | 85 | 85 | meters connected: 0
Upper East | community | Talensi | Nungu | E.K.Asare Enterprise Ltd. | 30 | 30 | meters connected: 0
Upper East | community | Talensi | Nungu-Biengo | E.K.Asare Enterprise Ltd. | 53 | 53 | meters connected: 0
Upper East | community | Talensi | Duusi-Natinga | E.K.Asare Enterprise Ltd. | 42 | 42 | meters connected: 0
Upper East | community | Builsa North | Wiaga Longsa | A.A Awuchei Electricals Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North | Tankansa | A.A Awuchei Electricals Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North | Bayanags A Beliwmaz UK | A.A Awuchei Electricals Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North | Mwanlon GSA | A.A Awuchei Electricals Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North | Yimonsa (Kpikpal UK) | A.A Awuchei Electricals Limited | 0 | 0 | meters connected: 0
Upper East | community | Talensi | Winkongo Goriko Chief Palace | E.K.Asare Enterprise Limited | 80 | 80 | meters connected: 220
Upper East | community | Bawku | Parsnatinga/Azara-Saa | Kwofos Engineering Limited | 60 | 60 | meters connected: 59
Upper East | community | Bawku | Zuuku Kutanga/Sampiase | Kwofos Engineering Limited | 70 | 70 | meters connected: 73
Upper East | community | Bawku | Missiga Yas Natinga #1 | Kwofos Engineering Limited | 44 | 70 | meters connected: 106
Upper East | community | Bawku | Missiga Yas Natinga #2 | Kwofos Engineering Limited | 44 | 70 | meters connected: 101
Upper East | community | Bawku | Gumakutari (Ext) (1&2) | Kwofos Engineering Limited | 19 | 69 | meters connected: 104
Upper East | community | Bawku | Gumakutari Chief 's Palace | Kwofos Engineering Limited | 43 | 43 | meters connected: 58
Upper East | community | Bawku | Galaka -Mognori | Kwofos Engineering Limited | 18 | 18 | meters connected: 70
Upper East | community | Bawku | Mognori Baribari/ Abisigin/Awigbeeg/Zeidbin ( | Kwofos Engineering Limited | 33 | 33 | meters connected: 53
Upper East | community | Bawku West | Komako Basic School | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Yiikikugu Gumbia | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Komako | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Gbezuoza | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Salpiiga | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Kaare Natinga | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Ziika | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Kare Natinga Yapalla | Bosco Light Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Gadema Tajirinsa | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Gadema Tampela | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Sakpare Suuni | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Bapelugu | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Buugin | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Tengre Yagre | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Builsa North & Talensi | Nandoya Talahig | Jeopa Company Limited | 0 | 0 | meters connected: 0
Upper East | community | Tempane | Abarpusiga | Korigu Engineering Construction Limited | 0 | 70 | meters connected: 0
Upper East | community | Tempane | Sumadure | Korigu Engineering Construction Limited | 0 | 66 | meters connected: 0
Upper East | community | Tempane | Komkomada#1 | Korigu Engineering Construction Limited | 0 | 67 | meters connected: 0
Upper East | community | Tempane | Komkomada#2 | Korigu Engineering Construction Limited | 0 | 60 | meters connected: 0
Upper East | community | Tempane | Tipint | Korigu Engineering Construction Limited | 0 | 75 | meters connected: 0
Upper East | community | Tempane | Bimpella 1 | Korigu Engineering Construction Limited | 0 | 55 | meters connected: 0
Upper East | community | Tempane | Bimpella 2 | Korigu Engineering Construction Limited | 0 | 60 | meters connected: 0
Upper East | community | Tempane | Doanyediga 2 | Korigu Engineering Construction Limited | 0 | 43 | meters connected: 0
Upper East | community | Tempane | Nagani-Kparsako | Korigu Engineering Construction Limited | 0 | 78 | meters connected: 0
Upper East | community | Tempane | Ninsum | Korigu Engineering Construction Limited | 0 | 56 | meters connected: 0
Upper East | community | Bongo | Abagribono/Ayogate | Osei Kuffour Electrical Company Limited | 17 | 78 | meters connected: 0
Upper East | community | Bongo | Akirikenkua Ext. | Osei Kuffour Electrical Company Limited | 17 | 60 | meters connected: 0
Upper East | community | Bawku West | Binba/Awedkoliko | Perzoo Limited | 0 | 0 | meters connected: 0
Upper East | community | Bawku West | Bina/Kpalkwolgo | Perzoo Limited | 0 | 0 | meters connected: 0
Upper East | community | Bolgatanga East | Zonno-Zori | Twumasi & Co Engineering Limited | 45 | 70 | meters connected: 0
Upper East | community | Bolgatanga East | Kantia | Twumasi & Co Engineering Limited | 50 | 75 | meters connected: 0
Upper East | community | Bolgatanga East | Gonno Zue | Twumasi & Co Engineering Limited | 60 | 60 | meters connected: 0
Upper East | community | Bolgatanga East | Kagrebiisi | Twumasi & Co Engineering Limited | 42 | 80 | meters connected: 70
Upper East | community | Bolgatanga East | Asongen | Twumasi & Co Engineering Limited | 55 | 80 | meters connected: 80
Upper East | community | Bolgatanga East | Sakoote | Twumasi & Co Engineering Limited | 40 | 75 | meters connected: 56
Upper East | community | Bolgatanga East | Kalanga | Twumasi & Co Engineering Limited | 70 | 70 | meters connected: 100
Upper East | community | Bawku West | Zoayanga No.1 | Budic Engineering Ltd. | 44 | 44 | meters connected: 0
Upper East | community | Bawku West | Zoayanga No.2 | B- Bone Electrical Enterprise | 44 | 44 | meters connected: 0
Upper East | community | Bongo | Vea-Tanga Poren | Budic Engineering Ltd. | 56 | 56 | meters connected: 00
Upper East | community | Bongo | Vea-Nayikura | Budic Engineering Ltd. | 51 | 51 | meters connected: 0
Upper East | community | Bongo | Anafobiisi Zuin | Budic Engineering Ltd. | 56 | 95 | meters connected: 129
Upper East | community | Kasena Nankana West | Azinzoka | Budic Engineering Ltd. | 24 | 24 | meters connected: 0
Upper East | community | Kasena Nankana West | Gonnum-Aku | Budic Engineering Ltd. | 36 | 36 | meters connected: 0
Upper East | community | Kasena Nankana West | Gonnum-Daboo | Budic Engineering Ltd. | 38 | 38 | meters connected: 0
Upper East | community | Kasena Nankana West | Zampeego | Budic Engineering Ltd. | 44 | 44 | meters connected: 0
Upper East | community | Kasena Nankana West | Tintuumbisi | Budic Engineering Ltd. | 52 | 52 | meters connected: 0
Upper East | community | Bongo | Konkua Doone | Budic Electrical & Engineering Works | 70 | 70 | meters connected: 25
Upper East | community | Bongo | Apuwongo-Tingre | E.K. Asare Enterprise | 68 | 68 | meters connected: 0
Upper East | community | Bongo | Yekine Tingre | E.K. Asare Enterprise | 61 | 61 | meters connected: 0
Upper East | community | Bongo | Boko Azumbuo | E.K. Asare Enterprise | 37 | 37 | meters connected: 0
Upper East | community | Bongo | Boko Asackow | E.K. Asare Enterprise | 57 | 57 | meters connected: 0
Upper East | community | Bongo | Apuwongo Zui | E.K. Asare Enterprise | 26 | 26 | meters connected: 0
Upper East | community | Bongo | Boko Kumabilgo | E.K. Asare Enterprise | 30 | 30 | meters connected: 0
Upper East | community | Pusiga | Kulungugu Chamata | Ibbecow Company Ltd | 43 | 89 | meters connected: 70
Upper East | community | Pusiga | Kulungugu Natinga | Ibbecow Company Ltd | 80 | 80 | meters connected: 20
Upper East | community | Pusiga | Kulungugu Cinkon | Ibbecow Company Ltd | 59 | 59 | meters connected: 37
Upper East | community | Pusiga | Kulungugu CEPS | Ibbecow Company Ltd | 59 | 59 | meters connected: 100
Upper East | community | Binduri | Tirago | Ampohblay Will Ltd | 30 | 30 | meters connected: 30
Upper East | community | Binduri | Iddi | Ampohblay Will Ltd | 35 | 35 | meters connected: 0
Upper East | community | Binduri | Agon-Nara | Ampohblay Will Ltd | 100 | 100 | meters connected: 80
Upper East | community | Binduri | Tinogo | Ampohblay Will Ltd | 11 | 11 | meters connected: 0
Upper East | community | Binduri | Nin-Sarko | Ampohblay Will Ltd | 37 | 37 | meters connected: 0
Upper East | community | Binduri | Nara Sung | Ampohblay Will Ltd | 92 | 92 | meters connected: 85
Upper East | community | Binduri | Sakperi-Natinga | Ampohblay Will Ltd | 88 | 88 | meters connected: 60
Upper East | community | Binduri | Sarabogo | Ampohblay Will Ltd | 33 | 33 | meters connected: 0
Upper East | community | Binduri | Avondango Chief's Palace | Ampohblay Will Ltd | 80 | 80 | meters connected: 69
Upper East | community | Binduri | Zuulugo | Ampohblay Will Ltd | 72 | 72 | meters connected: 0
Upper East | community | Binduri | Avondango Market | Ampohblay Will Ltd | 88 | 88 | meters connected: 0
Upper East | community | Bolgatanga Mun. | Polugu | Richmanda Eng. Ltd | 119 | 119 | meters connected: 210
Upper East | community | Bolgatanga Mun. | Kumbosco | Richmanda Eng. Ltd | 85 | 85 | meters connected: 0
Upper East | community | Bolgatanga Mun. | Kumbosco Clinic | Richmanda Eng. Ltd | 90 | 90 | meters connected: 157
Upper East | community | Bolgatanga Mun. | Yarigabisi - Asogrebisi | Richmanda Eng. Ltd | 107 | 107 | meters connected: 179
Upper East | community | Bolgatanga Mun. | Yarigabisi - Agungabisi | Richmanda Eng. Ltd | 103 | 103 | meters connected: 220
Upper East | community | Bolgatanga Mun. | Yarigabisi - Awanabisi | Richmanda Eng. Ltd | 96 | 96 | meters connected: 146
Upper East | community | Bolgatanga Mun. | Yarigabisi - Ricemill | Richmanda Eng. Ltd | 167 | 167 | meters connected: 53
Upper East | community | Bolgatanga Mun. | Tongo Beo Primary | Richmanda Eng. Ltd | 109 | 109 | meters connected: 184
Upper East | community | Bolgatanga Mun. | Tongo Beo Chief's Palace | Richmanda Eng. Ltd | 123 | 123 | meters connected: 63
Upper East | community | Bongo | Tankuo (Tankoo) | Richmanda Eng. Ltd | 99 | 99 | meters connected: 132
Upper East | community | Bongo | Tankuo Nayiri | Richmanda Eng. Ltd | 99 | 99 | meters connected: 105
Upper East | community | Talensi | Namoranteng | Budic Electrical & Engineering Works | 101 | 101 | meters connected: 102
Upper East | community | Talensi | Santeng | Budic Electrical & Engineering Works | 107 | 107 | meters connected: 202
Upper East | community | Talensi | Tenzuk | Budic Electrical & Engineering Works | 90 | 90 | meters connected: 174
Upper East | community | Talensi | Duusi-Tindongo | Budic Electrical & Engineering Works | 80 | 80 | meters connected: 210
Upper East | community | Talensi | Yaale | Budic Electrical & Engineering Works | 38 | 38 | meters connected: 0
Upper East | community | Kasena Nankana West. | Azinzoka | Budic Electrical & Engineering Works | 29 | 29 | meters connected: 0
Upper East | community | Kasena Nankana West. | Gonnum Daboo | Budic Electrical & Engineering Works | 37 | 37 | meters connected: 0
Upper East | community | Kasena Nankana West. | Gonnum Aku-A | Budic Electrical & Engineering Works | 36 | 36 | meters connected: 0
Upper East | community | Kasena Nankana West. | Zampeego/Apibisi | Budic Electrical & Engineering Works | 31 | 31 | meters connected: 0
Upper East | community | Kasena Nankana West. | Tintuumbisi | Budic Electrical & Engineering Works | 52 | 52 | meters connected: 0
Upper East | community | Builsa South | Jiningsa | Kwodam Electrical Ent. | 57 | 57 | meters connected: 106
Upper East | community | Builsa South | Nyakasa/Piisa | Kwodam Electrical Ent. | 123 | 123 | meters connected: 60
Upper East | community | Builsa South | Samsa | Kwodam Electrical Ent. | 43 | 43 | meters connected: 60
Upper East | community | Builsa South | Sikabsa | Kwodam Electrical Ent. | 87 | 87 | meters connected: 30
Upper East | community | Builsa South | Zogsa | Kwodam Electrical Ent. | 67 | 67 | meters connected: 20
Upper East | community | Builsa South | Luisa | Kwodam Electrical Ent. | 28 | 28 | meters connected: 100
Upper East | community | Builsa South | Kunyinsa | Kwodam Electrical Ent. | 100 | 100 | meters connected: 100
Upper East | community | Builsa North | Kori-Alabyire | Powertech Engineering Services Ltd. | 55 | 55 | meters connected: 0
Upper East | community | Builsa North | Kori-Kanansa Kauesa | Powertech Engineering Services Ltd. | 58 | 58 | meters connected: 0
Upper East | community | Builsa North | Kori-Kanansa | Powertech Engineering Services Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Builsa North | Yipaala # 1 | Powertech Engineering Services Ltd. | 56 | 56 | meters connected: 0
Upper East | community | Builsa North | Yipaala # 2 | Powertech Engineering Services Ltd. | 56 | 56 | meters connected: 0
Upper East | community | Builsa North | Awichaanayire | Powertech Engineering Services Ltd. | 56 | 56 | meters connected: 0
Upper East | community | Builsa North | Chanyire Nanjana-Yea | Powertech Engineering Services Ltd. | 56 | 56 | meters connected: 0
Upper East | community | Builsa North | Chanyire-Guuta | Powertech Engineering Services Ltd. | 56 | 56 | meters connected: 0
Upper East | community | Builsa North | Chanyire-Yipaala | Powertech Engineering Services Ltd. | 63 | 63 | meters connected: 0
Upper East | community | Pusiga | Koose Sanga | Joditec Electrical Ltd | 34 | 34 | meters connected: 0
Upper East | community | Pusiga | Koose Chief's Palace | Joditec Electrical Ltd | 61 | 61 | meters connected: 0
Upper East | community | Pusiga | Bimpiela #1 | Joditec Electrical Ltd | 87 | 87 | meters connected: 89
Upper East | community | Pusiga | Bimpiela #2 | Joditec Electrical Ltd | 88 | 88 | meters connected: 100
Upper East | community | Pusiga | Kogadem | Joditec Electrical Ltd | 51 | 51 | meters connected: 0
Upper East | community | Pusiga | Belimtanga | J-Karimus Company Ltd. | 89 | 100 | meters connected: 81
Upper East | community | Pusiga | Salwabin | J-Karimus Company Ltd. | 89 | 100 | meters connected: 94
Upper East | community | Pusiga | Tesgbego | J-Karimus Company Ltd. | 89 | 100 | meters connected: 105
Upper East | community | Pusiga | Sarabogo | J-Karimus Company Ltd. | 89 | 100 | meters connected: 84
Upper East | community | Pusiga | Palnnaba | J-Karimus Company Ltd. | 89 | 100 | meters connected: 42
Upper East | community | Kasena Nankana West. | Ayingayire/Akaoore | Kwofos Engineering Ltd. | 10 | 10 | meters connected: 0
Upper East | community | Kasena Nankana West. | Gayingo/Bolinga (Nayeri) | Kwofos Engineering Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West. | Aburiwasa/Leengo | Kwofos Engineering Ltd. | 12 | 12 | meters connected: 0
Upper East | community | Kasena Nankana West. | Achuligoyire | Kwofos Engineering Ltd. | 10 | 10 | meters connected: 0
Upper East | community | Kasena Nankana East. | Sonnu-Kura Nayagenia | Kwofos Engineering Ltd. | 85 | 85 | meters connected: 62
Upper East | community | Kasena Nankana East. | Nayegenia Ext. | Kwofos Engineering Ltd. | 85 | 85 | meters connected: 90
Upper East | community | Bolgatanga Municipality | Nyonkoko/Asonge | Richmanda Eng. Ltd | 58 | 58 | meters connected: 13
Upper East | community | Bolgatanga Municipality | Benkote (Ext) | Richmanda Eng. Ltd | 15 | 15 | meters connected: 5
Upper East | community | Bolgatanga Municipality | Zoore | Richmanda Eng. Ltd | 79 | 79 | meters connected: 53
Upper East | community | Bolgatanga Municipality | Genebiisi/Banenbiisi | Richmanda Eng. Ltd | 81 | 81 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Pogwongbiisi/Kokan | Richmanda Eng. Ltd | 92 | 92 | meters connected: 80
Upper East | community | Bolgatanga Municipality | Akenga (Ext) | Richmanda Eng. Ltd | 14 | 14 | meters connected: 21
Upper East | community | Bolgatanga Municipality | Boosiya (ext) | Richmanda Eng. Ltd | 32 | 32 | meters connected: 44
Upper East | community | Bolgatanga Municipality | Boosiya Gambigo Tingre | Richmanda Eng. Ltd | 103 | 103 | meters connected: 204
Upper East | community | Bolgatanga Municipality | Soorebiisi | Richmanda Eng. Ltd | 110 | 110 | meters connected: 123
Upper East | community | Bolgatanga Municipality | Tansobkor | Richmanda Eng. Ltd | 100 | 100 | meters connected: 53
Upper East | community | Bolgatanga Municipality | Nyangu Yorogo Asogrebiisi | Richmanda Eng. Ltd | 35 | 35 | meters connected: 55
Upper East | community | Bolgatanga Municipality | Zenga | Richmanda Eng. Ltd | 87 | 87 | meters connected: 74
Upper East | community | Bolgatanga Municipality | Tokobiisi | Richmanda Eng. Ltd | 61 | 61 | meters connected: 39
Upper East | community | Bolgatanga Municipality | Dorongo New | Richmanda Eng. Ltd | 70 | 70 | meters connected: 23
Upper East | community | Bolgatanga Municipality | Akegma/tampo | Richmanda Eng. Ltd | 91 | 91 | meters connected: 160
Upper East | community | Bolgatanga Municipality | Katanga Boko | Richmanda Eng. Ltd | 96 | 96 | meters connected: 75
Upper East | community | Bolgatanga Municipality | Anaba-Doone | Richmanda Eng. Ltd | 104 | 104 | meters connected: 42
Upper East | community | Bolgatanga Municipality | Nyaariga Doone | Richmanda Eng. Ltd | 106 | 106 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Kembisi | Khesby Engineering Ltd. | 57 | 57 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Zurebisi | Khesby Engineering Ltd. | 77 | 77 | meters connected: 84
Upper East | community | Bolgatanga Municipality | Kumberigo | Khesby Engineering Ltd. | 83 | 83 | meters connected: 79
Upper East | community | Bolgatanga Municipality | Nyonkoko | Khesby Engineering Ltd. | 79 | 79 | meters connected: 13
Upper East | community | Bolgatanga Municipality | Sirigu (Nayire) / Tangabiisi | Khesby Engineering Ltd. | 46 | 46 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Sapio | Khesby Engineering Ltd. | 57 | 57 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Tinganibiisi | Khesby Engineering Ltd. | 74 | 74 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Bugelego | Khesby Engineering Ltd. | 58 | 58 | meters connected: 0
Upper East | community | Bolgatanga Municipality | Mossi | Khesby Engineering Ltd. | 64 | 90 | meters connected: 30
Upper East | community | Bolgatanga Municipality | Ayesikabiisi | Khesby Engineering Ltd. | 50 | 75 | meters connected: 44
Upper East | community | Bolgatanga Municipality | Dubila | Khesby Engineering Ltd. | 38 | 85 | meters connected: 35
Upper East | community | Bawku West | Bugore | Quanta Elect. Co. Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Gozesi | Quanta Elect. Co. Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Sitande | Quanta Elect. Co. Ltd. | 46 | 46 | meters connected: 0
Upper East | community | Bawku West | Kopella | Quanta Elect. Co. Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Agaogo | Quanta Elect. Co. Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Zeego | Quanta Elect. Co. Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Gabuliga | Quanta Elect. Co. Ltd. | 36 | 36 | meters connected: 0
Upper East | community | Bawku West | Alotam/Wiriguud | Dokmel Elect. Eng. Works | 56 | 56 | meters connected: 0
Upper East | community | Bawku West | Kpalsako | Dokmel Elect. Eng. Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Tang Dabote | Dokmel Elect. Eng. Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Ayad/Kinab-Dabote | Dokmel Elect. Eng. Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Toende | Dokmel Elect. Eng. Works | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Wiiga/Gunga | Dokmel Elect. Eng. Works | 33 | 33 | meters connected: 0
Upper East | community | Kasena Nankana West | Gumongo | Buhas Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Alimbila | Buhas Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Nabango Nyongo | Buhas Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Dazongo | Buhas Enterprise Limited | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Wolingum | Metro Energy & Training Wks. | 31 | 31 | meters connected: 0
Upper East | community | Kasena Nankana West | Akadaka | Metro Energy & Training Wks. | 21 | 21 | meters connected: 0
Upper East | community | Kasena Nankana West | Pingo/Tikongo | Metro Energy & Training Wks. | 20 | 20 | meters connected: 0
Upper East | community | Kasena Nankana West | Abuguziondone | Metro Energy & Training Wks. | 20 | 20 | meters connected: 0
Upper East | community | Kasena Nankana West | Kansan | King Nimod Electrical | 53 | 53 | meters connected: 0
Upper East | community | Kasena Nankana West | Pungbisi/Kulnyurisum | King Nimod Electrical | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Kasalingo/Chengo | King Nimod Electrical | 27 | 27 | meters connected: 0
Upper East | community | Kasena Nankana West | Kumbusigo | King Nimod Electrical | 45 | 80 | meters connected: 55
Upper East | community | Binduri | Yarigungu-Natinga | Happy World of Techn. Ltd. | 86 | 86 | meters connected: 92
Upper East | community | Binduri | Yarigungu-Asikonde | Happy World of Techn. Ltd. | 77 | 77 | meters connected: 124
Upper East | community | Binduri | Bakanga | Happy World of Techn. Ltd. | 73 | 73 | meters connected: 67
Upper East | community | Binduri | Azum-Sapeliga | King Nimod Electrical | 100 | 100 | meters connected: 179
Upper East | community | Binduri | Kpagogo #1 | King Nimod Electrical | 100 | 100 | meters connected: 162
Upper East | community | Binduri | Kpagogo #2 | King Nimod Electrical | 100 | 100 | meters connected: 126
Upper East | community | Binduri | Kpagogo North | King Nimod Electrical | 100 | 100 | meters connected: 315
Upper East | community | Pusiga | Teshnatinga/Terago | Happy World of Techn. Ltd. | 44 | 44 | meters connected: 70
Upper East | community | Pusiga | Saratinga-Teshnatinga | Happy World of Techn. Ltd. | 41 | 41 | meters connected: 100
Upper East | community | Pusiga | Gareke #1 - Teshnatinga | Happy World of Techn. Ltd. | 58 | 58 | meters connected: 155
Upper East | community | Pusiga | Gareke #2 - Teshnatinga | Happy World of Techn. Ltd. | 59 | 59 | meters connected: 200
Upper East | community | Pusiga | Silteega | Happy World of Techn. Ltd. | 32 | 32 | meters connected: 0
Upper East | community | Pusiga | Poanaba | Happy World of Techn. Ltd. | 38 | 50 | meters connected: 0
Upper East | community | Bawku Municipality | Zuuli Basic School | Y.B. General Electricals Ltd. | 33 | 85 | meters connected: 40
Upper East | community | Bawku Municipality | Kaabing/Zuli #2 | Y.B. General Electricals Ltd. | 33 | 90 | meters connected: 55
Upper East | community | Bawku Municipality | Gaag-Kuka | Y.B. General Electricals Ltd. | 56 | 88 | meters connected: 60
Upper East | community | Bawku Municipality | Winating | Y.B. General Electricals Ltd. | 56 | 89 | meters connected: 55
Upper East | community | Bawku Municipality | Lamb/Lambkong/Tempelug | Y.B. General Electricals Ltd. | 31 | 79 | meters connected: 30
Upper East | community | Bawku Municipality | Narun/Winadateng | Y.B. General Electricals Ltd. | 36 | 75 | meters connected: 45
Upper East | community | Bawku Municipality | Zom | Y.B. General Electricals Ltd. | 29 | 85 | meters connected: 40
Upper East | community | Bawku Municipality | Zaasi/Kpalug/Terug | Y.B. General Electricals Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku Muncipality | Gentiga #1 | Mohatu Electrical Ltd | 89 | 89 | meters connected: 50
Upper East | community | Bawku Muncipality | Gentiga #2 | Mohatu Electrical Ltd | 89 | 89 | meters connected: 50
Upper East | community | Bawku Muncipality | Pars Natinga/Azara-Saa | Kwofos Engineering Ltd. | 47 | 47 | meters connected: 50
Upper East | community | Bawku Muncipality | Gumakutari Chief's Palace | Kwofos Engineering Ltd. | 46 | 46 | meters connected: 59
Upper East | community | Bawku Muncipality | Baribari-Parabnating | Kwofos Engineering Ltd. | 89 | 89 | meters connected: 84
Upper East | community | Bawku West | Googo | Vims Electrical & Electronics Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Bawku West | Bugare Kpalsako | Vims Electrical & Electronics Ltd. | 27 | 27 | meters connected: 0
Upper East | community | Bawku West | Apoddabogo | Vims Electrical & Electronics Ltd. | 44 | 44 | meters connected: 0
Upper East | community | Bawku West | Zobako | Vims Electrical & Electronics Ltd. | 24 | 24 | meters connected: 0
Upper East | community | Builsa South | Kasiesa-Yemona | Daniel Abatara Electricals LTD | 43 | 43 | meters connected: 0
Upper East | community | Builsa South | Kasiesa-chief’s Palace | Daniel Abatara Electricals LTD | 33 | 33 | meters connected: 0
Upper East | community | Builsa South | Kasiesa-Yipaala | Daniel Abatara Electricals LTD | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Kasiesa-Sinsangsa | Daniel Abatara Electricals LTD | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Kanjarga-Logvogsa | Daniel Abatara Electricals LTD | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Doninga | Daniel Abatara Electricals LTD | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Zamsa | Daniel Abatara Electricals LTD | 19 | 19 | meters connected: 0
Upper East | community | Builsa South | Uwasa-Zuasa | Daniel Abatara Electricals LTD | 35 | 35 | meters connected: 0
Upper East | community | Builsa South | Fumbisi-Naadema | Adda Electrical Services Ltd. | 20 | 20 | meters connected: 0
Upper East | community | Builsa South | Wupiasa | Adda Electrical Services Ltd. | 20 | 20 | meters connected: 0
Upper East | community | Builsa South | Bachongsa-Nyanbisa | Adda Electrical Services Ltd. | 19 | 19 | meters connected: 0
Upper East | community | Builsa South | Gbedemazeng | Adda Electrical Services Ltd. | 11 | 11 | meters connected: 0
Upper East | community | Builsa South | Kazensa | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Zuasa | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Yadem | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Guluk | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Abaayeri | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Tuadem | Abeo Electrical Engineering Works Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Builsa South | Vandema | Hassanash Ventures | 134 | 134 | meters connected: 0
Upper East | community | Builsa South | Nandem/Damburinsa | Hassanash Ventures | 56 | 56 | meters connected: 0
Upper East | community | Builsa South | Kalaasa | Hassanash Ventures | 130 | 130 | meters connected: 0
Upper East | community | Builsa North | Kandem | Hassanash Ventures | 11 | 11 | meters connected: 0
Upper East | community | Builsa North | Nyansa | Hassanash Ventures | 28 | 28 | meters connected: 0
Upper East | community | Builsa North | Kaljisa #1 | Powertech Engineering Services Ltd. | 60 | 60 | meters connected: 84
Upper East | community | Builsa North | Longsa | Powertech Engineering Services Ltd. | 40 | 40 | meters connected: 0
Upper East | community | Builsa North | Kobedam | Powertech Engineering Services Ltd. | 28 | 28 | meters connected: 0
Upper East | community | Builsa North | Nawasa #1 | Powertech Engineering Services Ltd. | 36 | 36 | meters connected: 0
Upper East | community | Builsa North | Suwaransa | Powertech Engineering Services Ltd. | 64 | 64 | meters connected: 0
Upper East | community | Builsa North | Faransa | Powertech Engineering Services Ltd. | 58 | 58 | meters connected: 0
Upper East | community | Builsa North | Yimonsa | Powertech Engineering Services Ltd. | 71 | 71 | meters connected: 0
Upper East | community | Builsa North | Chiok (Atidiok) | Powertech Engineering Services Ltd. | 43 | 43 | meters connected: 0
Upper East | community | Builsa North | Nanjuaping | Powertech Engineering Services Ltd. | 36 | 36 | meters connected: 0
Upper East | community | Bongo | Akamo | ILA Engineering Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Yaka | ILA Engineering Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Akundoo chief's Palace | ILA Engineering Ltd | 22 | 22 | meters connected: 0
Upper East | community | Bongo | Akundoo-kiibo/Apeliga | ILA Engineering Ltd | 16 | 16 | meters connected: 0
Upper East | community | Bongo | Asakule | ILA Engineering Ltd | 2 | 2 | meters connected: 0
Upper East | community | Bongo | Yekine-Dabuure | Richmanda Eng. Ltd | 89 | 89 | meters connected: 14
Upper East | community | Binduri | Sakpari Central | Ike Electrical Co. Ltd | 32 | 32 | meters connected: 147
Upper East | community | Binduri | Sakpari-Kumpalgoga | Ike Electrical Co. Ltd | 77 | 77 | meters connected: 84
Upper East | community | Binduri | Sakpari-Bakango | Ike Electrical Co. Ltd | 74 | 74 | meters connected: 73
Upper East | community | Binduri | Sakpari-Poayamire | Ike Electrical Co. Ltd | 44 | 44 | meters connected: 367
Upper East | community | Binduri | Morgo | Mohatu Electrical Ltd | 62 | 62 | meters connected: 0
Upper East | community | Pusiga | Kultamise | Mohatu Electrical Ltd | 68 | 68 | meters connected: 0
Upper East | community | Pusiga | Kamadugu/Sunkelma | Mohatu Electrical Ltd | 61 | 61 | meters connected: 0
Upper East | community | Pusiga | Koose Basic School | Mohatu Electrical Ltd | 60 | 60 | meters connected: 0
Upper East | community | Kasena Nankana East | Saboro | Mohatu Electrical Ltd | 44 | 44 | meters connected: 0
Upper East | community | Kasena Nankana West | Benbisi | Mohatu Electrical Ltd | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Kayelo | Mohatu Electrical Ltd | 22 | 22 | meters connected: 0
Upper East | community | Kasena Nankana West | Adungu | Mohatu Electrical Ltd | 22 | 22 | meters connected: 0
Upper East | community | Binduri | Zeego (Zaago)/Bankago Ext | Tirago Enterprise Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Binduri | Atoba-Mognori | Tirago Enterprise Ltd. | 0 | 0 | meters connected: 0
Upper East | community | Binduri | Atoba-Avoase | Tirago Enterprise Ltd. | 0 | 0 | meters connected: 0
Upper East | community | Binduri | Tansia-Bugrin/Zeego/ Kolnatinga | Tirago Enterprise Ltd. | 84 | 84 | meters connected: 110
Upper East | community | Binduri | Atoba Main Town | Tirago Enterprise Ltd. | 33 | 33 | meters connected: 0
Upper East | community | Binduri | Kaadi-Kudugu | Tirago Enterprise Ltd. | 0 | 55 | meters connected: 0
Upper East | community | Binduri | Agomisin | Tirago Enterprise Ltd. | 0 | 60 | meters connected: 0
Upper East | community | Binduri | Wabzug | Tirago Enterprise Ltd. | 0 | 55 | meters connected: 0
Upper East | community | Binduri | Dabuugu/Kukparigu | Elios Company Ltd. | 33 | 33 | meters connected: 84
Upper East | community | Binduri | Dulnatinga/Agbelgimvoos | Elios Company Ltd. | 67 | 67 | meters connected: 79
Upper East | community | Binduri | Boko #2 | Elios Company Ltd. | 179 | 179 | meters connected: 159
Upper East | community | Binduri | Bazua Newtown (ext)/Biaka | Elios Company Ltd. | 94 | 94 | meters connected: 180
Upper East | community | Binduri | Sakparna Tinga | Elios Company Ltd. | 100 | 100 | meters connected: 89
Upper East | community | Binduri | Tendaatengen | J - Karimus Company Ltd. | 22 | 22 | meters connected: 0
Upper East | community | Binduri | Gotesaliga | J - Karimus Company Ltd. | 69 | 90 | meters connected: 123
Upper East | community | Binduri | Asintapelug | J - Karimus Company Ltd. | 22 | 89 | meters connected: 0
Upper East | community | Kasena Nankana | Punelingo | Jetumah Electrical Works Ltd. | 21 | 21 | meters connected: 0
Upper East | community | Kasena Nankana | Gunwoko/Basengo-More | Jetumah Electrical Works Ltd. | 19 | 19 | meters connected: 0
Upper East | community | Kasena Nankana | Tundoogo/Tingino | Jetumah Electrical Works Ltd. | 22 | 22 | meters connected: 115
Upper East | community | Kasena Nankana | Gunwoko No. 2/Bigkum | Jetumah Electrical Works Ltd. | 11 | 11 | meters connected: 157
Upper East | community | Kasena Nankana | Pogitam (Ext) | Jetumah Electrical Works Ltd. | 22 | 22 | meters connected: 105
Upper East | community | Kasena Nankana | Tangasia | Jetumah Electrical Works Ltd. | 37 | 37 | meters connected: 79
Upper East | community | Kasena Nankana | Wugingo/Basengo | Jetumah Electrical Works Ltd. | 18 | 18 | meters connected: 37
Upper East | community | Bongo | Kadali | KASN Engineering and Consult Ltd | 83 | 83 | meters connected: 252
Upper East | community | Bongo | Tindongo | KASN Engineering and Consult Ltd | 33 | 33 | meters connected: 0
Upper East | community | Bongo | Goo/Widongo | KASN Engineering and Consult Ltd | 84 | 84 | meters connected: 100
Upper East | community | Bongo | Awaa Atiabiisi | KASN Engineering and Consult Ltd | 33 | 33 | meters connected: 0
Upper East | community | Bongo | Awaa Tarongo Ext | KASN Engineering and Consult Ltd | 55 | 55 | meters connected: 0
Upper East | community | Bongo | Abelumzanga Ext | KASN Engineering and Consult Ltd | 33 | 33 | meters connected: 0
Upper East | community | Bongo | Awale Namoo | KASN Engineering and Consult Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Sikabiisi Nayari | KASN Engineering and Consult Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Sikabiisi Akondone | KASN Engineering and Consult Ltd | 12 | 12 | meters connected: 0
Upper East | community | Bongo | Sikabiisi Abokobisi | KASN Engineering and Consult Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Lungu Dangoogo | KASN Engineering and Consult Ltd | 0 | 0 | meters connected: 0
Upper East | community | Bongo | Ayourpia | KASN Engineering and Consult Ltd | 23 | 90 | meters connected: 70
Upper East | community | Bongo | Beo Lembisi | KASN Engineering and Consult Ltd | 0 | 70 | meters connected: 65
Upper East | community | Bongo | Beo Mooshidaboro | KASN Engineering and Consult Ltd | 36 | 89 | meters connected: 100
Upper East | community | Talensi/Pusiga | GAARE BONG | Happy World of Technology Ltd. | 56 | 56 | meters connected: 304
Upper East | community | Talensi/Pusiga | GAARE LOOTE/ZOORE | Happy World of Technology Ltd. | 44 | 44 | meters connected: 100
Upper East | community | Talensi/Pusiga | GAARE MARKET | Happy World of Technology Ltd. | 83 | 83 | meters connected: 102
Upper East | community | Talensi/Pusiga | GBANI DATOK/TASOYERI | Happy World of Techn. Ltd. | 44 | 44 | meters connected: 50
Upper East | community | Talensi/Pusiga | GBANI DANYIRE | Happy World of Techn. Ltd. | 78 | 78 | meters connected: 60
Upper East | community | Talensi/Pusiga | GBEWAA NO.2/SIGNOGO | Happy World of Techn. Ltd. | 100 | 100 | meters connected: 203
Upper East | community | Talensi/Pusiga | GBEWAA NO.1 | Happy World of Techn. Ltd. | 100 | 100 | meters connected: 153
Upper East | community | Garu | Zare-Zua | Powertech Engineering Ltd | 0 | 50 | meters connected: 0
Upper East | community | Garu | Duubulugu | Powertech Engineering Ltd | 0 | 50 | meters connected: 0
Upper East | community | Garu | Kpatia Poraguur | Powertech Engineering Ltd | 0 | 45 | meters connected: 0
Upper East | community | Garu | Poraguur | Powertech Engineering Ltd | 0 | 30 | meters connected: 0
Upper East | community | Garu | Kugri Kpalsiako | Powertech Engineering Ltd | 0 | 0 | meters connected: 0
Upper East | community | Garu | Siirigu | Sounsong Company Ltd | 60 | 60 | meters connected: 0
Upper East | community | Garu | Menkaesir | Sounsong Company Ltd | 107 | 107 | meters connected: 0
Upper East | community | Garu | Namore | Sounsong Company Ltd | 54 | 54 | meters connected: 0
Upper East | community | Garu | Tambaalugu | Sounsong Company Ltd | 49 | 49 | meters connected: 0
Upper East | community | Garu | Bugwia Seltego | Sounsong Company Ltd | 59 | 59 | meters connected: 0
Upper East | community | Garu | Waadugu | Sounsong Company Ltd | 74 | 74 | meters connected: 0
Upper East | community | Kasena Nankana East | Terkura -Pungu | 3 Coolman Company Limited | 61 | 61 | meters connected: 0
Upper East | community | Kasena Nankana East | Wuru | 3 Coolman Company Limited | 69 | 69 | meters connected: 0
Upper East | community | Kasena Nankana East | Kolna/Biu Ext | 3 Coolman Company Limited | 14 | 14 | meters connected: 0
Upper East | community | Kasena Nankana East | Kolna Biu | 3 Coolman Company Limited | 17 | 17 | meters connected: 0
Upper East | community | Kasena Nankana East | Tampol A Ext | 3 Coolman Company Limited | 14 | 14 | meters connected: 0
Upper East | community | Kasena Nankana East | Kologo Natire | 3 Coolman Company Limited | 11 | 11 | meters connected: 0
Upper East | community | Kasena Nankana East | Akuka | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Azaazi (Atosala | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Mayoro - Wanchoko (Ext | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Gumango Basic Sch | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Lower Gumango | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Mayoro Wanjagina | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Bania | A.A WARNCHAN COMPANY LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Kalosoko | Twins Touch Electricals LTD | 0 | 0 | meters connected: 2
Upper East | community | Kasena Nankana East | Zuo Timpelugu | Twins Touch Electricals LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Mainzuo Ext | Twins Touch Electricals LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Naaga No.1 | Twins Touch Electricals LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Naaga No.2 | Twins Touch Electricals LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Kungogo | Twins Touch Electricals LTD | 0 | 0 | meters connected: 0
Upper East | community | Kasena Nankana East | Punyoro Kababia | Twins Touch Electricals LTD | 10 | 10 | meters connected: 0
Bono East | community | Pru | Budan | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Congo | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Brahabebome | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Bomboben | My Redeemer |  | 8 | 8%
Bono East | community | Pru | Wobrase | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Wodomeabra | My Redeemer |  | 10 | 10%
Bono East | community | Pru | New Ajona | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Jato Zongo Jumpa Akura | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Jato Zongo Area | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Zongo No.3 Mangoase | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Israel | My Redeemer |  | 40 | 91.40%
Bono East | community | Pru | Prang Domeabra | My Redeemer |  | 89 | 89%
Bono East | community | Pru | Kachawura Newsite | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Jumpe | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | New Patuda | My Redeemer |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Zongo | Kingsco Electricals & Civil Eng. Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Lowcost Area | Kingsco Electricals & Civil Eng. Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Amanfrom | Kingsco Electricals & Civil Eng. Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Adom Fiano Road | Kingsco Electricals & Civil Eng. Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Pru | Zamara North | Kingsco Electricals & Civil Eng. Ltd. () |  | 10 | 10%
Bono East | community | Pru | Zamara South | Kingsco Electricals & Civil Eng. Ltd. () |  | 10 | 10%
Bono East | community | Pru | Zamara East | Kingsco Electricals & Civil Eng. Ltd. () |  | 10 | 10%
Bono East | community | Pru | Zamara West | Kingsco Electricals & Civil Eng. Ltd. () |  | 10 | 10%
Bono East | community | Pru | Yawpare | Kingsco Electricals & Civil Eng. Ltd. () |  | 20 | 20%
Bono East | community | Pru | Ajaraja Beposo | Kingsco Electricals & Civil Eng. Ltd. () |  | 90 | 90%
Bono East | community | Pru | Nakpei Beposo | Kingsco Electricals & Civil Eng. Ltd. () |  | 20 | 98.20%
Bono East | community | Sene West | Africa/Zabrama | Unique Cosby Enterprise () |  | 10 | 10% Yet to start scope
Bono East | community | Sene West | Davakope | Unique Cosby Enterprise () |  | 10 | 10%
Bono East | community | Sene West | Dunkwape | Unique Cosby Enterprise () |  | 10 | 10% Yet to start scope
Bono East | community | Sene West | Burkina | Unique Cosby Enterprise () |  | 10 | 10% Yet to start scope
Bono East | community | Sene West | Amangoase | Stevgarbs () |  | 60 | 29.60%
Bono East | community | Sene West | Konkose | Stevgarbs () |  | 50 | 12.50%
Bono East | community | Sene West | Chokose | Stevgarbs () |  | 3 | 3%
Bono East | community | Sene West | Ningo | Stevgarbs () |  | 40 | 26.40%
Bono East | community | Sene West | Todaykope | Stevgarbs () |  | 41 | 41%
Bono East | community | Sene West | Asempaneye | Stevgarbs () |  | 30 | 44.30%
Bono East | community | Sene East | Tabus | Stevgarbs () |  | 2 | 4.2%
Bono East | community | Sene East | Gakope | Stevgarbs () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Ohiasomawo | Stevgarbs () |  | 10 | 10%
Bono East | community | Sene East | CFAO Quarters | Stevgarbs () |  | 10 | 10%
Bono East | community | Sene East | Nyakonakope | Stevgarbs () |  | 10 | 10%
Bono East | community | Sene East | Agyata | Stevgarbs () |  | 50 | 6.50%
Bono East | community | Sene East | Gbili | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Bilaba/Gbeti | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Abuoso/Chafi | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Issifu-Yaw Mensah | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Wajul | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Asuoso Mud | Franves () |  | 10 | 10%
Bono East | community | Sene East | Sumsunpe/Aliwoe | Franves () |  | 10 | 10%
Bono East | community | Sene East | Ningo Akpalu | Franves () |  | 10 | 10%
Bono East | community | Sene East | Oldman | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Sene East | Beposo | Franves () |  | 10 | 10%
Bono East | community | Kintampo North | Mo Line | Korigu () |  | 89 | 89%
Bono East | community | Kintampo North | Gruma Line | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Sawaba Down | Korigu () |  | 89 | 89%
Bono East | community | Kintampo North | Nwoase | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Kojovi Ext | Korigu () |  | 85 | 85%
Bono East | community | Kintampo North | Malik Ext | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Jidi Ext | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | New Town Ext | Korigu () |  | 85 | 85%
Bono East | community | Kintampo North | Airport Ext | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Asukoko | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Awurata | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Kongo | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Larempe | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Nyamebekyere | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Nkeyinedea | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Yabraso | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Sarachigona | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Tanokrom | Korigu () |  | 20 | 23.20%
Bono East | community | Kintampo North | Telefufuo | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Wala Akura | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Baabu Akura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Sempoa Akura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Tano Akura | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Awaa Akura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Sissala Line Ext. | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Attakrom Asugya | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Adekese | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Azuma Akura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Atakrom | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Kaaka | Korigu () |  | 70 | 70%
Bono East | community | Kintampo North | Abena Num | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Dagomba Alhassan | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Kpukpabine | Korigu () |  | 70 | 70%
Bono East | community | Kintampo North | Bunkwata | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Berecha krom | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Naaba | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Yerepemso | Korigu () |  | 90 | 90%
Bono East | community | Kintampo North | Bukariakura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Dakori | Korigu () |  | 70 | 70%
Bono East | community | Kintampo North | Adage | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Alampram | Korigu () |  | 70 | 33.70%
Bono East | community | Kintampo North | Drepo | Korigu () |  | 70 | 70%
Bono East | community | Kintampo North | Fosu Akura | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Domeabra | Korigu () |  | 70 | 17.70%
Bono East | community | Kintampo North | Mamprisi Line Ext. | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Belompe Ext. | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Kadelso Ext. | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Bemkrom Ext. | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Timber Market | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Just Love Area | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Substation And Magazine | Korigu () |  | 40 | 40%
Bono East | community | Kintampo North | Kwajove No.2 | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Kobeda | Korigu () |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo North | Jidi Town | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Central College | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Gruma Down | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Assemblies of God | Korigu () |  | 10 | 10%
Bono East | community | Kintampo North | Targona | Korigu () |  | 10 | 10%
Bono East | community | Atebubu Amantin | Islamic | Unique Titan Company Ltd. () |  | 70 | 70%
Bono East | community | Atebubu Amantin | New Duabone | Unique Titan Company Ltd. () |  | 10 | 41.10%
Bono East | community | Atebubu Amantin | Nyomase | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Beposo | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Agric Station | Unique Titan Company Ltd. () |  | 30 | 24.30%
Bono East | community | Atebubu Amantin | Jumpa | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Kumfia | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Fakwasi | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Dobidi | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Amantin Dogu | Unique Titan Company Ltd. () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Sabon Zongo | Unique Titan Company Ltd. () |  | 50 | 50.50%
Bono East | community | Atebubu Amantin | Mem | Kamnaa () |  | 2 | 6.2%
Bono East | community | Atebubu Amantin | Watro | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Old Kronkron | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Kitikrom | Kamnaa () |  | 8 | 3.8%
Bono East | community | Atebubu Amantin | Seneso | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Kokofu | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Garadima | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Duabone | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Yaw Tuffour | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Bresuano | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Asempaneye | Kamnaa () |  | 0 | 0% Yet to start scope
Bono East | community | Wenchi Municipal/ Nkoranza North | Adoe | Pabseimah () |  | 60 | 15.60%
Bono East | community | Wenchi Municipal/ Nkoranza North | Boana | Pabseimah () |  | 80 | 22.80%
Bono East | community | Wenchi Municipal/ Nkoranza North | Bomua | Pabseimah () |  | 90 | 90%
Bono East | community | Wenchi Municipal/ Nkoranza North | Tom | Pabseimah () |  | 30 | 20.30%
Bono East | community | Wenchi Municipal/ Nkoranza North | Busunya West | Pabseimah () |  | 90 | 90%
Bono East | community | Wenchi Municipal/ Nkoranza North | Busunya East | Pabseimah () |  | 17 | 17%
Bono East | community | Wenchi Municipal/ Nkoranza North | Dromankese | Pabseimah () |  | 89 | 89%
Bono East | community | Wenchi Municipal/ Nkoranza North | Dromankese No.2 | Pabseimah () |  | 89 | 89%
Bono East | community | Wenchi Municipal/ Nkoranza North | Dromankoma | Pabseimah () |  | 89 | 89%
Bono East | community | Nkoranza North | Odumase | Franves () |  | 60 | 8.60%
Bono East | community | Nkoranza North | Fiema | Franves () |  | 20 | 20%
Bono East | community | Nkoranza North | Akonkonti | Franves () |  | 10 | 10%
Bono East | community | Nkoranza North | Bonte | Franves () |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Yefri | Franves () |  | 10 | 10%
Bono East | community | Nkoranza North | Asekye | Franves () |  | 20 | 18.20%
Bono East | community | Nkoranza North | Senya | Franves () |  | 20 | 20%
Bono East | community | Nkoranza North | Bomini | Franves () |  | 40 | 1.40%
Bono East | community | Nkoranza North | Domeabra | Franves () |  | 60 | 4.60%
Bono East | community | Nkoranza North | Akrudwa | Franves () |  | 20 | 8.20%
Bono East | community | Nkoranza North | Bodom | Franves () |  | 20 | 7.20%
Bono East | community | Nkoranza North | Pienyina | Franves () |  | 90 | 10.90%
Bono East | community | Nkoranza North | Mangoase Junction | Franves () |  | 70 | 4.70%
Bono East | community | Techiman South | Dentehkrom | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 79 | 79%
Bono East | community | Techiman South | Attahkrom | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 79 | 79%
Bono East | community | Techiman South | Yaw Afere Krom | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 79 | 79%
Bono East | community | Techiman South | Moframfadwen | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 10 | 10%
Bono East | community | Techiman South | Jatokrom | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 10 | 10%
Bono East | community | Techiman South | Yerepemso | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 10 | 10%
Bono East | community | Techiman South | Anankasu | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 4 | 4.4%
Bono East | community | Techiman South | Esereso no. 1 | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 2 | 3.2%
Bono East | community | Techiman South | Esereso no. 2 | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 7 | 6.7%
Bono East | community | Techiman South | Esereso no. 3 | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 5 | 5.5%
Bono East | community | Techiman South | Esereso no. 4 | Hon. Martin Adjei-Mensah Korsah Contractor: Check Point |  | 4 | 2.4%
Bono East | community | Techiman | RCC Office/Bungalows | Hon. Regional Minister |  | 0 | 0% Yet to start scope
Bono East | community | Techiman North | Tanokrom | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 90 | 90%
Bono East | community | Techiman North | Buom | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 0 | 0% Yet to start scope
Bono East | community | Techiman North | Asueye Domeabra | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 37 | 37%
Bono East | community | Techiman North | Gyama Boasogya | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 40 | 40%
Bono East | community | Techiman North | Tuobodom Zongo | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 2 | 5.2%
Bono East | community | Techiman North | Tano Avenue | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 80 | 80%
Bono East | community | Techiman North | Magazine Newsite | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 6 | 12.6%
Bono East | community | Techiman North | Tenabea | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 6 | 1.6%
Bono East | community | Techiman North | Ayeasu | Hon. Elizabeth Adjare Contractor: Pabseimah |  | 10 | 10%
Bono East | community | Nkoranza South | Nkoranza Town | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 7 | 3.7%
Bono East | community | Nkoranza South | Donkro Nkwanta | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 7 | 6.7%
Bono East | community | Nkoranza South | Kyeredese | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 8 | 15.8%
Bono East | community | Nkoranza South | Salamkrom | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 5 | 3.5%
Bono East | community | Nkoranza South | Asunkwa | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 8 | 4.8%
Bono East | community | Nkoranza South | Akumsa Domase | Hon. Emmanuel Agyekum Contractor: Twumas Ltd. |  | 3 | 3%
Bono East | community | Nkoranza North | Bono Manso | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Kranka | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Badukwan Farms | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Abrekyirekrom | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Asuoti | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Nkoranza North | Anafour | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Adiembra | Hon. Alexander Gyan |  | 10 | 10%
Bono East | community | Kintampo South | Nana Yaakrom | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Yawmoakrom | Hon. Alexander Gyan |  | 10 | 10%
Bono East | community | Kintampo South | Boadi | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Nyamebekyere | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Boblobo | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Asaase | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Kwabea | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Kintampo South | Akura | Hon. Alexander Gyan |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Bompa | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Yaw Tuffour II | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Bolga Village | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Bachaaso | Dce |  | 0 | 0% Yet to start scope
Bono East | community | Atebubu Amantin | Awuraso | Dce |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi Fomena | Nintini | Bukjee () |  | 90 | 90% complete
Ashanti | community | Adansi Fomena | Apunpunso | Bukjee () |  | 3 | 53.3% complete
Ashanti | community | Adansi Fomena | Anyinabrem | Isaac Fordjour () |  | 90 | 90% complete
Ashanti | community | Adansi Fomena | Bura | Isaac Fordjour () |  | 90 | 90% complete
Ashanti | community | Adansi Fomena | Bena | Isaac Fordjour () |  | 90 | 90% complete
Ashanti | community | Adansi Fomena | Kwakukrom | Isaac Fordjour () |  | 90 | 90% complete
Ashanti | community | Adansi Fomena | Denkyie | Isaac Fordjour () |  | 90 | 90% complete
Ashanti | community | Adansi North | Fomena Ahmadiya SHS | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Nursing & Midwifery | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Dompoase SHS | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | New Amensia | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Kusa Newsite | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Kyekyewere Newsite | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Hemang Poultry Newsite | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Dadwen Newsite | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Akrokeri Training College | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Asare Bediako SHS | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Broni Kurom Senit | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Sampakrom | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Abadwam | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Aktakyieso Community Mining | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Sodua | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Akrofuom | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | New Nyamebekyere | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Wiawso Community Mining | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Adumenu Community Mining Site | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Kusa Scrap | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi North | Bonriase 1D1F | Bukjee () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Yawowusukrom | Ans () |  | 4 | 96.4% complete
Ashanti | community | Adansi South | Kramokrom | Ans () |  | 30 | 30% complete
Ashanti | community | Adansi South | Kwakye Krom | Ans () |  | 3 | 21.3% complete
Ashanti | community | Adansi South | Nyamebekyere | Ans () |  | 6 | 92.6% complete
Ashanti | community | Adansi South | Adukroba | Ans () |  | 90 | 90% complete
Ashanti | community | Adansi South | Bethlehem | Ans () |  | 90 | 90% complete
Ashanti | community | Adansi South | Adomanyame | Ans () |  | 90 | 90% complete
Ashanti | community | Adansi South | Beseasi | Ans () |  | 90 | 90% complete
Ashanti | community | Adansi South | Boakyekrom | Ans () |  | 0 | 89.0% complete
Ashanti | community | Adansi South | Nhyiaso 1 | Ans () |  | 0 | 20.0% complete
Ashanti | community | Adansi South | Nhyiaso 2 | Ans () |  | 7 | 1.7%
Ashanti | community | Adansi South | Nnyameso | Ans () |  | 0 | 70.0%
Ashanti | community | Adansi South | Gyimi Camp | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Bekampa | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South/ Sekyere Central | Yadome | Agenbec () |  | 7 | 45.7%
Ashanti | community | Adansi South/ Sekyere Central | Bertenase | Agenbec () |  | 2 | 38.2%
Ashanti | community | Adansi South/ Sekyere Central | Adubanaso | Agenbec () |  | 2 | 72.2%
Ashanti | community | Adansi South/ Sekyere Central | Mensahkrom | Agenbec () |  | 7 | 89.7%
Ashanti | community | Adansi South/ Sekyere Central | Asaasebomebosia | Agenbec () |  | 8 | 75.8%
Ashanti | community | Adansi South/ Sekyere Central | Akaasu No.1 | Agenbec () |  | 9 | 77.9%
Ashanti | community | Adansi South/ Sekyere Central | Akaasu No.2 | Agenbec () |  | 8 | 86.8%
Ashanti | community | Adansi South/ Sekyere Central | Dampayam | Agenbec () |  | 2 | 29.2%
Ashanti | community | Adansi South/ Sekyere Central | Comfortable Nkwanta | Agenbec () |  | 40 | 40%
Ashanti | community | Adansi South/ Sekyere Central | Ofrikrom | Agenbec () |  | 1 | 31.1%
Ashanti | community | Adansi South/ Sekyere Central | Agengensu | Agenbec () |  | 7 | 33.7%
Ashanti | community | Adansi South/ Sekyere Central | Bredi | Agenbec () |  | 40 | 40%
Ashanti | community | Adansi South/ Sekyere Central | Fawoman | Agenbec () |  | 4 | 24.4%
Ashanti | community | Afigya Kwabre | Apagya | E.K. Senkyere () |  | 90 | 90%
Ashanti | community | Afigya Kwabre | Dumanafo | E.K. Senkyere () |  | 90 | 90%
Ashanti | community | Afigya Kwabre | Adubinso Bea | A. A. Warncharn Ltd. |  | 89 | 89%
Ashanti | community | Kwabre East | Krobo | Tanja () |  | 10 | 10%
Ashanti | community | Kwabre East | Pasoro | Tanja () |  | 0 | 0% Yet to start scope
Ashanti | community | Kwabre East | Adantem Manchia Newsite | Antoa-B () |  | 2 | 19.2%
Ashanti | community | Kwabre East | Adiembra New Site | Pomark () |  | 9 | 45.9%
Ashanti | community | Kwabre East | Henoo | Pomark () |  | 4 | 65.4%
Ashanti | community | Kwabre East | Djako | Pomark () |  | 28 | 28%
Ashanti | community | Kwabre East | Ntonso | Viniado () |  | 5 | 23.5%
Ashanti | community | Kwabre East | Ntonso Afiakrom | Viniado () |  | 5 | 37.5%
Ashanti | community | Kwabre East | Akotosu | Osmed Plus () |  | 90 | 90%
Ashanti | community | Kwabre East | Adjei Mpra | Osmed Plus () |  | 90 | 90%
Ashanti | community | Kwabre East | Antoa Newsite | Lastman () |  | 3 | 1.3%
Ashanti | community | Kwabre East | Ntrodanim | Twins Touch |  | 2 | 34.2%
Ashanti | community | Bosomtwi | Jachie Newsite | Matwen Awurade () |  | 0 | 0% Yet to start scope
Ashanti | community | Bosomtwi | Akwaduom | Matwen Awurade () |  | 0 | 0% Yet to start scope
Ashanti | community | Bosomtwi | Aboaso Newsite | Matwen Awurade () |  | 0 | 0% Yet to start scope
Ashanti | community | Bosomtwi | Sewia Newsite | Matwen Awurade () |  | 0 | 0% Yet to start scope
Ashanti | community | Bosomtwi | Atobiase Newsite | Matwen Awurade () |  | 0 | 0% Yet to start scope
Ashanti | community | New Edubiase | Amudurase | Global New Beginning () |  | 85 | 85%
Ashanti | community | New Edubiase | Adansi Paaso | Global New Beginning () |  | 1 | 49.1%
Ashanti | community | New Edubiase | Ataasi-Nkwanta | Global New Beginning () |  | 83 | 83%
Ashanti | community | Atwima Nwabiagya North | Sene | Global New Beginning () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Saase | Global New Beginning () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | DKC | Global New Beginning () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Bukankyi | Global New Beginning () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Agyeikrom | Global New Beginning () |  | 0 | 0% Yet to start scope
Ashanti | community | Effiduase & Atwima Kwahoma | Nkwabeng | Osmed Plus () |  | 70 | 70%
Ashanti | community | Effiduase & Atwima Kwahoma | Pepease Ankaase | Osmed Plus () |  | 7 | 43.7%
Ashanti | community | Effiduase & Atwima Kwahoma | Dadieso Mexico | Osmed Plus () |  | 61 | 61%
Ashanti | community | Effiduase & Atwima Kwahoma | Dadieso Agric | Osmed Plus () |  | 47 | 47%
Ashanti | community | Effiduase & Atwima Kwahoma | Adanso Agya Zone | Osmed Plus () |  | 0 | 0% Yet to start scope
Ashanti | community | Effiduase & Atwima Kwahoma | Adanso Agya Hwe | Osmed Plus () |  | 60 | 60%
Ashanti | community | Bekwai Municipal | Nkwata | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Dedesua | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Aduaden | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Abono | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Obbo | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Nkowie | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Old Brodekwanho | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Konkoma | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Brodekwanho | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Asisriwa | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Bekwai Municipal | Adwafo | Amakye () |  | 0 | 0% Yet to start scope
Ashanti | community | Kma/ Offinso South/ Amansie West | Amankwatia Town | Patco () |  | 6 | 20.6%
Ashanti | community | Kma/ Offinso South/ Amansie West | Apotosu Town | Patco () |  | 11 | 11%
Ashanti | community | Kma/ Offinso South/ Amansie West | Amaning Town | Patco () |  | 6 | 35.6%
Ashanti | community | Kma/ Offinso South/ Amansie West | Boahenkwaa Town | Patco () |  | 2 | 2%
Ashanti | community | Kma/ Offinso South/ Amansie West | Ayaasu Town | Patco () |  | 3 | 39.3%
Ashanti | community | Kma/ Offinso South/ Amansie West | Baaniekrom | Patco () |  | 6 | 41.6%
Ashanti | community | Kma/ Offinso South/ Amansie West | Wawase Town | Patco () |  | 8 | 7.8%
Ashanti | community | Kma/ Offinso South/ Amansie West | Namong Wenchi | Patco () |  | 84 | 84%
Ashanti | community | Ahafo Ano North/ Adansi South | Camp 1 | Pathayford Ltd. |  | 8 | 94.8%
Ashanti | community | Ahafo Ano North/ Adansi South | Tepa Beposo | Pathayford Ltd. |  | 100 | 100%
Ashanti | community | Ahafo Ano North/ Adansi South | Tepa Ward | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Tepa Filermu | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | King Jesus-Tepa | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Boadesua | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Tepa Rexco | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Kyensedaho | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Amankwa | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Ahafo Ano North/ Adansi South | Annorkrom | Pathayford Ltd. |  | 90 | 90%
Ashanti | community | Atwima Mponua | Kyekyewere | Possible () |  | 9 | 36.9%
Ashanti | community | Atwima Mponua | Nkyensrekrom | Possible () |  | 35 | 35%
Ashanti | community | Atwima Mponua | Kasotie | Possible () |  | 90 | 90%
Ashanti | community | Atwima Mponua | Toase | Possible () |  | 6 | 18.6%
Ashanti | community | Atwima Mponua | Dabang | Possible () |  | 7 | 39.7%
Ashanti | community | Atwima Mponua | Yabee | Possible () |  | 5 | 24.5%
Ashanti | community | Atwima Mponua | Mansasu | Possible () |  | 7 | 56.7%
Ashanti | community | Atwima Mponua | Kwamedua | Possible () |  | 5 | 38.5%
Ashanti | community | Atwima Mponua | Bedabour | Possible () |  | 6 | 74.6%
Ashanti | community | Atwima Mponua | Beposo | Possible () |  | 4 | 67.4%
Ashanti | community | Atwima Mponua | Abompe | Possible () |  | 3 | 68.3%
Ashanti | community | Atwima Mponua | Yawbour | Eagle Power () |  | 7 | 53.7%
Ashanti | community | Atwima Mponua | Kyenkyenta | Eagle Power () |  | 6 | 54.6%
Ashanti | community | Atwima Mponua | Asuaya | Eagle Power () |  | 40 | 40%
Ashanti | community | Atwima Mponua | Akantensu | Eagle Power () |  | 8 | 81.8%
Ashanti | community | Atwima Mponua | Wansamire | Eagle Power () |  | 90 | 90%
Ashanti | community | Atwima Mponua | Awesesu | Eagle Power () |  | 9 | 47.9%
Ashanti | community | Amansie Central | Abubuasini | New Life () |  | 85 | 85%
Ashanti | community | Amansie Central | Wromanso | New Life () |  | 70 | 70%
Ashanti | community | Amansie Central | Subima | New Life () |  | 90 | 90%
Ashanti | community | Amansie Central | Gyaaman | New Life () |  | 90 | 90%
Ashanti | community | Amansie Central | Skuumu | New Life () |  | 90 | 90%
Ashanti | community | Amansie Central | Bepotenten | New Life () |  | 90 | 90%
Ashanti | community | Amansie Central | Penipa | New Life () |  | 70 | 70%
Ashanti | community | Amansie Central | Aboagyekrom | New Life () |  | 70 | 70%
Ashanti | community | Amansie Central | Awawom | New Life () |  | 4 | 16.4%
Ashanti | community | Amansie Central | Mmodobamu | New Life () |  | 89 | 89%
Ashanti | community | Amansie Central | Esaase | New Life () |  | 84 | 84%
Ashanti | community | Amansie Central | Bronikrom | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Konkori | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Trede | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Ntwaso & Aduntia | Puretec () |  | 2 | 31.2%
Ashanti | community | Amansie Central | Mile 18 | Puretec () |  | 9 | 9.9%
Ashanti | community | Amansie Central | Adwease No. 1&2 | Puretec () |  | 3 | 8.3%
Ashanti | community | Amansie Central | Sudantoa | Puretec () |  | 5 | 15.5%
Ashanti | community | Amansie Central | Odumto | Puretec () |  | 9 | 12.9%
Ashanti | community | Amansie Central | Manfo | Puretec () |  | 9 | 13.9%
Ashanti | community | Amansie Central | Sabe 1 | Puretec () |  | 6 | 9.6%
Ashanti | community | Amansie Central | Sabe 2 | Puretec () |  | 14 | 14%
Ashanti | community | Amansie Central | Ewiase | Puretec () |  | 10 | 10%
Ashanti | community | Amansie Central | Edunso | Puretec () |  | 90 | 90%
Ashanti | community | Amansie Central | Apeboso | Puretec () |  | 2 | 30.2%
Ashanti | community | Amansie Central | Nwease | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Akwankwaso | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Dotom | Puretec () |  | 90 | 90%
Ashanti | community | Amansie Central | Obeng ne Obeng | Puretec () |  | 90 | 90%
Ashanti | community | Amansie Central | Asuadae | Puretec () |  | 1 | 4.1%
Ashanti | community | Amansie Central | Mpenkyireni | Puretec () |  | 8 | 7.8%
Ashanti | community | Amansie Central | Nteben | Puretec () |  | 90 | 90%
Ashanti | community | Amansie Central | Bentenseni | Puretec () |  | 7 | 15.7%
Ashanti | community | Ahafo Ano South | Asuokor 1&2 | Possible () |  | 85 | 85%
Ashanti | community | Ahafo Ano South | Manhyia/ Achiase | Possible () |  | 1 | 97.1%
Ashanti | community | Ahafo Ano South | Adiembra | Possible () |  | 2 | 84.2%
Ashanti | community | Ahafo Ano South | Dotiem | Possible () |  | 90 | 90%
Ashanti | community | Ahafo Ano South | Ango | Possible () |  | 90 | 90%
Ashanti | community | Ahafo Ano South | Ofirikrom | Possible () |  | 97 | 97%
Ashanti | community | Ahafo Ano South | Kwaso-Deduako | Puretec () |  | 90 | 90%
Ashanti | community | Ahafo Ano South | Nyameadom | Prestige () |  | 7 | 85.7%
Ashanti | community | Ahafo Ano South | Odoyefe | Prestige () |  | 90 | 90%
Ashanti | community | Ahafo Ano South | Kumawu | Prestige () |  | 4 | 89.4%
Ashanti | community | Ahafo Ano South | Dunyan-Nkwanta | Prestige () |  | 7 | 78.7%
Ashanti | community | Ahafo Ano South | Okroase | Prestige () |  | 4 | 91.4%
Ashanti | community | Ahafo Ano South | Asibey-Nkwanta | Prestige () |  | 1 | 82.1%
Ashanti | community | Ahafo Ano South | Awaduwa | Prestige () |  | 5 | 87.5%
Ashanti | community | Ahafo Ano South | Pinewotrim | Prestige () |  | 3 | 83.3%
Ashanti | community | Ahafo Ano South | Kunsu-Camp | Prestige () |  | 5 | 93.5%
Ashanti | community | Ahafo Ano South | Bonsukrom | Prestige () |  | 7 | 73.7%
Ashanti | community | Ahafo Ano South | Onyinanufu | Prestige () |  | 90 | 90%
Ashanti | community | Ahafo Ano South | Gyaekontabuo | Prestige () |  | 2 | 92.2%
Ashanti | community | Ahafo Ano South | Awaduwa Nkwanta | Prestige () |  | 70 | 70%
Ashanti | community | Ahafo Ano South East | Abesewa | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Nyamebekyere | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Betinko | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Amanfoase | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Nsuta | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Kwamekyemkrom | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Ahwrewam | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Ahafo Ano South East | Fawoman | Godbless Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | New Edubiase | Apagya | New Life () |  | 1 | 16.1%
Ashanti | community | New Edubiase | Atobiase | New Life () |  | 5 | 16.5%
Ashanti | community | New Edubiase | Ataabre | New Life () |  | 9 | 18.9%
Ashanti | community | New Edubiase | New Edubiase | New Life () |  | 22 | 22%
Ashanti | community | Afigya Kwabre North & South | Adam & Hawa | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North & South | Alhidaya | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North & South | Wonoagya | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North & South | Ajaiku | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North & South | Ahenfo | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Nkrang | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Atwima Mim | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Nkawie Panin | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Adankwame | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Newtown | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya North | Amadum | New Life () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Akropong | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Mfensi | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Taabre | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Ntensere | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Nyankyerehenease | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Nwabiagya South | Pokukrom | Apam A.E. Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Buoya | Godcan () |  | 90 | 90%
Ashanti | community | Sekyere East | Addukrom | Godcan () |  | 89 | 89%
Ashanti | community | Sekyere East | Motokrodua | Godcan () |  | 89 | 89%
Ashanti | community | Sekyere East | Tetekaaso No.1 | Godcan () |  | 89 | 89%
Ashanti | community | Sekyere East | Tetekaaso No.2 | Godcan () |  | 89 | 89%
Ashanti | community | Sekyere East | Adagya No. 1&2 | Godcan () |  | 89 | 89%
Ashanti | community | Sekyere East | Effiduase Barrier | Godcan () |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Kobreso | Godcan () |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Adensuagya | Godcan () |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere Central | Barlana | Saini Morrison |  | 70 | 70%
Ashanti | community | Sekyere Central | Dome | Saini Morrison |  | 4 | 75.4%
Ashanti | community | Sekyere Central | Sankakaase | Saini Morrison |  | 3 | 57.3%
Ashanti | community | Sekyere Central | Congo Nkwanta | Saini Morrison |  | 2 | 34.2%
Ashanti | community | Sekyere Central | Tailor Nkwanta | Saini Morrison |  | 1 | 27.1%
Ashanti | community | Sekyere Central | Okun Nkwanta | Saini Morrison |  | 40 | 40%
Ashanti | community | Sekyere Central | Okufea | Saini Morrison |  | 2 | 22.2%
Ashanti | community | Sekyere East | Oseikrom | The Saint Electricals |  | 40 | 40%
Ashanti | community | Sekyere East | Attakrom | The Saint Electricals |  | 40 | 40%
Ashanti | community | Sekyere East | Obaaoayikrim | The Saint Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Adenhuagya | The Saint Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Ahotokrom | The Saint Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Asokore Zongo | The Saint Electricals |  | 0 | 0% Yet to start scope
Ashanti | community | Sekyere East | Krobea Newsite | The Saint Electricals |  | 30 | 15.30%
Ashanti | community | Akrofuom | Akrofuom Extension | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Sikaman | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Brofoyedu | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Amponyase | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Amponyase Junction | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Wawase | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Fenaso Nkwanta | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Akrofuom | Kokotenten | Ans () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Agogo | New Life () |  | 9 | 24.9%
Ashanti | community | Asante Akim | Juansa | New Life () |  | 40 | 40%
Ashanti | community | Asante Akim | Domeabra | New Life () |  | 10 | 10%
Ashanti | community | Asante Akim | Hwediem | New Life () |  | 10 | 10%
Ashanti | community | Asante Akim | Anawuokrom | Matwen Awurade () |  | 2 | 56.2%
Ashanti | community | Asante Akim | Nsiakrom | Matwen Awurade () |  | 2 | 56.2%
Ashanti | community | Asante Akim | Nyamebekyekrom | Matwen Awurade () |  | 4 | 24.4%
Ashanti | community | Asante Akim | Beposo | Matwen Awurade () |  | 8 | 12.8%
Ashanti | community | Asante Akim | Bomfa Newsite | Matwen Awurade () |  | 10 | 10%
Ashanti | community | Asante Akim | Wioso | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Akutuase | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Amantena | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Pekyebrekye | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Behwe | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Nyanponase | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim | Praaso | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Atwedie | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Kwawkrom | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Yawkwei No.2 | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Odumase Mr Odoom Area | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Praaso Old Town | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Konongo Lady Diana | Puretec () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Konongo Domeabra | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Agogo Collins SHS | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Mankyekye Spot Area | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Konongo Garage | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Bontibease | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Dabi Asem Area | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Asiwa | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Bomfa Old Town | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Bomfa New Town | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Achiase Town | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Konongo Low Cost | Faah Tech Engineering Co. Ltd. () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Wenchi | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Bompata | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Kropa | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Bogu No.2 | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Jubi | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Mampongteng | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Osei krom | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Agyekum krom | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Omane Boamah | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Kokum Krom | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Kontomire | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Ahnsan | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Adonfe | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Domi Amintim | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Dwansah | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Otuoserebour | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Pipam | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim North | Wofa Kyei | Badjer Engineering Services Company Limited () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Alamire China 2 | Kinfix Services Limited () |  | 3 | 59.3%
Ashanti | community | Ejura Municipal | Sabongari | Kinfix Services Limited () |  | 1 | 50.1%
Ashanti | community | Ejura Municipal | Dobidi | Kinfix Services Limited () |  | 9 | 57.9%
Ashanti | community | Ejura Municipal | Serikikrom | Kinfix Services Limited () |  | 7 | 62.7%
Ashanti | community | Ejura Municipal | Abrodanho | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Zongo Frafra | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Zongo B | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Sekyire New Town | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Nyamesomkrom | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Ejura Municipal | Sunkwa | A. A. Warncharn Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | New Edubiase & Adansi South | Atobease 1D1F | W.A. Duah Electricals Limited () |  | 45 | 45%
Ashanti | community | New Edubiase & Adansi South | Subrisu Ketewa | W.A. Duah Electricals Limited () |  | 40 | 40%
Ashanti | community | New Edubiase & Adansi South | Bepoase CHIP Compound | W.A. Duah Electricals Limited () |  | 10 | 10%
Ashanti | community | New Edubiase & Adansi South | Tweapeasen CHIP Compound | W.A. Duah Electricals Limited () |  | 4 | 5.4%
Ashanti | community | New Edubiase & Adansi South | Menanng CHIPS Compound | W.A. Duah Electricals Limited () |  | 5 | 42.5%
Ashanti | community | Atwima Kwahoma | Kantinkyire Township | Ben K Electrical Works |  | 0 | 0% Yet to start scope
Ashanti | community | Atwima Kwahoma | Afraho Odumase Township | Ben K Electrical Works |  | 3 | 47.3%
Ashanti | community | Atwima Kwahoma | Ampabame No. 2 | Dadie Kwadwo () |  | 0 | 9.0%
Ashanti | community | Atwima Kwahoma | Asaman Township | Dadie Kwadwo () |  | 5 | 23.5%
Ashanti | community | Atwima Kwahoma | Nketia Township | Dadie Kwadwo () |  | 1 | 24.1%
Ashanti | community | Effiduase | Nsutam dandwa | Pabseimah () |  | 10 | 10%
Ashanti | community | Effiduase | Nsutam Kofikrom | Pabseimah () |  | 10 | 10%
Ashanti | community | Effiduase | Akwam | Pabseimah () |  | 10 | 10%
Ashanti | community | Effiduase | Oyoko Akotosu | Pabseimah () |  | 10 | 10%
Ashanti | community | Effiduase | Oyoko SDA | Pabseimah () |  | 10 | 10%
Ashanti | community | Effiduase | Pepease Domeabra | Pabseimah () |  | 10 | 10%
Ashanti | community | Ejisu Municipality | Dwenease | Pabseimah () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Hwereso | Pabseimah () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Atiakrom | Pabseimah () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Adersena Islam | Pabseimah () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Donase Krakrom | Pabseimah () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Adersena | Kamnaa () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Otentic | Kamnaa () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Donase | Kamnaa () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Penchreni | Kamnaa () |  | 0 | 0% Yet to start scope
Ashanti | community | Ejisu Municipality | Abenase | Kamnaa () |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Nsuta Subriso | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Obuobikrom | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Samankrom | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Mpetenmua | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Bosukrom | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Sonkoyiwa | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Fremu | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Acheampong | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Domeabra | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Apagya SHS | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Afedea | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Tensuoni | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Adaagye | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Adansi South | Odoomkrom | Former Mp Contractor: W.A Duah Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Adowa | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Akyerema | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Aworasa | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Sikafriham | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Pentenpena | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Jatokrom | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Kotenso | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Kofihwikrom | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie Central | Daban 1&2 | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Datano | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Adubia | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Kaniago | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Tontokrom | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Odaho | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Mem | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Akwasiso/Kumpese | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Takorasi | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Amansie South | Ayirebikrom | Former Mp Contractor: Bukjee Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North | Ahenkro | Former Deputy Energy Minister Contractor: Okoso & Sons |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North | Nkwantakese Town | Former Deputy Energy Minister Contractor: Okoso & Sons |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North | Nkwantakese Habitat | Former Deputy Energy Minister Contractor: Okoso & Sons |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North | Esaase | Former Deputy Energy Minister Contractor: Okoso & Sons |  | 0 | 0% Yet to start scope
Ashanti | community | Afigya Kwabre North | Kwamang | Former Deputy Energy Minister Contractor: Okoso & Sons |  | 0 | 0% Yet to start scope
Ashanti | community |  | Oyera |  |  | 10 | 10%
Ashanti | community | Offinso North | Apatamu | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Gyamang | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Amponsahkrom | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Dwendabi | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Papasisi | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Konkon | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Komfour Duodu | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Agude Area | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Afrancho Enterprise | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Amoanimkrom | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Bobra | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Akrofu | Former Mp Contractor: Amakye Global Links Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | Akrofua | Former Mp Contractor: Augyeb Ltd. |  | 8 | 38.8%
Ashanti | community | Offinso North | Nyamebekyere | Former Mp Contractor: Augyeb Ltd. |  | 1 | 36.1%
Ashanti | community | Offinso North | Bosomposo | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Mpapaamu | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Nkwaakwaa | Former Mp Contractor: Augyeb Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Offinso North | New Atwene | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Kwaem | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Sraneso No.1 | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Sraneso Zongo | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Offinso North | Sraneso No.2 | Former Mp Contractor: Augyeb Ltd. |  | 89 | 89%
Ashanti | community | Asante Akim South | Akwaatia No.2 | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Odoiakora | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Komeagya Odubi | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Awereso | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Okonyaw | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Mentukwa | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Tanokrom | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Kofi Sei | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Boadan | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Wrompo Junction | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Kaamu Gensoso | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Kpodzinyanor | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Didkpnchi No.2 | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Amaakrom | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Asantekrom | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Ashanti | community | Asante Akim South | Kyempo Zongo | Former Dce Contractor: A.E Apam Ltd. |  | 0 | 0% Yet to start scope
Savannah | community | Central Gonja P1 | Zomlampe | Ila | 97 | 97 | 0.0
Savannah | community | Central Gonja P1 | Nikpegu | Ila | 89.1 | 89.1 | 0.0
Savannah | community | Central Gonja P1 | Torope | Ila | 97.3 | 97.3 | 0.0
Savannah | community | Central Gonja P1 | Dokope | Ila | 97.1 | 97.1 | 0.0
Savannah | community | Central Gonja P1 | Kpatinyan | Ila | 96.7 | 96.7 | 0.0
Savannah | community | Central Gonja P1 | Darivogupe | Ila | 98.6 | 98.6 | 0.0
Savannah | community | Central Gonja P2 | Bagpe | Ila | 89.3 | 89.3 | 0.0
Savannah | community | Central Gonja P2 | Dawunipe | Ila | 95.9 | 95.9 | 0.0
Savannah | community | Central Gonja P2 | Diwurupe | Ila | 95.7 | 95.7 | 0.0
Savannah | community | Central Gonja P2 | Larigbani | Ila | 97.1 | 97.1 | 0.0
Savannah | community | Central Gonja P2 | Mammudupe | Ila | 89.4 | 89.4 | 0.0
Savannah | community | Central Gonja P2 | Sankaupe | Ila | 89.9 | 89.9 | 0.0
Savannah | community | East Gonja | Kpembe | Asamoah Const. | 94.9 | 94.9 | 0.0
Savannah | community | East Gonja | Iddipe | Asamoah Const. | 84.6 | 84.6 | 0.0
Savannah | community | East Gonja | Sabon Kasoa | Asamoah Const. | 90.7 | 90.7 | 0.0
Northern | community | Kpandai | Kokonaje area | Mohatu | 49.8 | 49.8 | 0.0
Northern | community | Kpandai | Kokomba chief | Mohatu | 78.5 | 78.5 | 0.0
Northern | community | Kpandai | Kpansec camp | Mohatu | 33.3 | 33.3 | 0.0
Northern | community | Kpandai | Polyclinic area | Mohatu | 91.7 | 91.7 | 0.0
Northern | community | Kpandai | Baduli | Mohatu | 96.7 | 96.7 | 0.0
Northern | community | Kpandai | Zongo | Mohatu | 53.3 | 53.3 | 0.0
Northern | community | Kpandai | Behind lorry station | Mohatu | 19.6 | 19.6 | 0.0
Northern | community | Nanumba North | Baguo | Mohatu | 48.6 | 48.6 | 0.0
Northern | community | Nanumba North | Jeji | Mohatu | 68.1 | 68.1 | 0.0
Northern | community | Nanumba North | Kasapoi | Mohatu | 43.4 | 43.4 | 0.0
Northern | community | Nanton | Zoozugu | Mohatu | 99.7 | 99.7 | 0.0
Northern | community | Nanton | Kabongyaga | Mohatu | 16.7 | 16.7 | 0.0
Northern | community | Nanton | Bilpella | Mohatu | 62.9 | 62.9 | 0.0
Northern | community | Savelugu | Zaachi-Taansi | Al-Sofwan | 27.6 | 27.6 | 0.0
Northern | community | Savelugu | Tootanyili | Al-Sofwan | 38.8 | 38.8 | 0.0
Northern | community | Savelugu | Digkpuli | Al-Sofwan | 52.3 | 52.3 | 0.0
Northern | community | Savelugu | Saakpuli | Al-Sofwan | 89.5 | 89.5 | 0.0
Northern | community | Karaga | Tamalgu | Hudu Fam | 50.2 | 50.2 | 0.0
Northern | community | Karaga | Bagurugu | Hudu Fam | 59.8 | 59.8 | 0.0
Northern | community | Karaga | Sung | Hudu Fam | 48.8 | 48.8 | 0.0
Northern | community | Karaga | Pishigu | Hudu Fam | 59.8 | 59.8 | 0.0
Northern | community | Nanumba North | Machoni | E.K. Kwasak | 45.1 | 45.1 | 0.0
Northern | community | Nanumba North | Salnayili | E.K. Kwasak | 99.9 | 99.9 | 0.0
Northern | community | Nanumba North | Kuboabu | E.K. Kwasak | 71.7 | 71.7 | 0.0
Northern | community | Nanumba North | Monkuado | E.K. Kwasak | 24.8 | 24.8 | 0.0
Northern | community | Nanumba North | Sikpam | E.K. Kwasak | 46.3 | 46.3 | 0.0
Northern | community | Nanumba North | Okpanjani | E.K. Kwasak | 0 | 0 | 0.0
Northern | community | Yendi | Kulkpeni | Bright Conner | 0 | 0 | 0.0
Northern | community | Yendi | Kpalsondo | Bright Conner | 47.9 | 47.9 | 0.0
Northern | community | Saboba | Namong Bani | Bi-Netti | 52.3 | 52.3 | 0.0
Northern | community | Saboba | Bichakiyado | Bi-Netti | 44.3 | 44.3 | 0.0
Northern | community | Saboba | Sayal/Zamsheigu | Bi-Netti | 29.3 | 29.3 | 0.0
Northern | community | Tatale | Bulkpali | Primus | 98.6 | 98.6 | 0.0
Northern | community | Nanumba South | Sakpe | Abudu Elec. | 77.1 | 77.1 | 0.0
Northern | community | Nanumba South | Gunguni | Abudu Elec. | 80.1 | 80.1 | 0.0
Northern | community | Nanumba South | Kapugu | Abudu Elec. | 55.5 | 55.5 | 0.0
Northern | community | Nanumba South | Bandiyilli | Abudu Elec. | 77.6 | 77.6 | 0.0
Northern | community | Nanumba South | Asafoatse | Abudu Elec. | 20 | 20 | 0.0
Northern | community | Nanumba North | Worbogu | Fidelity Ltd | 57.5 | 57.5 | 0.0
Northern | community | Karaga | Shamsia | M.Y. Elec | 64.7 | 64.7 | 0.0
Northern | community | Karaga | Dabulo | Gargash Ent. | 33.3 | 33.3 | 0.0
Northern | community | Karaga | Vowari | Gargash Ent. | 33.3 | 33.3 | 0.0
Northern | community | Tolon | Kapalnayili/ Toroyili | Mohatu | 61.7 | 61.7 | 0.0
Northern | community | Tolon | Tindang/ Apleyili | Mohatu | 81.4 | 81.4 | 0.0
Northern | community | Tolon | Botingli/ Dalimbili | Mohatu | 74 | 74 | 0.0
Northern | community | Tolon | Buyili | Mohatu | 11.9 | 11.9 | 0.0
Northern | community | Tolon | Nyankpala/ Kuoknayili | Mohatu | 40 | 40 | 0.0
Northern | community | Tamale South | Pagazaa | Edicas & Son | 64.7 | 64.7 | 0.0
Northern | community | Tamale South | Datoyili | Edicas & Son | 65 | 65 | 0.0
Northern | community | Tamale South | Chanzeni | Edicas & Son | 25 | 25 | 0.0
Northern | community | Tamale South | Changnayili | Edicas & Son | 33.3 | 33.3 | 0.0
Northern | community | Tamale South | Zuo | Edicas & Son | 16.7 | 16.7 | 0.0
Northern | community | Tamale South | Bulpela Dam | Edicas & Son | 0 | 0 | 0.0
Northern | community | Tamale South | Dohini | Edicas & Son | 0 | 0 | 0.0
Northern | community | Tamale South | Kukuo | Edicas & Son | 0 | 0 | 0.0
Northern | community | Karaga | Karaga North, South, Assem | Bf 21 Ent. | 85.4 | 85.4 | 0.0
Northern | community | Yendi | Andoyili | Bihasung Elec. | 75 | 75 | 0.0
Northern | community | Yendi | Klukpanga | Bihasung Elec. | 75 | 75 | 0.0
Northern | community | Yendi | Zakolinyen Bologni | Madi Saha | 89.4 | 89.4 | 0.0
Northern | community | Yendi | Neibong | E.F. Electricals | 65.1 | 82.0 | 16.9
Northern | community | Yendi | Oseido | E.F. Electricals | 63.8 | 63.8 | 0.0
Northern | community | Yendi | Kpanji | Shin-Anoli Ent. | 91.0 | 91.0 | 0.0
Northern | community | Yendi | Banchiyill 1&2 | Shin-Anoli Ent. | 91.4 | 91.4 | 0.0
Northern | community | Yendi | Sunsongbun | Meizeri Gh. Ltd | 67.7 | 67.7 | 0.0
Northern | community | Yendi | Kpatiya | Meizeri Gh. Ltd | 47.8 | 59.0 | 11.2
Northern | community | Yendi | Nalogu | Meizeri Gh. Ltd | 66.4 | 82.9 | 16.5
Savannah | community | North Gonja | Kito | Archives Ent. | 85.9 | 85.9 | 0.0
Savannah | community | North Gonja | Gao | Archives Ent. | 75.4 | 75.4 | 0.0
Savannah | community | North Gonja | Donkope | Archives Ent. | 23.7 | 23.7 | 0.0
Savannah | community | North Gonja | Wawato | Archives Ent. | 15.8 | 15.8 | 0.0
Savannah | community | North Gonja | Guebagu | Archives Ent. | 17.6 | 17.6 | 0.0
Northern | community | Yendi | Nasa Achiyili | Proswen Giants | 66.7 | 66.7 | 0.0
Northern | community | Yendi | Jemboni | Proswen Giants | 0 | 0 | 0.0
Northern | community | Yendi | Baaduli | Proswen Giants | 0 | 0 | 0.0
Northern | community | Yendi | Kpalsogni | Proswen Giants | 4.2 | 8.0 | 3.8
Northern | community | Yendi | Jagol | Al-Sofwan | 16.7 | 23.8 | 7.1
Northern | community | Yendi | Napali-Bemolimi | Al-Sofwan | 0 | 0 | 0.0
Savannah | community | North East Gonja | Kpinchilla | Dema-Naa | 97.7 | 97.7 | 0.0
Savannah | community | North East Gonja | Sakpalua | Tasco | 95.5 | 95.5 | 0.0
Savannah | community | West Gonja | Kpiri-Frafra no. 1 | Pat Hayford | 81.8 | 81.8 | 0.0
Savannah | community | West Gonja | Kpiri-Frafra no. 2 | Archives Ent. | 47.6 | 59.5 | 11.9
Savannah | community | West Gonja | Kpiri-Frafra no. 3 | Archives Ent. | 54.8 | 70.5 | 15.7
Savannah | community | West Gonja | Kpiri-Frafra no. 6 | E.F. Electricals | 36.5 | 59.6 | 23.1
Savannah | community | West Gonja | Kadendelampa | Kug-Bihi | 31.5 | 31.5 | 0.0
Savannah | community | West Gonja | Dakpala Kura | T-Tommy | 40 | 40 | 0.0
Savannah | community | West Gonja | Lorito | A. Awuche Eng. | 24.8 | 24.8 | 0.0
Savannah | community | West Gonja | Seiyiri | Hudu Fam | 20.5 | 20.5 | 0.0
Savannah | community | West Gonja | Kpiri-Frafa no. 4 | Darex | 0.0 | 0.0 | 0.0
Savannah | community | West Gonja | Kpiri-Frafa no. 5 | Darex | 0.0 | 0.0 | 0.0
Savannah | community | West Gonja | Abukari Kura | Shin-Anoli Ent. | 91.9 | 91.9 | 0.0
Savannah | community | West Gonja | Zanji Kura | Shin-Anoli Ent. | 88.4 | 88.4 | 0.0
Northern | community | Yendi | Warikpomo | Shin-Anoli Ent. | 11.1 | 11.1 | 0.0
Northern | community | Yendi | Kpasani | Shin-Anoli Ent. | 16.7 | 16.7 | 0.0
Northern | community | Yendi | Pion Kamonayili | Shin-Anoli Ent. | 0.0 | 0.0 | 0.0
Northern | community | Savelugu | Tarikpa | A.A. Bucas Ent. | 0.0 | 0.0 | 0.0
Northern | community | Savelugu | Pong Tamale | A.A. Bucas Ent. | 22.5 | 22.5 | 0.0
Northern | community | Savelugu | Diare | A.A. Bucas Ent. | 0.0 | 0.0 | 0.0
Northern | community | Savelugu | Mogla | Bazaah Ent | 0.0 | 0.0 | 0.0
Northern | community | Savelugu | Savelugu | Bazaah Ent | 11.1 | 11.1 | 0.0
Northern | community | Kpandai | Tikpakpani | Mohatu | 0.0 | 0.0 | 0.0
Northern | community | Kpandai | Buogben | Mohatu | 0.0 | 0.0 | 0.0
Northern | community | Kpandai | Gbebendo | Mohatu | 0.0 | 0.0 | 0.0
Northern | community | Kpandai | Nfigmado & Kumunisi | Mohatu | 0.0 | 0.0 | 0.0
Northern | community | Kpandai | Banajado & Ugando | Mohatu | 0.0 | 0.0 | 0.0
Savannah | community | West Gonja | Damongo Military camp | M-H Shalifa |  | 100 | Completed May (Cost Sharing)
Savannah | community | Central Gonja | Nyantang | Korigu Construction |  | 100 | Completed June (SHEP 4)
Savannah | community | West Gonja | Azure Kura | M-H Shalifa |  | 100 | Completed August (Cost Sharing)
Savannah | community | East Gonja | Kpembe | A.Asamoah Const. |  | 100 | Completed September (SHEP 4)
Savannah | community | East Gonja | Iddipe | A.Asamoah Const. |  | 100 | Completed September (SHEP 4)
Savannah | community | East Gonja | Sabon Kasoa | A.Asamoah Const. |  | 100 | Completed September (SHEP 4)
Savannah | community | Central Gonja | Zomlampe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Nikpegu | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Torope | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Dokope | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Kpatinyan | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Darivogupe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Bagpe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Dawunipe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Diwurupe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Larigbani | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Mammudupe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Sankaupe | Ila Engineering |  | 100 | Completed October (SHEP 4)
Savannah | community | Central Gonja | Nyinyape | Ila Engineering |  | 100 | Completed October (SHEP 4)
Northern | community | Tatale | Bulkpali | Primus Laborem |  | 100 | Completed October (SHEP 5)
Northern | community | Gushegu | Saguli | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Zulogu | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Kpanashei | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Bogu | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Kutung | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Tinyogu | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Nagnuni | Gushegu Mp |  | 100 | Completed November (Cost Sharing)
Northern | community | Gushegu | Kpahikpaba | Gushegu Mp |  | 100 | Completed November (Cost Sharing)

## BE_ASR_Q4_Poles
region | district | community | contractor | package_number | lv_poles_erected_q | hv_poles_erected_q
Bono East | NKORANZA NORTH | ASEKYE | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 | 60
Bono East | NKORANZA NORTH | FIEMA | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 | 40
Bono East | NKORANZA NORTH | BONTE | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 | 100
Bono East | NKORANZA NORTH | BODOM | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 | 50
Bono East | NKORANZA NORTH | MANGOASE JUNCTION | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 30
Bono East | PRU | JUMPE | MY REDEEMER ELE. & CVL ENG. WKS. | SHEP-4-BER-PD-MRECEW-10-19 | 50
Ashanti | AMANSIE CENTRAL | Ntwaso & Aduntia | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 12
Ashanti | AMANSIE CENTRAL | Mile 18 | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 18 | 2
Ashanti | AMANSIE CENTRAL | Adwease No. 1&2 | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 6
Ashanti | AMANSIE CENTRAL | Sudantoa | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 20
Ashanti | AMANSIE CENTRAL | Odumto | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 25 | 9
Ashanti | AMANSIE CENTRAL | Manfo | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 20 | 5
Ashanti | AMANSIE CENTRAL | Sabe 1 | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 25 | 5
Ashanti | AMANSIE CENTRAL | Sabe 2 | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 12 | 4
Ashanti | AMANSIE CENTRAL | Ewiase | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 18
Ashanti | AMANSIE CENTRAL | Apeboso | PURETEC | SHEP-ASR-ACD-PEL-05-18 | 12 | 21
Ashanti | AMANSIE CENTRAL | Asuadae | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 21
Ashanti | AMANSIE CENTRAL | Mpenkyireni | PURETEC | SHEP-ASR-ACD-PEL-05-18 |  | 43
Ashanti | KWABRE EAST | Ntonso | VINIADO ENG. LIMITED | SHEP-4-ASR-KEM-VEL-07-19 |  | 100
Ashanti | ATWIMA MPONUA | Toase | POSSIBLE POWER LIMITED | SHEP-ASR-AMDA-PPEL-10-16 |  | 80
Ashanti | ATWIMA MPONUA | Dabang | POSSIBLE POWER LIMITED | SHEP-ASR-AMDA-PPEL-10-16 |  | 80
Ashanti | ATWIMA MPONUA | Yabee | POSSIBLE POWER LIMITED | SHEP-ASR-AMDA-PPEL-10-16 |  | 30
Ashanti | ATWIMA MPONUA | Kyekyewere | POSSIBLE POWER LIMITED | SHEP-ASR-AMDA-PPEL-10-16 |  | 60
Ashanti | ATWIMA MPONUA | Nkyensrekrom | POSSIBLE POWER LIMITED | SHEP-ASR-AMDA-PPEL-10-16 |  | 50
Ashanti | ADANSI FOMENA | Apunpunso | BUKJEE COMPANY LIMITED |  |  | 60

## BE_ASR_Q4_Transformers
region | district | community | contractor | package_number | tx_11kv | tx_33kv | tx_count
Bono East | PRU | AJARAJA BEPOSO | KINGSCO LTD. | SHEP-4-BER-PD-KECEL-10-19 |  | 100KVA, 1 | 1
Bono East | SENE WEST | Amangoase | STEVGARBS LTD. | SHEP-BAR-SWD-SEL-09-16 |  | 50KVA, 1 | 1
Bono East | SENE WEST | Konkose | STEVGARBS LTD. |  |  | 100KVA, 1 | 1
Bono East | SENE WEST | Chokose | STEVGARBS LTD. |  |  | 50KVA, 1 | 1
Bono East | NKORANZA NORTH | Odumase | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Fiema | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Akonkonti | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Bonte | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Yefri | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 200kVA, 1 | 1
Bono East | NKORANZA NORTH | Asekye | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Senya | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Bomini | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Domeabra | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Akrudwa | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Bodom | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Pienyina | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Mangoase Junction | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 1 | 1
Bono East | NKORANZA NORTH | Mpintsin | FRANVES ENG. WORKS | SHEP-4-BE&WE-NN&EKD-FEL-09-19 |  | 100kVA, 2 | 1
Bono East | ATEBUBU AMANTIN | Islamic | UNIQUE TITAN | SHEP-4-BAR-AAD-UTCL-03-20 |  | 100kVA, 1 | 1
Bono East | ATEBUBU AMANTIN | New Duabone | UNIQUE TITAN | SHEP-4-BAR-AAD-UTCL-03-20 |  | 100kVA, 1 | 1
Bono East | ATEBUBU AMANTIN | Agric Station | UNIQUE TITAN | SHEP-4-BAR-AAD-UTCL-03-20 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Nyamebekyere | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Sarachigona | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Tanokrom | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Baabu Akura | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Tano Akura | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Sissala Line Ext. | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 /P3 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Drepo | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Yerepemso | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Attahkrom | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Brechakrom | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 50kVA, 1 | 1
Bono East | KINTAMPO NORTH | Asuogya | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 100kVA, 1 | 1
Bono East | KINTAMPO NORTH | Dakorii | KORIGU LTD. | SHEP-4-BER-KND-KCCL-07-19 |  | 50kVA, 1 | 1
Ashanti | Asante Akim | Anawuokrom | Matwen Awurade Ltd. | SHEP-4-ASR-AAD-MAEECL-02-20 |  | 100KVA, 1 | 1
Ashanti | Asante Akim | Nsiakrom | Matwen Awurade Ltd. | SHEP-4-ASR-AAD-MAEECL-02-20 |  | 100KVA, 1 | 1
Ashanti | Asante Akim | Nyamebekyere | Matwen Awurade Ltd. | SHEP-4-ASR-AAD-MAEECL-02-20 |  | 50KVA, 1 | 1
Ashanti | Asante Akim | Beposo | Matwen Awurade Ltd. | SHEP-4-ASR-AAD-MAEECL-02-20 |  | 100KVA, 1 | 1
Ashanti | Asante Akim | Bomfa Newste | Matwen Awurade Ltd. | SHEP-4-ASR-AAD-MAEECL-02-20 |  | 100KVA, 1 | 1
Ashanti | Kwabre East | Henoo | Pomark Ltd. | SHEP-4-ASR-KEM-PECL-11-19 | 100KVA |  | 1
Ashanti | Kwabre East | Djako | Pomark Ltd. | SHEP-4-ASR-KEM-PECL-11-19 | 100KVA |  | 1
Ashanti | Kwabre East | Adjeimpra | Pomark Ltd. | SHEP-4-ASR-KEM-PECL-11-19 | 100KVA |  | 1
Ashanti | Kwabre East | Adadiemtem Manchia Newsite | Antoa B | SHEP-4-ASR-KEM-ABVL-07-19 | 100KVA |  | 1

## UE_Poles_Supplied
district | contractor | community | lv_poles_supplied | ht_poles_supplied
Builsa North | Wilkwak Limited | Kalibiisa | 100
Builsa North | Wilkwak Limited | Fiisa | 120
Builsa North | Wilkwak Limited | Chuchuliga Awuchinayeri | 110
Builsa North | Wilkwak Limited | Chuchuliga Yiepala | 100
Builsa North | Wilkwak Limited | Jaata | 145
Builsa North | Wilkwak Limited | Molinsa | 155
Builsa North | Wilkwak Limited | Tajirinsa | 100
Builsa North | Wilkwak Limited | Tampela | 170
Bongo | Kasn And Consult Limited | Awaa Atiabiisi |  | 100
Bongo | Kasn And Consult Limited | Awale Namoo |  | 95
Bongo | E. K. Asare Enterprise | Boko-Azumbuo | 100
Bongo | E. K. Asare Enterprise | Boko-Asackow | 100
Bongo | E. K. Asare Enterprise | Boko-Kumbilgo | 30
Binduri | Tirago Enterprise | Kaadi-Kudugu | 100
Binduri | Tirago Enterprise | Agomisin | 100 | 165
Binduri | Tirago Enterprise | Kaadi/Vako | 150
Binduri | Elios Engineering Limited | Dabuugu/Kukparigu | 100
Binduri | Elios Engineering Limited | Dulnatinga/Agbelgimvoos | 100
Binduri | Elios Engineering Limited | Boko | 210
Binduri | Elios Engineering Limited | Noyoko # 2 | 100
Binduri | Elios Engineering Limited | Noyoko # 1/Polsiga/Naboya | 90
Talensi | Jerferson Thompson | Kobelinsa/Bachingsa/Mutiensa | 100
Talensi | Jerferson Thompson | Gadema Tajirinsa | 120
Talensi | Jerferson Thompson | Gadem Tampela | 150
Talensi | Jerferson Thompson | Sakpare Suuni | 90
Talensi | Jerferson Thompson | Bapelugu | 40
Payaba Enterprise | Binduri | Bansi Winaba | 100
Payaba Enterprise | Binduri | 0 | 100

## Volta_Unparsed
contractor | district | sentence
David & Sons Limited | Akatsi North | 15 LV poles at Akeykope respectively in July, 2024.
David & Sons Limited | Akatsi North | 10 HT pole spans, 11 LV pole spans
David & Sons Limited | Akatsi North | and 15 LV pole spans strung at Tomkope and Akeykope respectively in August, 2024.
David & Sons Limited | Akatsi North | and 15 LV pole spans strung at Tomkope and Akeykope respectively in August, 2024.
Saini Morrison Engineering Limited | Ketu South | as 15LVpoles planted at Adzidote in May,2023.
Saini Morrison Engineering Limited | Keta/Anloga | 40 LV poles planted and strung at Avenui and 42 LV poles planted at Anfoeta Zongo.
Kwanash Enterprise | Akatsi South and Ketu North | The contractor installed 65 single phase meters at Avadre and 47 single phase meters at Adetsewui in May, 2023.
Kwanash Enterprise | Akatsi South and Ketu North | The contractor installed 65 single phase meters at Avadre and 47 single phase meters at Adetsewui in May, 2023.
Kwanash Enterprise | Akatsi South and Ketu North | The contractor is to complete 32 LV pole spans stringing and to plant 9
Kwanash Enterprise | Akatsi South and Ketu North | 30 single phase meters have been installed at Avadre, 39 single phase meters at Awayikope and 52 single phase meters at Agordeke in June, 2023.
Nyanab Ghana Limited | Krachi West | The contractor planted 88 LV
Nyanab Ghana Limited | Krachi West | poles and 72 HT poles in 3 communities in June 2017.
Nyanab Ghana Limited | Krachi West | Only an additional 33 LV
Nyanab Ghana Limited | Krachi West | The contractor planted additional 73 HT poles at Wananando #1 and
Nyanab Ghana Limited | Krachi West | The contractor planted additional 73 HT poles at Wananando #1 and
Nyanab Ghana Limited | Krachi West | 24 HT pole spans strung and additional
Nyanab Ghana Limited | Krachi West | 8 LV poles planted at Wananando #1 in January, 2024.
Nyanab Ghana Limited | Krachi West | 8 LV poles planted at Wananando #1 in January, 2024.
Nyanab Ghana Limited | Nkwanta North | 100 and 70 LV poles at Nabu and Gbango respectively.
Nyanab Ghana Limited | Nkwanta North | Additional 150 LV poles planted at
Nyanab Ghana Limited | Nkwanta North | Nabu and 34 LV poles at Gbango (Kpassa Extension) in September, 2022.
Transpower Engineering and Construction Limited | Krachi West | Additional 2 LV poles planted, 20 LV pole spans and 7 HT pole spans have been
Transpower Engineering and Construction Limited | Krachi West | meters at Lonkortor , 68 single phase meters at Kaliako, 36 single phase meters at Beposo
Transpower Engineering and Construction Limited | Krachi West | and 32 single phase meters at Konado in October, 2023.
Transpower Engineering and Construction Limited | Krachi West | The contractor received 150 LV poles in May 2017.
Transpower Engineering and Construction Limited | Krachi West | All the 150 LV poles were planted by the contractor in 5 communities in June 2017.
Transpower Engineering and Construction Limited | Krachi West | All the 150 LV poles were dressed with pole top materials without stay construction in July 2017.
Transpower Engineering and Construction Limited | South Tongu | meters installed at Nugblevi , 72 single phase meters installed at Sogbekope, 106 single phase meters installed at Adjahokope, 54 single phase meters installed at Deti and 110 single phase meters at Bayive.
Transpower Engineering and Construction Limited | South Tongu | The contractor strung 27 LV pole spans Korvenu/ Anyiheme/Anyidzene and 44 LV pole spans at
Kwanash Enterprise | Akatsi South | Additional 3 HT poles planted,
Kwanash Enterprise | Akatsi South | The contractor mounted a 50KVA transformer on the platform and transformer dressing on going as well as 1 LV pole planted and strung at Kporwui in May, 2024.
Kwanash Enterprise | Akatsi South | 2 HT wooden poles planted and substation work on-going at Gidisukope in November, 2025.
Kwanash Enterprise | Akatsi South | The contractor planted 6 LV poles and strung 6 LV pole spans at Gidisukope, 27 HT and19 LV pole spans Strung at Lawui Avedzi, 8 HT and 20 LV pole spans strung at Lawui Avegadzi and 10 HT and 11 LV pole spans strung at Lawui Kpota respectively in Febr
Kwanash Enterprise | Akatsi South | The contractor strung 11 HT pole spans at Kpevenu and also installed
Kwanash Enterprise | Akatsi South | The contractor strung 11 HT pole spans at Kpevenu and also installed
Kwanash Enterprise | Akatsi South | 23 single phase meters at Tsive in May, 2023.
Kwanash Enterprise | Akatsi South | The contractor strung 10 LV pole spans at
Kwanash Enterprise | Akatsi South | Asadame, 20 LV pole spans at Agblorkpo and 14 LV pole spans at Kpevenu respectively in
Kwanash Enterprise | Akatsi South | 6 LV pole spans strung at Agblorkpo and 7 LV pole spans strung at Kpevenu
Stone Electrical Limited | Ho West | pole-mounted transformers and 34 HT poles ( 14 steel and 20 wood) to the
Ghameric Enterprise | Buem | The above 9 communities were completed with LV netwoks except Ketsi with 70 LV poles planted without stringing.
David & Sons Limited | Ketu North | The contractor installed 100 and 50 single phase meters at Alagbavi #1 & #2, and Fiagbedu
David & Sons Limited | Ketu North | The contractor installed 100 and 50 single phase meters at Alagbavi #1 & #2, and Fiagbedu
David & Sons Limited | Ketu North | 6 HT poles have been planted at Savekor and 5 LV poles
David & Sons Limited | Ketu North | 6 HT poles have been planted at Savekor and 5 LV poles
David & Sons Limited | Ketu North | The contractor strung 6 HT and 4 LV pole spans at
David & Sons Limited | Ketu North | 6 LV poles were planted at
Ideal Electrical Works | Ketu North | The contractor installed 110 and 22 single phase
Ideal Electrical Works | Ketu North | The contractor strung 4 LV poles
Ideal Electrical Works | Ketu North | Spans at Adagbledu, 14 LV poles spans at Kuve/Deme and a pole span at Borkorgakope in
Ideal Electrical Works | Ketu North | 6 HT poles planted
Ideal Electrical Works | Ketu North | The contractor installed 260 meters with 258
Ideal Electrical Works | Ketu North | single phase and 2 three phase at Adagbledu, 118 meters with 115 single and 3 three
Ideal Electrical Works | Ketu North | phase meters installed at Awlikope as well as 153 meters with 149 single phase and 4 three
Ideal Electrical Works | Ketu North | The contractor strung 11 LV pole spans at
Demsack Engineering Limited | Krachi West | The contractor installed 57 and 30 single phase meters in
Demsack Engineering Limited | Krachi West | 28 LV poles planted and 7 LV pole spans strung at
Mensklif Company Limited | Ho West | 5 LV poles planted and 3 LV pole spans strung.
Addisco Electricals Ghana Limited | Nkwanta South | 1 LV pole planted and 30 LV poles spans strung at Kofie Akura and LV work completed in November, 2022.
Addisco Electricals Ghana Limited | Nkwanta South | 1 LV pole planted and 30 LV poles spans strung at Kofie Akura and LV work completed in November, 2022.
Addisco Electricals Ghana Limited | Nkwanta South | 1 LV pole planted and 30 LV poles spans strung at Kofie Akura and LV work completed in November, 2022.
Addisco Electricals Ghana Limited | Nkwanta South | The contractor strung 8 LV pole spans at Linkin Akura and 12 HT pole spans at Kofie Akura in December, 2022.
Addisco Electricals Ghana Limited | Nkwanta South | The contractor strung 8 LV pole spans at Linkin Akura and 12 HT pole spans at Kofie Akura in December, 2022.
Saini Morrison Engineering Limited | South Tongu | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans strung at Thunder Village, 36 LV poles planted and 6 LV pole spans strun
Saini Morrison Engineering Limited | South Tongu | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans strung at Thunder Village, 36 LV poles planted and 6 LV pole spans strun
Saini Morrison Engineering Limited | South Tongu | At Toklokpo Avegorme New Town, the contractor planted 26 LV poles and strung 26 LV pole spans.
Saini Morrison Engineering Limited | South Tongu | 7 LV pole spans strung at Medical City II and 4 LV pole spans strung at Thunder Village in October 2022.
Saini Morrison Engineering Limited | South Tongu | The contractor planted 7HT poles at Thunder Village, 2 HT poles at Toklokpo-Avegorme New Town and 4 LV pole spans strung at Medical City 2 in June, 2023.
Saini Morrison Engineering Limited | South Tongu | The contractor planted 7HT poles at Thunder Village, 2 HT poles at Toklokpo-Avegorme New Town and 4 LV pole spans strung at Medical City 2 in June, 2023.
Jenak Electrical Engineering Limited | Nkwanta South | 38 LV poles planted
Jenak Electrical Engineering Limited | Nkwanta South | 10 LV and 3LV poles planted at B.Zongo and Charti respectively in March, 2024.
Jenak Electrical Engineering Limited | Nkwanta South | 10 LV and 3LV poles planted at B.Zongo and Charti respectively in March, 2024.
Jenak Electrical Engineering Limited | Nkwanta South | 30 LV poles planted at Wanja Akura, 41 LV poles planted at Kofi Akura and 37 LV poles planted at Bisani in May, 2024.
Jenak Electrical Engineering Limited | Nkwanta South | The contractor mounted all 7 transformers on the platforms in the various communities in February, 2025 and awaiting dressing and earthing works.
Johome Company Limited | North Tongu | The contractor received 70 LV poles, planted 40 LV poles at Vome – Ext.
Johome Company Limited | North Tongu | 40 LV pole spans strung at Vome – Ext.
Johome Company Limited | North Tongu | The contractor planted 13 HT
Johome Company Limited | North Tongu | 60 LV poles planted and strung at
Johome Company Limited | North Tongu | The contractor planted 4 HT and 30 LV poles at
Johome Company Limited | North Tongu | Deikorpe/Fulakorpe, 25 LV poles at Bukarikope, 30 LV poles at Volo New Town and 20 LV
Addisco Electricals Ghana Limited | Biakoye | Additional 10 HT pole spans strung at C K Kofe in` April, 2023.
Addisco Electricals Ghana Limited | Biakoye | The contractor strung 12HT pole spans at Odormitor and 2 HT poles were planted at CK Kope respectively in July, 2023.
Addisco Electricals Ghana Limited | Biakoye | The contractor strung 12HT pole spans at Odormitor and 2 HT poles were planted at CK Kope respectively in July, 2023.
Addisco Electricals Ghana Limited | Biakoye | (Klefe) The contractor planted and strung 21 LV poles.
Johome Company Limited | Ho West | 21 HT poles were planted at
Johome Company Limited | Ho West | The contractor planted 42 LV poles at Kpenoe – Agadzi Zone 2 and no work done in Aklamakpetoe.
Johome Company Limited | Ho West | The contractor planted 23 LV poles and 61 pole spans strung at Kpenoe – Agadzi Zone May, 2023.
Johome Company Limited | Ho West | 13 HT poles planted and 3 HT pole spans strung at Kpenoe – Agadzi Zone October, 2023.
Johome Company Limited | Ho West | The contractor installed 190 single phase meters and strung 7 HT pole spans at Kpenoe - Agadzi Zone 2 in July 2024.166No single phase meters and 4No three phase meters installed at Kpenoe - Agadzi Zone 2 in August, 2024.
Johome Company Limited | Ho West | The contractor installed 190 single phase meters and strung 7 HT pole spans at Kpenoe - Agadzi Zone 2 in July 2024.166No single phase meters and 4No three phase meters installed at Kpenoe - Agadzi Zone 2 in August, 2024.
Johome Company Limited | Ho West | The contractor installed 190 single phase meters and strung 7 HT pole spans at Kpenoe - Agadzi Zone 2 in July 2024.166No single phase meters and 4No three phase meters installed at Kpenoe - Agadzi Zone 2 in August, 2024.
Demsack Engineering Limited | Nkwanta South | The contractor planted 68 LV poles and strung 56 LV pole spans at Mem Akura , 10 LV poles planted at Mantsei Akura and 20 HT pole spans strung at Sowyer in November 2022.
Demsack Engineering Limited | Nkwanta South | The contractor planted additional 37 HT poles, 12 LV poles and strung 6 HT pole spans in Sowyer in February, 2026.
Demsack Engineering Limited | Nkwanta South | Please Note: 61HT poles planted in Djato Akura earlier.
Ike Electrical & Civil Engineering Limited | South Tongu | The contractor was supplied with 150 LV poles.
Ike Electrical & Civil Engineering Limited | South Tongu | 95 LV poles were planted by the
Ike Electrical & Civil Engineering Limited | South Tongu | The contractor planted, dressed and strung 12 LV
Demsack Engineering Limited | Kpando | The contractor installed 22 and 10 single phase meters at Debidebi and Avega respectively in September, 2023.
Demsack Engineering Limited | Kpando | The contractor installed 22 and 10 single phase meters at Debidebi and Avega respectively in September, 2023.
Demsack Engineering Limited | Kpando | The contractor installed 23 and 35 single phase meters at Kudzra Asiklotoe No: 1&2 respectively in October, 2023.
Energy Works Limited | Nkwanta North | The contractor planted 59 HT poles at Obunja and strung 34 spans, 91 LV poles were planted with 68 spans strung.
Energy Works Limited | Nkwanta North | The contractor planted 59 HT poles at Obunja and strung 34 spans, 91 LV poles were planted with 68 spans strung.
Energy Works Limited | Nkwanta North | 30 HT poles planted at Koni 1&2 in January, 2025.
Energy Works Limited | Nkwanta North | 30 HT poles planted at Koni 1&2 in January, 2025.
David & Sons Limited | Nkwanta South | The contractor planted 80 HT poles in Alukpatsa Kotokro in October 2023.
David & Sons Limited | Nkwanta South | The contractor strung 18 HT and 22 HT pole spans at Dainkope and Krachi Akura respectively in February, 2025.
David & Sons Limited | Nkwanta South | The contractor strung 18 HT and 22 HT pole spans at Dainkope and Krachi Akura respectively in February, 2025.
David & Sons Limited | Nkwanta South | 11 LV and 20 LV poles planted in Panku Akura and Dain Akura respectively in February, 2026.
Demsack Engineering Limited | Nkwanta North | (Please Note: 35 LV poles planted in January, 2023 and 51 LV poles planted in February, 2023.)
Demsack Engineering Limited | Nkwanta North | (Please Note: 9 HT and 11 LV poles planted respectively in December, 2022).
Demsack Engineering Limited | Nkwanta North | 2 HT wooden poles planted and 6 HT pole spans strung.
Demsack Engineering Limited | Nkwanta North | 24 LV pole spans strung at Anomantu and additional 3 LV poles planted and 5 LV pole spans strung at Gbosike in May, 2024.
Wilkwak Engineering Company Limited | Ho West | The contractor planted 4 HT poles at Godokpe – New Site, 6 HT poles at Sokode Lande and 4 HT poles at Torgodo - New Site respectively in July, 2025.
Wilkwak Engineering Company Limited | Ho West | The contractor planted 4 HT poles at Godokpe – New Site, 6 HT poles at Sokode Lande and 4 HT poles at Torgodo - New Site respectively in July, 2025.

## Volta_Statements
contractor | district | community | verb | qty | item | sentence
David & Sons Limited | Akatsi North | Tomkope/Adivete | planted | 12 | HT poles | The contractor planted 12 HT poles and 15 LV poles at Tomkope/Adivete as well as
Saini Morrison Engineering Limited | Ketu South | Agblekpui | planted | 10 | LV pole spans | Additional 68 LV poles planted and 10LV pole spans strung at Agblekpui as well
Saini Morrison Engineering Limited | Ketu South | Agblekpui | planted | 68 | LV poles | Additional 68 LV poles planted and 10LV pole spans strung at Agblekpui as well
Saini Morrison Engineering Limited | Ketu South | Agblekpui | installed | 80 | single phase meters | The contractor installed 80 single phase meters at Agblekpui in July 2024.
Saini Morrison Engineering Limited | Ketu South | Tublukope | installed | 200 | single phase meters | 200 single phase meters installed at Tublukope in August, 2024.
Saini Morrison Engineering Limited | Ketu South | Tublukope | installed | 4 | three phase meters | The contractor installed 13 additional single phase meters at Agblekpui, 4 three phase meters at Tublukope, 75 single phase and 1 three phase meters at Tetekope as well as 70 singl
Saini Morrison Engineering Limited | Keta/Anloga | Avenui | planted | 4 | HT poles | The contractor planted 4 HT poles and strung 4HT pole spans at Avenui.
Saini Morrison Engineering Limited | Keta/Anloga | Anfoeta Zongo | planted | 42 | LV poles | 40 LV poles planted and strung at Avenui and 42 LV poles planted at Anfoeta Zongo.
Saini Morrison Engineering Limited | Keta/Anloga | Anyrawase | planted | 20 | LV poles | Substation work completed at Avenui and 20 LV poles planted at Anyrawase in November 2023.
Saini Morrison Engineering Limited | Keta/Anloga | Avenui | installed | 40 | single phase meters | The contractor installed 40 single phase meters at Avenui in September, 2024.
Saini Morrison Engineering Limited | Keta/Anloga | Anyrawase Official Town | planted | 34 | LV pole spans | 14 LV poles planted and 34 LV pole spans strung at Anyrawase Official Town in February, 2026.
Saini Morrison Engineering Limited | Keta/Anloga | Anyrawase Official Town | planted | 14 | LV poles | 14 LV poles planted and 34 LV pole spans strung at Anyrawase Official Town in February, 2026.
Kwanash Enterprise | Akatsi South and Ketu North | Avadre | installed | 30 | single phase meters | 30 single phase meters have been installed at Avadre, 39 single phase meters at Awayikope and 52 single phase meters at Agordeke in June, 2023.
Kwanash Enterprise | Akatsi South and Ketu North | Agordoe | strung | 15 | HT pole spans | 15 HT pole spans strung at Agordoe in February, 2024.
Kwanash Enterprise | Akatsi South and Ketu North | Flakavi | strung | 13 | LV pole spans | The contractor strung 13 LV pole spans at Flakavi in October, 2025.
Kwanash Enterprise | Akatsi South and Ketu North | Flakavi | strung | 18 | HT pole spans | 18 HT pole spans strung at Flakavi in February, 2026.
Nyanab Ghana Limited | Krachi West | Lakeside | planted | 119 | HT poles | 119 HT poles were planted at Lakeside in April
Nyanab Ghana Limited | Nkwanta North | Nabu | planted | 106 | HT poles | 106 HT poles were planted at Nabu with 54 strung.
Nyanab Ghana Limited | Nkwanta North | Nabu | planted | 37 | HT poles | The contractor planted 37 HT poles and strung 21 HT pole spans at Nabu in June, 2023.
Nyanab Ghana Limited | Nkwanta North | Gbango | planted | 21 | HT poles | 21 HT poles planted at Gbango in the month of July, 2023.
Nyanab Ghana Limited | Nkwanta North | Gbango | strung | 39 | LV pole spans | The contractor strung 39 LV pole spans at Gbango in December, 2023.
Nyanab Ghana Limited | Nkwanta North | Gbango | strung | 10 | HT pole spans | 10 HT pole spans have been strung at Gbango in January, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 65 | LV pole spans | 65 LV pole spans strung at Nabu in March, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 67 | LV pole spans | 67 LV pole spans strung at Nabu in April, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | planted | 34 | LV poles | The contractor planted additional 34 LV poles and strung 54 LV pole spans at Nabu as well as 12 LV pole spans at Gbango in May, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 30 | LV pole spans | 30 LV pole spans were strung at Nabu in June, 2024.
Nyanab Ghana Limited | Nkwanta North | Gbango | strung | 7 | HT pole spans | The contractor strung 7 HT pole spans at Gbango , 40 LV pole spans and 25 HT pole spans at Nabu in July 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 10 | LV pole spans | 15 HT and 10 LV pole spans strung at Nabu in October, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 20 | HT pole spans | The contractor strung 20 HT pole spans and 10 LV pole spans at Nabu in November, 2024.
Nyanab Ghana Limited | Nkwanta North | Nabu | strung | 4 | LV pole spans | 4 LV pole spans strung at Nabu in January, 2025.
Transpower Engineering and Construction Limited | Krachi West | Lonkortor and | installed | 28 | single phase meters | The contractor installed 52 and 28 single phase meters at Lonkortor and
Transpower Engineering and Construction Limited | Krachi West | Gyato | planted | 48 | LV poles | 48 LV poles were planted and strung at Gyato
Transpower Engineering and Construction Limited | Krachi West | Gyato Chanyo | planted | 22 | LV pole spans | 6 LV poles planted and 22 LV pole spans including combinations strung at Gyato Chanyo in February, 2025.
Transpower Engineering and Construction Limited | Krachi West | Gyato Chanyo | planted | 6 | LV poles | 6 LV poles planted and 22 LV pole spans including combinations strung at Gyato Chanyo in February, 2025.
Transpower Engineering and Construction Limited | Krachi West | Dornogbor | planted | 15 | LV poles | Stringing of the LV lines at Woe Dzidzorfe, Woe Aklorbodzi and Atsibor/Dorve was completed in April 2019.The contractor received and planted15 LV poles at Dornogbor in May 2019.
Transpower Engineering and Construction Limited | South Tongu | Adzikope | strung | 40 | LV pole spans | The contractor strung 40 LV pole spans at Adzikope, 23 LV pole spans at Chiefkope and 20 LV pole spans at Vigbedorkope in November 2023.
Transpower Engineering and Construction Limited | South Tongu | Chiefkope | planted | 2 | HT pole spans | 6 HT poles planted, 2 HT pole spans strung and 5 LV pole spans strung at Chiefkope as well as substations work completed at Dordoekope, Adzikope and Chiefkope respectively in Janua
Transpower Engineering and Construction Limited | South Tongu | Chiefkope | planted | 6 | HT poles | 6 HT poles planted, 2 HT pole spans strung and 5 LV pole spans strung at Chiefkope as well as substations work completed at Dordoekope, Adzikope and Chiefkope respectively in Janua
Transpower Engineering and Construction Limited | South Tongu | Bayive | planted | 2 | HT poles | The contractor planted 2 HT poles for transformer installation work at Bayive, dressed
Transpower Engineering and Construction Limited | South Tongu | Devevia | dressed | 10 | LV poles | The contractor dressed 10 LV poles at Devevia, 4HT poles and 9LV poles at Huadagbakope,
Transpower Engineering and Construction Limited | South Tongu | Fusesekope | dressed | 1 | HT pole | 1 HT pole and 16 LV poles dressed at Fusesekope, 14 HT poles and 30 LV poles dressed at
Transpower Engineering and Construction Limited | South Tongu | Deve Netideke all | dressed | 12 | LV poles | Sogbekope, 12 LV poles dressed at Deve Netideke all in January,2023.
Transpower Engineering and Construction Limited | South Tongu | Wlitey Extension | installed | 200 | single phase meters | installed 200 single phase meters at Wlitey Extension in February, 2023.
Transpower Engineering and Construction Limited | South Tongu | Wlitey Extension | installed | 6 | three phase meters | 300 single phase and 6 three phase meters were installed at Wlitey Extension, 90 single phase
Transpower Engineering and Construction Limited | South Tongu | Sogbekope | installed | 72 | single phase meters | meters installed at Nugblevi , 72 single phase meters installed at Sogbekope, 106 single phase meters installed at Adjahokope, 54 single phase meters installed at Deti and 110 sing
Transpower Engineering and Construction Limited | South Tongu | Adjahokope | installed | 106 | single phase meters | meters installed at Nugblevi , 72 single phase meters installed at Sogbekope, 106 single phase meters installed at Adjahokope, 54 single phase meters installed at Deti and 110 sing
Transpower Engineering and Construction Limited | South Tongu | Adjahokpe | strung | 12 | LV pole spans | 10 LV pole spans strung at Korvenu/ Anyiheme/Anyidzene, 12LV pole spans strung at Adjahokpe , 5HT poles and 75LV pole spans strung as well as 15 LV poles planted at Bayive Upgrade
Transpower Engineering and Construction Limited | South Tongu | Bayive Upgrade | strung | 15 | LV poles | 10 LV pole spans strung at Korvenu/ Anyiheme/Anyidzene, 12LV pole spans strung at Adjahokpe , 5HT poles and 75LV pole spans strung as well as 15 LV poles planted at Bayive Upgrade
Transpower Engineering and Construction Limited | South Tongu | Korvenu/ Anyiheme/Anyidzene | strung | 10 | LV pole spans | 10 LV pole spans strung at Korvenu/ Anyiheme/Anyidzene, 12LV pole spans strung at Adjahokpe , 5HT poles and 75LV pole spans strung as well as 15 LV poles planted at Bayive Upgrade
Transpower Engineering and Construction Limited | South Tongu | Bayive Upgrade | strung | 5 | HT poles | 10 LV pole spans strung at Korvenu/ Anyiheme/Anyidzene, 12LV pole spans strung at Adjahokpe , 5HT poles and 75LV pole spans strung as well as 15 LV poles planted at Bayive Upgrade
Transpower Engineering and Construction Limited | South Tongu | Avata | strung | 19 | LV pole spans | The contractor strung 19 LV pole spans at Avata, 28 LV pole spans strung at Sokpekope, 15 LV pole spans stung at Huadagbakope, 10 LV pole spans strung at Fusesekope and 12 LV pole
Transpower Engineering and Construction Limited | South Tongu | Huadagbakope | strung | 15 | LV pole spans | The contractor strung 19 LV pole spans at Avata, 28 LV pole spans strung at Sokpekope, 15 LV pole spans stung at Huadagbakope, 10 LV pole spans strung at Fusesekope and 12 LV pole
Transpower Engineering and Construction Limited | South Tongu | Deve Netideke | strung | 12 | LV pole spans | The contractor strung 19 LV pole spans at Avata, 28 LV pole spans strung at Sokpekope, 15 LV pole spans stung at Huadagbakope, 10 LV pole spans strung at Fusesekope and 12 LV pole
Kwanash Enterprise | Akatsi South | Kporwui | strung | 4 | LV poles | 2 HT poles spans strung , 4 LV poles planted, 29 LV pole spans strung at Kporwui in May,2023.
Kwanash Enterprise | Akatsi South | Kporwui | strung | 2 | HT poles | 2 HT poles spans strung , 4 LV poles planted, 29 LV pole spans strung at Kporwui in May,2023.
Kwanash Enterprise | Akatsi South | Gakpokope | installed | 102 | single phase meters | The contractor installed 102 single phase meters at Gakpokope, 35 single phase meters at Dadamey and 43 single phase meters at Maleme in June, 2023.
Kwanash Enterprise | Akatsi South | Gidisukope | planted | 6 | LV poles | The contractor planted 6 LV poles and strung 6 LV pole spans at Gidisukope, 27 HT and19 LV pole spans Strung at Lawui Avedzi, 8 HT and 20 LV pole spans strung at Lawui Avegadzi and
Kwanash Enterprise | Akatsi South | Lawui Kpota | strung | 11 | LV pole spans | The contractor planted 6 LV poles and strung 6 LV pole spans at Gidisukope, 27 HT and19 LV pole spans Strung at Lawui Avedzi, 8 HT and 20 LV pole spans strung at Lawui Avegadzi and
Kwanash Enterprise | Akatsi South | Kpevenu | strung | 7 | LV pole spans | 6 LV pole spans strung at Agblorkpo and 7 LV pole spans strung at Kpevenu
Kwanash Enterprise | Akatsi South | Agblorkpo | planted | 3 | LV poles | 3 LV poles planted and strung at Agblorkpo in February, 2026.
Stone Electrical Limited | Ho West | Tsito | planted | 8 | HT poles | The contractor planted 8 HT poles at Tsito
David & Sons Limited | Ketu North | Bagome | planted | 5 | LV poles | The contractor planted 5 LV poles and strung 6 LV pole spans at Bagome in May, 2023.The contractor awaits the supply of materials to continue work at Fiagbedu.
David & Sons Limited | Ketu North | Dorwuime/Savekor | strung | 6 | LV pole spans | 6 LV pole spans strung and substation work completed at Dorwuime/Savekor in February, 2024.
David & Sons Limited | Ketu North | Dorwuime/Savekor | planted | 5 | LV poles | Additional 5 LV poles planted and strung at Dorwuime/Savekor in May, 2024.
David & Sons Limited | Ketu North | Kpelikope/Avafe | planted | 1 | HT pole | The contractor planted 1 HT pole and dressed 21 HT poles at Kpelikope/Avafe in July, 2024.
David & Sons Limited | Ketu North | Kpelikope/Avafe | planted | 13 | LV poles | 2 LV poles planted and 13 LV poles spans strung at Kpelikope/Avafe in February, 2026.
David & Sons Limited | Ketu North | Kpelikope/Avafe | planted | 2 | LV poles | 2 LV poles planted and 13 LV poles spans strung at Kpelikope/Avafe in February, 2026.
Ideal Electrical Works | Ketu North | Atsiakope | strung | 15 | LV poles | The contractor strung 15 LV poles and also installed 58 single phase meters at Atsiakope,
Ideal Electrical Works | Ketu North | Adagbledu | strung | 60 | LV poles | 5 LV pole spans strung at Aglonukope, and 60 LV poles strung at Adagbledu in May,2023.
Ideal Electrical Works | Ketu North | Aglonukope | strung | 5 | LV pole spans | 5 LV pole spans strung at Aglonukope, and 60 LV poles strung at Adagbledu in May,2023.
Ideal Electrical Works | Ketu North | Adagbledu | strung | 13 | LV pole spans | 13 LV pole spans strung at Adagbledu in September 2023.
Ideal Electrical Works | Ketu North | Torve Agbornoe | planted | 6 | LV poles | 6 LV poles planted at Torve Agbornoe in April, 2024.
Ideal Electrical Works | Ketu North | Torve | strung | 5 | HT pole spans | 5 HT pole spans strung at Torve
Demsack Engineering Limited | Krachi West | Jerusalem | planted | 20 | LV poles | 20 LV poles planted at Jerusalem in May, 2024.
Demsack Engineering Limited | Krachi West | Old Chantai no | strung | 13 | HT pole spans | The contractor strung 13 HT pole spans at Old Chantai no.
Demsack Engineering Limited | Krachi West | Old Chantai no | strung | 5 | HT pole spans | 5 HT pole spans strung at Old Chantai no.
Demsack Engineering Limited | Krachi West | Old Chantai no | planted | 7 | HT poles | The contractor planted 7HT poles and strung 2HT pole spans at Old Chantai no.1&2 in May, 2025.
Demsack Engineering Limited | Krachi West | Old Chantai no | strung | 14 | HT pole spans | 14HT pole spans strung at Old Chantai no.1&2 in June, 2025.
Demsack Engineering Limited | Krachi West | Old Chantai no | planted | 24 | HT poles | The contractor planted 24 HT poles and strung 24 HT pole spans at Old Chantai no.1&2 in July, 2025.
Demsack Engineering Limited | Krachi West | Old Chantai no | planted | 12 | HT pole spans | 8 HT poles planted and 12 HT pole spans strung at Old Chantai no.1&2 in August, 2025.
Demsack Engineering Limited | Krachi West | Old Chantai no | planted | 8 | HT poles | 8 HT poles planted and 12 HT pole spans strung at Old Chantai no.1&2 in August, 2025.
Dass B Electrical Services Limited | Keta | Agbedrafor | strung | 52 | LV pole spans | The contractor strung 52 LV pole spans at Agbedrafor in May, 2023.
Mensklif Company Limited | Ho West | Nyekornakpoe | planted | 29 | LV poles | The contractor planted 29 LV poles at Nyekornakpoe in November 2022.
Mensklif Company Limited | Ho West | Nyekornakpoe | strung | 11 | LV pole spans | and 11LV pole spans strung at Nyekornakpoe in October, 2023 with some few defects to be
Mensklif Company Limited | Ho West | Nyekornakpoe | installed | 180 | single phase meters | The contractor installed 180 single phase meters at Nyekornakpoe in July 2024.
Mensklif Company Limited | Ho West | Abutia | installed | 4 | three phase meters | phase meters with 4No three phase meters and 175No single phase meters installed at Abutia
Addisco Electricals Ghana Limited | Nkwanta South | Kofie Akura | strung | 7 | HT pole spans | 7HT pole spans have been strung at Kofie Akura in October, 2023.
Addisco Electricals Ghana Limited | Nkwanta South | Kwadjo Heneba | planted | 30 | LV poles | The contractor planted 30 LV poles and strung 25LV pole spans at Kwadjo Heneba in November, 2024.
Addisco Electricals Ghana Limited | Nkwanta South | Portripor | strung | 7 | LV pole spans | 5 LV poles spans strung at Kwadjo Heneba as well as 7 LV pole spans strung and substation dressing completed at Portripor in January, 2025.
Addisco Electricals Ghana Limited | Nkwanta South | Kwadjo Heneba | strung | 5 | LV poles | 5 LV poles spans strung at Kwadjo Heneba as well as 7 LV pole spans strung and substation dressing completed at Portripor in January, 2025.
Addisco Electricals Ghana Limited | Nkwanta South | Kwadjo Heneba | planted | 5 | HT poles | The contractor planted 5HT poles at Kwadjo Heneba in May, 2025.
Saini Morrison Engineering Limited | South Tongu | Toklokpo | planted | 40 | LV poles | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Alavanyo | planted | 19 | LV pole spans | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Thunder Village | planted | 48 | LV pole spans | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Hlevi | planted | 6 | LV pole spans | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Alavanyo | planted | 52 | LV poles | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Thunder Village | planted | 64 | LV poles | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Hlevi | planted | 36 | LV poles | The contractor planted 40 LV poles and strung 33 LV pole spans at Toklokpo, 52 LV poles planted and 19 LV pole spans strung at Alavanyo, 64 LV poles planted and 48 LV pole spans st
Saini Morrison Engineering Limited | South Tongu | Thunder Village | strung | 4 | LV pole spans | 7 LV pole spans strung at Medical City II and 4 LV pole spans strung at Thunder Village in October 2022.
Dass B Electrical Services Limited | Ketu North | Agbovokorpe | planted | 26 | LV poles | The contractor planted and dressed 26 LV poles at Agbovokorpe.
Jenak Electrical Engineering Limited | Nkwanta South | Kpanja Akura | strung | 38 | LV pole spans | 38 LV pole spans strung at Kpanja Akura in March,
Jenak Electrical Engineering Limited | Nkwanta South | B | planted | 70 | LV poles | (Please Note 70 LV poles have already been planted at B.
Jenak Electrical Engineering Limited | Nkwanta South | Asomdwe Akura | planted | 22 | LV poles | The contractor planted 22 LV poles and strung 22 LV pole spans at Asomdwe Akura, additional 1 LV pole planted and 55 LV pole spans strung at Charti,
Jenak Electrical Engineering Limited | Nkwanta South | Charti | planted | 55 | LV pole spans | The contractor planted 22 LV poles and strung 22 LV pole spans at Asomdwe Akura, additional 1 LV pole planted and 55 LV pole spans strung at Charti,
Jenak Electrical Engineering Limited | Nkwanta South | Charti | planted | 1 | LV pole | The contractor planted 22 LV poles and strung 22 LV pole spans at Asomdwe Akura, additional 1 LV pole planted and 55 LV pole spans strung at Charti,
Jenak Electrical Engineering Limited | Nkwanta South | Wanja Akura | planted | 30 | LV poles | 30 LV poles planted at Wanja Akura, 41 LV poles planted at Kofi Akura and 37 LV poles planted at Bisani in May, 2024.
Johome Company Limited | North Tongu | Atsiekpoe- Ext | strung | 30 | LV pole spans | 30 LV pole spans strung at Atsiekpoe- Ext.
Johome Company Limited | North Tongu | Ngokpoe | strung | 11 | HT pole spans | poles including transformer poles and strung 11 HT pole spans at Ngokpoe in July, 2025.
Johome Company Limited | North Tongu | Vome Ext | strung | 9 | HT pole spans | The contractor strung 9 HT pole spans and 6 HT pole spans at Vome Ext.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 50 | HT poles | The contractor planted 20 LV, 38, 90, 50 HT poles at C K Kope, Akposo Okrabe, Nkonya Adzamanasu and Ampekrom respectively.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 35 | LV poles | 40 LV poles planted and 35 LV poles span strung at C K Kope in January, 2023.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 40 | LV poles | 40 LV poles planted and 35 LV poles span strung at C K Kope in January, 2023.
Addisco Electricals Ghana Limited | Biakoye | C K kope | planted | 19 | HT poles | The contractor planted 19 HT poles and 13 LV poles, strung 33LV pole spans at C K kope in February, 2023.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 10 | HT pole spans | One (1) additional HT pole planted and 10 HT pole spans strung at C K Kope with 10 LV pole spans strung at kortokofe in March, 2023.
Addisco Electricals Ghana Limited | Biakoye | Akposo Okrabe | planted | 26 | LV pole spans | 31 LV poles planted and 26 LV pole spans strung at Akposo Okrabe in August 2023.
Addisco Electricals Ghana Limited | Biakoye | Akposo Okrabe | planted | 31 | LV poles | 31 LV poles planted and 26 LV pole spans strung at Akposo Okrabe in August 2023.
Addisco Electricals Ghana Limited | Biakoye | Nkonya Adzamanasu | strung | 30 | LV pole spans | The contractor strung 30 LV pole spans at Nkonya Adzamanasu in July 2024.
Addisco Electricals Ghana Limited | Biakoye | Nkonya Adzamanasu | strung | 56 | LV pole spans | 56No LV pole spans strung at Nkonya Adzamanasu in August 2024.
Addisco Electricals Ghana Limited | Biakoye | Nkonya Adzamanasu | strung | 4 | LV pole spans | 4 LV pole spans strung at Nkonya Adzamanasu in January, 2025.
Addisco Electricals Ghana Limited | Biakoye | Odormitor Bumbula | strung | 2 | HT pole spans | 2 HT pole spans strung at Odormitor Bumbula in February, 2025.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 10 | LV pole spans | Additional 3 LV poles planted and 10 LV pole spans strung at C K Kope in May, 2025.
Addisco Electricals Ghana Limited | Biakoye | C K Kope | planted | 3 | LV poles | Additional 3 LV poles planted and 10 LV pole spans strung at C K Kope in May, 2025.
Addisco Electricals Ghana Limited | Biakoye | Akposo Okrabe | strung | 2 | HT pole spans | The contractor strung 2 HT pole spans at Akposo Okrabe in June, 2025.14 HT pole spans strung at Akposo Okrabe in September, 2025.
Addisco Electricals Ghana Limited | Biakoye | Akposo Okrabe | strung | 14 | HT pole spans | The contractor strung 2 HT pole spans at Akposo Okrabe in June, 2025.14 HT pole spans strung at Akposo Okrabe in September, 2025.
Addisco Electricals Ghana Limited | Biakoye | C.K | strung | 2 | HT pole spans | 2 HT pole spans strung at C.K.
Addisco Electricals Ghana Limited | Biakoye | Tapa Biposu | planted | 25 | LV poles | The contractor planted 25 LV poles at Tapa Biposu in March, 2026.
Addisco Electricals Ghana Limited | Biakoye | Tapa Biposu | strung | 20 | LV pole spans | 20 LV pole spans strung at Tapa Biposu in April, 2026.
Johome Company Limited | Ho West | Dzolokpuita | planted | 5 | HT poles | The contractor planted 5 HT poles, 12 LV poles planted and strung at Dzolokpuita
Johome Company Limited | Ho West | Dzolokpuita Assembly Site | strung | 3 | HT poles | 3HT poles spans strung at Dzolokpuita Assembly Site in June, 2023.
Johome Company Limited | Ho West | Dzolokpuita Assembly | planted | 23 | LV poles | The contractor planted 23 LV poles and strung 11 LV pole spans at Dzolokpuita Assembly
Johome Company Limited | Ho West | Kpenoe Agadzi Zone June | planted | 15 | LV poles | 15 LV poles planted and strung at Kpenoe Agadzi Zone June, 2023.
Johome Company Limited | Ho West | Aklamakpetoe | planted | 17 | LV poles | The contractor planted 17 LV poles and strung 15 LV pole spans at Aklamakpetoe as well as 39 LV poles planted and strung at Kpenoe-Agadzi Zone 2 in February, 2025.
Demsack Engineering Limited | Nkwanta South | Mem Akura | planted | 68 | LV poles | The contractor planted 68 LV poles and strung 56 LV pole spans at Mem Akura , 10 LV poles planted at Mantsei Akura and 20 HT pole spans strung at Sowyer in November 2022.
Demsack Engineering Limited | Nkwanta South | Sowyer | planted | 20 | HT pole spans | The contractor planted 68 LV poles and strung 56 LV pole spans at Mem Akura , 10 LV poles planted at Mantsei Akura and 20 HT pole spans strung at Sowyer in November 2022.
Demsack Engineering Limited | Kpando | Avega | planted | 10 | HT poles | 10 HT poles planted at Avega in January, 2023.
Demsack Engineering Limited | Kpando | Avega | planted | 6 | LV poles | The contractor planted 6 LV poles and strung 5 LV poles spans at Avega , 44 LV poles planted and strung 43 LV poles spans at Asikakrom in June, 2023.
Demsack Engineering Limited | Kpando | Asikakrom | planted | 43 | LV poles | The contractor planted 6 LV poles and strung 5 LV poles spans at Avega , 44 LV poles planted and strung 43 LV poles spans at Asikakrom in June, 2023.
Demsack Engineering Limited | Kpando | Asikakrom | planted | 44 | LV poles | The contractor planted 6 LV poles and strung 5 LV poles spans at Avega , 44 LV poles planted and strung 43 LV poles spans at Asikakrom in June, 2023.
Demsack Engineering Limited | Kpando | Avega | strung | 8 | HT pole spans | 2 respectively as well as strung 8 HT pole spans at Avega in August, 2023.
Energy Works Limited | Nkwanta North | Ujagandor | planted | 55 | HT poles | The contractor planted 55 HT poles and 46 HT pole spans strung at Ujagandor in February, 2024.
Energy Works Limited | Nkwanta North | Obunja | planted | 34 | HT poles | The contractor planted 34 HT poles at Obunja in September, 2024.
Energy Works Limited | Nkwanta North | Ogando | planted | 17 | LV poles | The contractor planted 17 LV poles and 16 LV pole spans strung at Ogando, 26 LV poles planted and 22 LV pole spans strung at Ujagandor as well as 80 LV poles planted with 40 LV pol
Energy Works Limited | Nkwanta North | Ujagandor | planted | 22 | LV pole spans | The contractor planted 17 LV poles and 16 LV pole spans strung at Ogando, 26 LV poles planted and 22 LV pole spans strung at Ujagandor as well as 80 LV poles planted with 40 LV pol
Energy Works Limited | Nkwanta North | Ujagandor | planted | 26 | LV poles | The contractor planted 17 LV poles and 16 LV pole spans strung at Ogando, 26 LV poles planted and 22 LV pole spans strung at Ujagandor as well as 80 LV poles planted with 40 LV pol
Energy Works Limited | Nkwanta North | Obunja | planted | 16 | HT poles | The contractor planted additional 16 HT poles and strung 67 HT pole spans at Obunja in November, 2024.
David & Sons Limited | Nkwanta South | Panku Akura | planted | 39 | HT poles | The contractor planted and strung 39 HT poles at Panku Akura, 24 HT poles planted at Dain Akura and 32 HT poles at Krachi Akura in September, 2022.
David & Sons Limited | Nkwanta South | Krachi Akura | planted | 32 | HT poles | The contractor planted and strung 39 HT poles at Panku Akura, 24 HT poles planted at Dain Akura and 32 HT poles at Krachi Akura in September, 2022.
David & Sons Limited | Nkwanta South | Alukpatsa | planted | 38 | HT poles | 38 HT poles were planted at Alukpatsa in November 2022.
David & Sons Limited | Nkwanta South | Krachi Akura | planted | 74 | LV poles | The contractor planted 74 LV poles at Krachi Akura in December, 2022.
David & Sons Limited | Nkwanta South | Krachi Akura | planted | 60 | LV pole spans | Additional 5 LV poles planted and 60 LV pole spans strung at Krachi Akura in October, 2024.
David & Sons Limited | Nkwanta South | Krachi Akura | planted | 5 | LV poles | Additional 5 LV poles planted and 60 LV pole spans strung at Krachi Akura in October, 2024.
David & Sons Limited | Nkwanta South | Alukpatsa Kotokro | planted | 30 | LV poles | 30 LV poles planted at Alukpatsa Kotokro in December, 2024.
Demsack Engineering Limited | Nkwanta North | Kpassa East Extension | planted | 10 | LV poles | The contractor planted 10 LV poles and strung 86 LV pole spans at Kpassa East Extension in March, 2023.
Demsack Engineering Limited | Nkwanta North | Aboete | planted | 21 | HT poles | The contractor planted 21HT poles and strung 20HT pole spans at Aboete in July, 2023.
Demsack Engineering Limited | Nkwanta North | Aboete | planted | 20 | LV pole spans | 9 LV poles planted and 20 LV pole spans strung at Aboete in October, 2023.
Demsack Engineering Limited | Nkwanta North | Aboete | planted | 9 | LV poles | 9 LV poles planted and 20 LV pole spans strung at Aboete in October, 2023.
Demsack Engineering Limited | Nkwanta North | Aboete | planted | 11 | HT poles | Due to changes on the HT network construction, 11 HT poles were removed and an additional 16 LV poles planted at Aboete in February, 2025.
Demsack Engineering Limited | Nkwanta North | Lemina | planted | 51 | HT poles | The contractor planted 51 HT poles at Lemina, 23 HT poles at Majemaje and 8 HT poles at Gbosike.
Demsack Engineering Limited | Nkwanta North | Lemina | planted | 67 | LV poles | The contractor planted 84 HT and 67LV poles at Lemina, 35 LV poles at Majemaje, 25 LV poles at Anomantu and 32 LV poles Gbosike in March, 2024.
Demsack Engineering Limited | Nkwanta North | Lemina | planted | 68 | LV pole spans | Pole planted and 68 LV pole spans strung at Lemina, 35 LV pole spans strung at Majimaji,
Demsack Engineering Limited | Nkwanta North | Majimaji | strung | 35 | LV pole spans | Pole planted and 68 LV pole spans strung at Lemina, 35 LV pole spans strung at Majimaji,
Demsack Engineering Limited | Nkwanta North | Gbosike | strung | 3 | LV poles | 24 LV pole spans strung at Anomantu and additional 3 LV poles planted and 5 LV pole spans strung at Gbosike in May, 2024.
Demsack Engineering Limited | Nkwanta North | Gbosike | strung | 30 | LV pole spans | The contractor strung 30 LV pole spans at Gbosike in June, 2024.
Demsack Engineering Limited | Nkwanta North | Lemina | strung | 100 | HT pole spans | The contractor strung 100HT pole spans at Lemina , 18HT pole spans at Majemaje and 6HT pole spans at Gbosike in December,2024.
Demsack Engineering Limited | Nkwanta North | Lemina | planted | 34 | HT poles | The contractor planted 34 HT poles and strung 52 HT pole spans at Lemina, 26 HT poles planted and strung as well as 35 LV poles planted and strung at Gbango, Substation works compl
Demsack Engineering Limited | Nkwanta North | Gbango | planted | 35 | LV poles | The contractor planted 34 HT poles and strung 52 HT pole spans at Lemina, 26 HT poles planted and strung as well as 35 LV poles planted and strung at Gbango, Substation works compl
Demsack Engineering Limited | Nkwanta North | Gbango | planted | 26 | HT poles | The contractor planted 34 HT poles and strung 52 HT pole spans at Lemina, 26 HT poles planted and strung as well as 35 LV poles planted and strung at Gbango, Substation works compl